## Speaker
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Define Battery Life and Charging Requirements | 1 | 5 |  |  | 0%
Define Connectivity Requirements | 1 | 5 |  |  | 0%
Define Size and Noise Output Requirements | 1 | 5 |  |  | 0%
Select appropriate battery | 6 | 2 |  |  | 0%
Select appropriate drivers | 8 | 2 |  |  | 0%
Select appropriate speaker casing | 10 | 2 |  |  | 0%
Select appropriate bluetooth module / microcontroller | 12 | 2 |  |  | 0%
Ensure chosen components are compatible | 14 | 4 |  |  | 0%
Order required components | 18 | 2 |  |  | 0%
Design Speaker Housing | 20 | 4 |  |  | 0%
PCB Circuit Design | 20 | 7 |  |  | 0%
Build Prototype | 27 | 2 |  |  | 0%
Test Protoype | 29 | 7 |  |  | 0%
Make Changes following testing | 36 | 5 |  |  | 0%
Re-test | 41 | 5 |  |  | 0%
Evaluate | 46 | 5 |  |  | 0%
Suggest Improvements | 51 | 5 |  |  | 0%
Report Write | 56 | 5 |  |  | 0%
Create Presentation of Findings | 61 | 5 |  |  | 0%
Time Buffer for delays | 66 | 11 |  |  | 0%