## Appendix One
Project Risk Log | Project: | PSCM22, Park Street, Cambridge
(To be updated weekly)
Risk no. | Description | Probability | Impact | Countermeasures | Estimated time/cost | Owner | Date entry last updated
1 | Site flooding | Medium | Medium | Pump available for use on site; excavate during dry periods | One week; ,£5000 for drainage. Contractor pumps may be used. | AM | 2022-12-10
2 | Presence of modern hazardous materials | Medium | Low | Pre-excavation inspection by qualified individuals; removal if necessary. All staff on site required to have asbestos awareness training | One week; <£5000 to clear | AM | 2022-12-10
3 | Staff injury and related absence | Medium | Medium | Detailed Risk Assessment and Health and Safety policy. Manual handling training. | Variable | AM | 2022-12-10
4 | Theft or damaging of equipment | Low | Medium | On-site security provided by client; lock all equipment away securely | Variable | AM | 2022-12-10