RISK ASSESSMENT

The ratings use a simple 1–5 scale, where:

- Likelihood: 1 = Very Low, 5 = Very High

- Impact: 1 = Negligible, 5 = Critical

- Risk Score = Likelihood × Impact

# Project 1: Redevelopment of the Central Transport Hub

| Risk | Likelihood | Impact | Risk Score | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Planning permission delays | 3 | 5 | 15 | Engage planning authorities early and submit documentation promptly. |
| Budget overruns due to inflation | 4 | 5 | 20 | Include contingency budget (10–15%) and regularly review costs. |
| Unexpected structural defects | 3 | 5 | 15 | Conduct comprehensive structural surveys before construction begins. |
| Contractor performance issues | 3 | 4 | 12 | Select experienced contractors and monitor performance using KPIs. |
| Public disruption and complaints | 4 | 3 | 12 | Implement stakeholder communication plans and phased construction schedules. |
| Health and safety incidents | 2 | 5 | 10 | Enforce health and safety regulations and conduct regular inspections. |
| Supply chain shortages | 3 | 4 | 12 | Identify alternative suppliers and maintain buffer stock for critical materials. |
| Environmental compliance issues | 2 | 4 | 8 | Carry out Environmental Impact Assessments and ensure regulatory compliance. |

# Project 2: Temporary Multimodal Transport Solution

| Risk | Likelihood | Impact | Risk Score | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Temporary facilities fail to meet demand | 4 | 4 | 16 | Conduct demand forecasting before implementation. |
| Traffic congestion increases | 4 | 4 | 16 | Develop detailed traffic management plans with local authorities. |
| Poor public acceptance | 3 | 3 | 9 | Run public awareness campaigns and provide regular updates. |
| Delays in installing temporary infrastructure | 3 | 4 | 12 | Procure equipment early and monitor supplier delivery schedules. |
| Increased operational costs | 3 | 4 | 12 | Allocate contingency funds and monitor expenditure monthly. |
| Equipment failure | 2 | 4 | 8 | Schedule preventive maintenance and maintain spare equipment. |
| Severe weather affecting temporary structures | 3 | 5 | 15 | Design temporary facilities to appropriate safety standards and prepare emergency response plans. |
| Coordination failure between transport providers | 3 | 4 | 12 | Establish clear governance structure and regular coordination meetings. |

# Project 3: Digital Modernisation of Passenger Flow and Logistics Coordination

| Risk | Likelihood | Impact | Risk Score | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Cybersecurity breach | 4 | 5 | 20 | Implement robust cybersecurity controls, encryption, and regular security testing. |
| Software implementation delays | 3 | 4 | 12 | Use Agile project management and phased implementation. |
| Resistance to technological change | 4 | 4 | 16 | Deliver user training and change management programmes. |
| Data migration failures | 3 | 5 | 15 | Perform multiple testing phases and maintain secure backups. |
| System downtime | 3 | 5 | 15 | Develop disaster recovery and business continuity plans. |
| Budget overrun | 3 | 4 | 12 | Monitor project costs and implement stage-gate approvals. |
| Integration issues with legacy systems | 4 | 4 | 16 | Conduct compatibility testing and involve technical specialists early. |
| GDPR and data privacy breaches | 2 | 5 | 10 | Ensure compliance with GDPR and conduct privacy impact assessments. |

# Project 4: Sustainable Redesign to Meet Net-Zero Objectives

| Risk | Likelihood | Impact | Risk Score | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Green technologies exceed budget | 3 | 5 | 15 | Conduct life-cycle costing and prioritise high-value investments. |
| Delays in obtaining environmental approvals | 3 | 4 | 12 | Engage regulators during project planning and prepare documentation early. |
| Shortage of sustainable materials | 4 | 4 | 16 | Develop multiple supplier agreements and secure early procurement. |
| Stakeholder disagreement over sustainability priorities | 3 | 4 | 12 | Facilitate stakeholder workshops and regular consultation. |
| Failure to achieve carbon reduction targets | 2 | 5 | 10 | Monitor KPIs continuously and adjust project scope where necessary. |
| New environmental regulations introduced during project | 2 | 4 | 8 | Monitor legislative changes and maintain regulatory compliance reviews. |
| Public opposition to redesign | 3 | 3 | 9 | Conduct community engagement and consultation throughout the project. |
| Extreme weather affecting construction | 3 | 5 | 15 | Build weather contingencies into the schedule and develop emergency plans. |

# Risk Matrix (Visual Aid)

| Impact ↓ / Likelihood → | 1 | 2 | 3 | 4 | 5 |
| --- | --- | --- | --- | --- | --- |
| 5 Critical | Low | Medium | High | Extreme | Extreme |
| 4 Major | Low | Medium | High | High | Extreme |
| 3 Moderate | Low | Medium | Medium | High | High |
| 2 Minor | Low | Low | Medium | Medium | High |
| 1 Negligible | Low | Low | Low | Low | Medium |

Colour Guide (for slides):

- 🟢 Low Risk (1–5): Monitor periodically.

- 🟡 Medium Risk (6–10): Assign an owner and monitor regularly.

- 🟠 High Risk (11–15): Develop mitigation plans and review frequently.

- 🔴 Extreme Risk (16–25): Immediate management attention and contingency planning required.

## Classroom Activity

Now over to you:

- Select one of the four projects.

- Add five additional project-specific risks.

- Score each risk using the likelihood × impact matrix.

- Justify why they assigned those scores.

- Propose realistic mitigation strategies.

- Identify the three highest-priority risks and explain how they would monitor them throughout the project.

This activity not only reinforces the theory of risk management but also develops students' analytical, decision-making, and stakeholder management skills by applying concepts to realistic project scenarios.