## Sheet1
Bluetooth Speaker
Bluetooth Speaker LTD | Mon, 15/6/2026
Mathew George | Mon, 15/6/2026 |  | JUNE | [16 empty] | JULY | [30 empty] | AUGUST
|  |  | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11
|  |  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 23 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29
TASK | START | END | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Define Requirements | bar: END
Initial Concept | 2026-06-15 | END: 2026-06-27
Setting Limits | 2026-06-20 | END: 2026-06-27
Research | 2026-06-20 | END: 2026-06-30
Specifications | 2026-06-22 | END: 2026-07-01
Planning | bar: END
Indentifiy Activities | 2026-06-28 | END: 2026-07-11
Goals and Objectives | 2026-07-06 | END: 2026-07-15
Set and Monitor Milestones | 2026-06-07 | END: 2026-07-18
Monitoring | bar: END
Monitoring and Record Achievements | 2026-06-15 | END: 2026-08-15
Implementing | bar: END
Finalise exact components | 2026-07-12 | END: 2026-07-21
Building the final product | 2026-07-19 | END: 2026-08-08
Testing & Evaluation | bar: END
Final Checks | 2026-08-09 | END: 2026-08-15
Verify the functions of the product | 2026-08-12 | END: 2026-08-19
Evaluation Methods | 2026-08-18 | END: 2026-08-22
Compare Outcome to original Spec | 2026-08-20 | END: 2026-08-24
Reporting | bar: END
Report Back | 2026-08-23 | END: 2026-08-29