Student name: Zachury Shane Jassi

Student id: 2017021

Programme: BA (hons) Leadership and management skills in the workplace

Module: BMSW 5104

Lecturer: Sujeewa Herath

Assignment title: Project management plan

Module title: managing projects in organizations

Table of contents

Cover page………………………………………………………………..………….…….…. page 1

Table of contents…………………………………………………………………………….…page 2

Introduction………………………………………………………………………………......…page 3

Basic project outline…………………………………………………………………...………page 3

Project scope……………………………………………………….…………………...…......page 4

Quad chart………………………………………………………………………………………page 5

Table 1 Quad chart grid……………………….………………………………………………page 5

Stake holder analysis………………………………………………………………………….page 6

Definition and importance of stakeholder grid of influence………………………………..page 6

Table 2 stakeholder grid of influence……………………………………………………......page 6

High power low interest stakeholders…………………………………………………….….page 6

High power high interest stake holders……………..…………………………………….…page 6

Low power low interest stakeholders………………………………………………………...page 7

Low power high interest stakeholders………………………………………………………..page 7

stakeholder engagement………………………………………………………………………page 7

Table 3 Stakeholder engagement plan………………………………………………….…page 7-8

Work breakdown structure……………………….……………………………………………page 8

Explanation of a few of the important tasks within the work breakdown structure...……page 8

Table 4 Work breakdown structure table………………...………………………………….page 9

Project schedule/Gantt chart………………….…………………………………………….page 10

Importance of a project schedule……………………………………………...……………page 10

Table 5 Gantt chart…………………………………………………………………………...page 10

Table 6 Consideration of resources………………………………………………………...page 11

Importance of resource planning……………………………………………………………page 11

Table 7 Risk assessment……………………………………………………………………page 12

Importance of a risk assessment……………………………………………………………page 12

Reference list……………………………………………………………………...………page 13-14

Introduction

This project management plan will cover the launch of a new improved child day care facility for children of the parents who will be returning back to work after the covid 19 pandemic. The project plan will use graphs and charts to analyse and assess each factor of the project plan, demonstrating the application of project management methods, techniques, and approaches. This project management plan will provide a detailed project scope recognising the main tasks to be carried out in order to complete the project, a stake holder analysis analysing the power each stakeholder possesses within the project and recognise forms of communication amongst stakeholders, the plan will also cover a work break down structure providing a breakdown of the tasks to be carried out along with a risk assessment and project deliverables.

Basic project outline

The aim of the project is to create a safe secure nursery for the children of parents who are returning back to work after the covid 19 pandemic. Due to the changes in operation of companies for example following safety guidelines like social distancing and hygiene rules and regulations. Allowing a safe environment for the children is essential in the project. Therefore, the aim is to provide a suitable equipped building with all the relevant security measures in place for example fencing around the property and safe parking on site. A team of certified trained and professional staff with relevant DBS checks to provide structured learning and help prepare the children for later education. The nursery will be registered with the country’s specific regulator and aim to meet the standards of the EYFS to an outstanding level. The nursery will have a structured workforce that will consist of cooks, meeting all dietary requirements, cleaners that will adhere to all covid 19 requirements to keep staff and children safe at all times, a caretaker to keep up general maintenance of the premises and to ensure the premiss is practicing a high quality of health and safety procedures continuously.

Project scope

The purpose of providing a project scope is to provide a comprehensive summary of all the aspects the project will cover, and to give an understanding of what the project is about. including all the activities needed to be conducted, a time frame or timelines, an understanding of resources needed to complete the project and to also identify stakeholders, needed for the project. (K. Fageha, 2013)

- Locate a suitable location with safe and appropriate surroundings for a nursery

- Arrange purchase, rent, or property lease

- Identify, arrange, and complete all relevant renovation work on the property

- Interior design, creating suitable environment for children

- Ensuring essential and appropriate safety features

- Provide suitable facilities e.g., toilets, kitchens, caretaker facilities, reception area, and a suitable car park.

- Register with the country’s specific regulator

- Ensure the standards of the (EYFS) are met

- Select qualified experienced staff with relent DBS checks

- Opening ceremony, Discount for opening ceremony

- Marketing

- Pay workers payment

- Tax, national insurance

- Cleanliness, arrange cleaners

- Accident, health, and safety

- Arrange food suppliers

- Staff training

- Pay in alignment with national minimum wage

- Arrange and agree relevant cleaning company/ arrange times and dates

- Arrange relevant contractors

- Agree caterers and dietary requirements

- Obtain relative insurances

- Ensure all health and safety measures are met

- Adhere to covid 19 regulations

- Plane to beat competitors/ research local nursery prices

- Arrange pricing structure

- Create social media

- Create branding

- Provide uniforms for staff

- Research relevant financing options

- Decide and apply for funding

- Design website

Quad chart

A quad chart is used for planning and communication objectives. Typically, in the form of a grid or table. A quad chart can allow a descriptive and visual demonstration of a project as well as provide an extensive explanation of what a project consists of. A quad chart can allow the structuring of tasks, concepts and ideas within the project planning stages, a quad chart consists of a table with four sections, the project purpose, allowing an understanding of who or what the project would benefit, stakeholders, which can help identify the stakeholders within the project and who will be involved in the project, desired result of the project, highlighting the goals of the project and identifying what makes a success of the project, measure of success, which can allow an understanding of when the project would be completed and factors that determine if the project was successful or not. (Keenan, 2020)

Table 1 quad chart Grid

| Purpose | Customers |
| --- | --- |
| - To create a safe, accessible nursery - Provide childcare for parents returning to work after covid 19 pandemic - Allow accessible childcare for the local community - Help prepare children for further education - The nursery provides structured learning experiences and cares for children - Create more jobs within the local community for example, teachers, cooks, cleaners, care takers | - The project is for parents who need to return to work after the covid 19 pandemic. - Children and parents in the local community will benefit from safe and secure childcare - Employees, nursery staff including cooks, teachers, cleaners, and caretakers - Stakeholders - Estate agent - Bank |
| Desired result | Measures of success |
| - Suitable location for childcare - A large building, with parking gates around building, - several rooms including kitchen, office, Toilets etc. - A team of helpful trained staff - Reasonable competitive childcare rates - A safe secure environment for children and parents | - Feed back form customers staff and the local community - Reviews from customers/parents - Quality - Time frame in which the project is completed - Number of students that attended the nursery - Number of successful applications submitted to the nursery |

Stakeholder analysis

A stakeholder analysis can be identified as an incredibly useful project management tool that consists of identifying any persons or groups that have invested, have an interest or some involvement with the project. This tool is used to identify stakeholders, their views, and the impact the project may have on them. A stake holder analysis is incredibly important for a project plan outlining the important persons that communication is essential with throughout the progression of the project. (ProductPlan, 2018)

Definition and importance of a stakeholder grid of influence

A stakeholder grid of influence allows a detailed evaluation of the influence each stake holder posses within the project. The grid can be used to categorize stakeholders based upon the power and influence they have towards the project. This tool has significant importance for prioritizing each stake holder. Ensuring the correct amount of communication is provided for each category of stakeholder throughout the project. (Mithun Sridharan, 2019)

Table 2 stake holder gride of influence

| High power low interest | High power high interest |
| --- | --- |
| - Council - Government - Education body - Caterers | - Bank - Sponsors - Shareholders - Parents |
| Low power low interest | Low power high interest |
| - Community | - Children - Staff |

High power low interest stakeholders

Organizations, groups, or individuals within this category posses a considerable influence on the project but have minimum investment in the success of the project, although it is incredibly important to keep these stakeholders informed and pleased and to ensure their requests are fulfilled, as theses stakeholder may have the authority to alter or avert the completion of the project. It is essential to keep this type of stake holder satisfied.

High power high interest stakeholders

High power high interest stakeholder posses a great power within the project and can have a significant impact on the outcome of the project. It is incredibly important to practice a prominent level of engagement and communication amongst theses stakeholders ensuring they are content and happy with each step of the project. It is essential to manage these types of stake holders closely. (Every, 2020)

Low power low interest stakeholder’s

The stakeholders within this group are likely to be affected by the project and the company’s behavior, although this group of stakeholder has no capital investment in the project or interest in the success of the project. For example, this group applies to members of the public or in the case of the nursery project the community in which the nursery operates. It is important to monitor and share relevant information within this group of stakeholders to create a more investable environment for the project. Allowing these types of stakeholders to gain an idea of project goals. (Shethna, 2016)

Low power high interest stakeholder’s

This category of stakeholder’s usually consists of the local community and employees within the project, although these stakeholders have less control on the key decisions within the project, they still possess a high interest in the success of the project. It is incredibly important to keep these types of stakeholders informed and involved as feedback from these stakeholders could be beneficial in the overall success of the project.

Stakeholder engagement

Stakeholder engagement can be known as the level of communication provided to each stakeholder, and the way each stake holder is managed and involved in the project. Stakeholder engagement is extremely important and beneficial throughout the project. A proficient level of stakeholder engagement could benefit the organization and create a positive impact. Forms of stakeholder engagement could include, involving stakeholders with project decision making, building relationships with stakeholders, and keeping stakeholders informed. Stakeholders can help guide and highlight issues and problems within the project. (APM, 2013)

Table 3 Stakeholder engagement plan

| Stakeholders | Engagement plan |
| --- | --- |
| High power low interest stakeholders - Council - Government - Education body - Caterers | - Provide project feedback - Regular updates via letters and emails - Form partnerships - Build relationships - Involve in decision making - Allow advice and guidance - Conferences - Open forums for discussion |
| High power high interest stakeholders - Bank - Sponsors - Shareholders - Parents | - Keep up to date with each aspect of the project - Involve with project panning - Involve with project research - Partnership agreements - Communicate progression results and outcomes regularly |

| Stakeholders | Engagement plan |
| --- | --- |
| Low power low interest stakeholders - Community | - Provide newsletters - Social media and websites - New articles - Letters and emails - Advertisements |
| low power high interest stakeholders - Children - Staff | - Regular progression updates - Meetings - Focus groups - Regular emails - Ask for feedback - Allow reviews |

Work breakdown structure

A work breakdown structure is an incredibly useful project management tool. A WBS consists of a breakdown of the project scope allowing a simplified structure of tasks that need to be completed in order to achieve success of the project plan. A WBS can provide a clear overview of the project, demonstrating the responsibilities and resources needed within the project. A WBS can also be used as a check list to ensure each task has been carried out successfully. A WBS can be implemented with the use of a table, chart, or mind map. (PMP, 2019)

Explanation of a few of the important tasks within the work breakdown structure

Locating a suitable building and location is essential for the project. The building needs to provide safe and secure facilities for childcare and also be in an accessible location within the community, with access to a car park for parents and visitors. It’s essential that the correct building is chosen and is able to facilitate childcare.

Recruiting highly trained staff is essential for the project. Staff must be qualified and have all relevant checks and be experienced with childcare. Staff must be able to follow all health and safety procedures to a high standard.

Health and safety is an important factor of the project. The nursery must comply with all government policies to lower the spread of coronavirus and all safety measures must be successfully put in place. The project must provide safe childcare and an excellent approach to controlling the spread of corona virus.

Table 4 Work breakdown structure table

| Planning | Finance | staff | Design | building | Marketing | Children | Safety |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Locate a suitable building for a nursery | Arrange discount for opening ceremony | Recruit qualified staff with relevant DBS check | Decide on interior design | Arrange builders’ times and dates | Create and design social media | Register with country’s specific regulator | Accident health and safety |
| Plan opening ceremony | Plan to beat competitors | Arrange cleaners’ times and dates needed | Create suitable environment for children | Arrange appropriate revocation on the property | Create and design website | Diet requirements | Ensure appropriate and essential safety features |
| Plan to beat competitor | Arrange staff payments in line with national minimum wage | Arrange caterers and food supply in line with diet requirements |  | Arrange relevant contractors | Create and design brand |  | Ensure standards of the EYFS are met |
| Plan for car park | Arrange to pay builders And workers | Arrange relevant staff training |  | Build car park |  |  | Cleanliness |
| Arrange property rent or lease | Tax and national insurance | Provide uniforms |  | Ensure appropriate facilities e.g., toilet, kitchen Reception area |  |  | Adhere to health and safety regulations |
|  | Obtain relative Insurances | Arrange staff working hours |  |  |  |  | Diet requirements |
|  | Arrange pricing structure |  |  |  |  |  | Adhere to covid 19 requirements |
|  | Research finance options |  |  |  |  |  |  |
|  | Apply for finance |  |  |  |  |  |  |

Project schedule/Gantt chart

Importance of a project schedule

A project schedule, usually centered around the work break down structure can allow an organized list of all the task that need to be completed within the project plan, the project schedule organizes such tasks into an order of times and dates that each task needs to be completed by, in order to achieve successful progression of the project plan. (Singh, 2021)

Table 5 Gantt chart

| Tasks to be completed | Time scale per month |  |  |  |
| --- | --- | --- | --- | --- |
|  | 1 month | 2 months | 3 months | 4 months |
| Locate a suitable location with safe and appropriate surroundings for a nursery |  |  |  |  |
| Arrange purchase, rent, or property lease |  |  |  |  |
| Identify, arrange, and complete all relevant renovation work on the property |  |  |  |  |
| Interior design, creating suitable environment for children |  |  |  |  |
| Ensuring essential and appropriate safety features |  |  |  |  |
| Provide suitable facilities e.g., toilets, kitchens, caretaker facilities, reception area, suitable car park |  |  |  |  |
| Register with the country’s specific regulator |  |  |  |  |
| Ensure the standards of the (EYFS) are met |  |  |  |  |
| Select qualified experienced staff with relent DBS checks |  |  |  |  |
| Opening ceremony, Discount for opening ceremony |  |  |  |  |
| Marketing |  |  |  |  |
| Plan to beat competitors, research local nursery prices |  |  |  |  |
| Pay workers payments |  |  |  |  |
| Pay Tax, national insurance |  |  |  |  |
| Accident procedures, health and safety requirements |  |  |  |  |
| Arrange cleaning staff schedule |  |  |  |  |
| Arrange food suppliers and chiefs/kitchen staff |  |  |  |  |
| Provide any essential Staff training |  |  |  |  |
| Pay in alignment with national minimum wage |  |  |  |  |
| Arrange relevant contractors |  |  |  |  |
| Obtain dietary requirements |  |  |  |  |
| Obtain relative insurances |  |  |  |  |
| Adhere to covid 19 regulations |  |  |  |  |
| Arrange pricing structure |  |  |  |  |
| Create social media |  |  |  |  |
| Create branding |  |  |  |  |
| Provide uniforms for staff and relevant equipment |  |  |  |  |
| Research relevant financing options |  |  |  |  |
| Arrange extra fund-raising events |  |  |  |  |
| Decide and apply for funding |  |  |  |  |
| Design website |  |  |  |  |

Table 6 Consideration of resources

| People needed | Cost |
| --- | --- |
| Builders | £3000 |
| Designers | £1000 |
| Decorators | £1450 |
| Gardeners | £300 |
| Nursery staff | £3420 per month |
| Website/ social media designer | £600 |
| Events planner | £900 |
| Plumbers | £400 |
| Chief | £427 per month |
| Cleaner | £427 per month |
| Accountant | £50 per hour |
| electricians | £1000 |
| Financial needs | Cost |
| Staff wages | £3420 per month |
| Payroll taxes | £513 |
| Relative insurances | £600 per month |
| Rent | £2000 per month |
| Loan payments | £200 per month |
| Utility bills | £1400 |
| Equipment needs | Cost |
| Toys | £3000 |
| Cooking equipment | £1500 |
| Building equipment | £3000 |
| Decorating equipment | £600 |
| Gardening equipment | £200 |
| Cleaning equipment | £400 |
| Materials needed | Cost |
| Food | £300 |
| Cleaning products | £200 |
| Flooring | £3500 |
| Décor materials | £645 |
| Building materials | £4050 |
| Fencing materials | £1200 |
| Electrician materials | £600 |
| Plumbing materials | £670 |
| Staff uniform | £450 |
| Child entertainment | £2600 |
| Staff drinks machine | £1000 |

Budget of £40,000 + fund raising events to meet extra expenditures.

Importance of resource planning

Resource planning arranges, acknowledges, and highlights the resources needed to conduct the project successfully. Resources can be known as assets that are essential to accomplish a project. Resources could include equipment, people, tools, supplies, time, materials, and money. (Larrick, n.d.)

| Potential risks | Level of risk | Prevention and solutions |
| --- | --- | --- |
| Loss of stakeholders, investors, resulting in a loss of budget | Low | - Provide appropriate stakeholder engagement - Involve stake holders and investors within project - Stick to allocated budget for each task needed to be conducted - Provide effective communication with stakeholders and investors - Provide clear project visibility amongst stakeholders - Ensure extra fund raising is successful |
| Exceeding project time scale, goals, deliverables | high | - Ensure work breakdown structure is followed critically - Ensure each task/goal is completed successfully before starting another - Ensure correct hiring of contractors needed - Provide contractors with clear instructions - Stick within allocated budget |
| Covid 19 outbreak, lockdowns, government regulations | high | - Ensure all government procedures are adhered to at a high standard - Provide all safeguarding policies are in place correctly - Ensure the correct practice of social distancing - Closely monitor government recommendations on covid 19 safety |
| Not being able to obtain correct licensing or insurance | low | - Ensure applications are produced correctly - Ensure applications are submitted within specified time limits - Ensure premises meets the standards of EYFS and regulators - Ensure a prominent level of building quality - Ensure an elevated level of health and safety within the building |

Table 7 Risk assessment

Importance of a risk assessment

A risk assessment is an incredibly crucial tool within project management, using a risk assessment could help to prevent risks and determine ways of avoiding risks within the project, risks within the project pose a great inconvenience and could slow down project progression resulting in poor time quality and cost management. (Frederick, 2016)

Reference list

APM (2013). Stakeholder Engagement. [online] Apm.org.uk. Available at: https://www.apm.org.uk/resources/find-a-resource/stakeholder-engagement/.

Every, P. (2020). Stakeholder Management using the Power Interest Matrix. [online] Solitaire Consulting Limited. Available at: https://www.solitaireconsulting.com/2020/07/stakeholder-management-using-the-power-interest-matrix/

Frederick, T. (2016). The Importance of Risk Management on Projects. [online] Business Support for Entrepreneurs. Available at: https://www.fftsbiz.com/importance-risk-managementprojects/#:~:text=%20Importance%20of%20risk%20management%20%201%20It.

K. Fageha, M. (2013). (PDF) Managing Project Scope Definition to Improve Stakeholders’ Participation and Enhance Project Outcome. [online] ResearchGate. Available at: https://www.researchgate.net/publication/257718824_Managing_Project_Scope_Definition_to_Improve_Stakeholders%27_Participation_and_Enhance_Project_Outcome.

Keenan, R. (2020). A brief intro to Quad(rant) charts» Positioning Insights. [online] Positioning Insights. Available at: https://positioninginsights.com.au/quad-charts/#:~:text=A%20quad%20chart%20is%20a%20form%20of%20technical  [Accessed 5 Aug. 2022].

Larrick, B. (n.d.). Resource Management Guide. [online] Project Manager. Available at: https://www.projectmanager.com/guides/resource-management.

Mithun Sridharan (2019). Stakeholder Analysis: Interest - Influence matrix | Think Insights. [online] Think Insights. Available at: https://thinkinsights.net/strategy/stakeholder-analysis/.

PMP, R.B.M. (2019). The Importance of A Work Breakdown Structure to Plan A Project. [online] True North PMP Consulting | Project Management Consultants. Available at: https://truenorthpmpconsulting.com/the-importance-of-a-work-breakdown-structure-to-plan-a-project/.

Product Plan (2018). What is Stakeholder Analysis? | Definition and Overview. [online] Productplan.com. Available at: https://www.productplan.com/glossary/stakeholder-analysis/.

Shethna, J. (2016). 5 Simple Steps to Manage Stakeholder Effectively (Types). [online] EDUCBA. Available at: https://www.educba.com/effective-stakeholder-management/.

Singh, P. (2021). What is Project Scheduling? | SelectHub. [online] select hub. Available at: https://www.selecthub.com/project-management/project-scheduling/  [Accessed 6 Aug. 2022].