BA(Hons) Business Management

Student Name: Cristina Borta

Student Number: 2239416

Course Name:  Project Management

Course Code:  LCBB6006

Lecturer Name: Zainab Atta

Date: 19 July 2026

Table of contents

1.	Introduction	1

2.	Aim, Objectives, and Scope	2

3.	Business Case	3

Table 1. SWOT Analysis for Bloom Coffee	4

4.	Project Charter	5

5.1 Project Deliverables	5

Table 2. Project Deliverables for Bloom Coffee	6

5.2 Work Breakdown Structure	7

Table 3. Work Breakdown Structure for Bloom Coffee	7

5.3 Resource Breakdown Structure	8

Table 4. Resource breakdown structure for Bloom Coffee	9

5.4 Cost Breakdown Structure	10

Table 5. Estimated budget for refurbishment of Bloom Coffee	10

5.5 Milestone and Gantt Chart	11

Table 6:  Milestones for Bloom Coffee	12

Figure 1. Gantt Chart for Bloom Coffee	13

6. Stakeholders	14

Table 7: Stakeholders Map	14

Table 8: Stakeholders Communication Plan	16

7. Risk Management	17

Table 9: Risk Register for Bloom Coffee Refurbishment	18

8. Recommendations	20

9. Conclusion	20

References	21

Appendix	23

Appendix A Project Charter for Bloom Coffee	23

1. Project Overview	23

2. Stakeholder Analysis	24

3.1 Scope, Boundaries and Deliverables	24

5.	Project Schedule	25

5. Risk Assessment and Management	26

6. Quality Management	26

7. Communication Plan	26

8. Budget and Resource Allocation	28

9. Approval	29

Appendix B: RACI Matrix for Bloom Coffee	30

# Introduction

Project Name: 
Project Plan for the Refurbishment and Reopening of Bloom Coffee Small Independent Coffee Shop

Location

Kent, Chatham

Launch
Four-five weeks
03/08/2026-04/09/2026

Project management is the application of knowledge, skills, tools, and techniques to project activities to meet project requirements (PMI, 2021). Bloom Coffee must coordinate refurbishment, equipment installation, supplier arrangements, staff preparation, and reopening within budget and time.

Bloom Coffee is a small independent coffee shop that requires internal refurbishment before re-opening. The project improves interior layout, customer seating, service counter, decoration, lighting, coffee equipment setup, signage, and final cleaning to prepare the premises for trading. Major structural work, long-term business operations, and marketing campaigns are excluded.

A structured approach is appropriate because the project has clear outputs, linked activities, resource needs, and time constraints. However, flexibility is required because refurbishment projects may include hidden defects, design changes, contractor delays, or supplier issues (Ali & Au-Yong, 2022). Thus, a principles-based approach allows project management tools to be tailored to the project (Shepherd et al., 2023).

# Aim, Objectives, and Scope

The goal of this project is to refurbish and prepare Bloom Coffee for reopening as a safe, functional, and customer-ready independent coffee shop within the agreed-upon budget, timeframe, and quality standards. This project must balance cost, time, quality, and operational readiness while accommodating supplier delays, layout changes, and hidden defects. Refurbishment projects are more uncertain than new-build projects (Ali and Au-Yong, 2022), so project principles should be tailored to the project.

The objectives are to:

- Confirm the refurbishment design, budget, schedule, and responsibilities before work starts.

- Clear the premises and prepare it for refurbishment.

- Complete decoration, flooring, lighting, and counter improvements.

- Install and test coffee equipment, refrigeration, till system, furniture, and signage.

- Check suppliers, stock, staff readiness and safety requirements.

- Complete final cleaning, inspection, and handover before reopening.

Interior refurbishment, customer seating, service counter setup, coffee equipment installation, furniture, signage, supplier setup, staff preparation, final cleaning, and reopening are included. Major structural changes, long-term operations, marketing campaigns, external repairs, and plumbing or electrical redesign are excluded. Good scope control is required to reduce cost growth, delay, and disagreement (PMI, 2021). However, if urgent defects or compliance issues are found during delivery, the scope should still be reviewed.

# Business Case

Business feasibility is the assessment of the practicality, cost, and legality of a proposed project before any resources are committed. The business case for Bloom Coffee is to renovate and reopen the coffee shop in a safe, attractive, and operational manner. 

From a business perspective, the initiative is viable as the reopening allows Bloom Coffee to restart trading and generate revenue. The renovation is to improve the customer experience through seating, lighting, decor, counter configuration, and ambiance. The physical ambiance, quality of products, employee performance, variety of offerings and their appropriateness influence the experiences in coffee shops as shown by Vu et al. (2025).

The project is technically feasible because it only concerns internal renovations and preparations for reopening. The work involves no major structural or external work and can be performed by a small team. However, renovation projects can also expose hidden defects, design changes, and delays from suppliers (Ali and Au-Yong, 2022). Viability therefore rests on initial assessments, supplier validation and weekly progress evaluations.

The project is financially viable provided that the budget of £15,730 is approved prior to commencement of work. Bauer (2024) states that scope and deliverables set expectations and define project boundaries. This is important because ambiguous additional work, like plumbing or electrical changes, can raise costs and delay reopening. Delivery time is expected to be four weeks plus one contingency week.

## Table 1. SWOT Analysis for Bloom Coffee

| Strengths | Weaknesses |
| --- | --- |
| The project has a clear purpose: refurbish and reopen Bloom Coffee. | The business may have limited budget as a small independent coffee shop. |
| The scope is manageable because it focuses on internal refurbishment only. | The project depends on contractors, suppliers, and equipment delivery. |
| A refreshed interior can improve customer experience and brand image. | Delays may reduce income because the shop cannot trade during refurbishment. |
| The project can be completed by a small team within a short timeframe. | Hidden defects or layout issues may appear once work begins. |
| Opportunities | Threats |
| Reopening can attract existing and new customers. | Supplier delays could affect equipment, furniture, or stock availability. |
| Improved seating, lighting and signage can increase customer satisfaction. | Cost increases could reduce the available budget. |
| Stronger customer experience can support repeat visits and positive reviews. | Competitors may continue trading while Bloom Coffee is closed. |
| Sustainable choices, such as reusing furniture or reducing waste, can improve the shop’s image. | Poor-quality refurbishment could damage reputation and reduce customer trust. |

Source: Author’s own work

The SWOT analysis identified that Bloom Coffee has a clear project objective, achievable internal scope, and opportunities to increase customer satisfaction. The main risks are supplier delays, hidden defects, cost increases and loss of revenue during the closed shop period. Therefore, the success of the project relies on Bloom Coffee’s ability to quickly validate supplier lead times, maintain a contingency budget, avoid scope creep, and assess progress on a weekly basis.

# Project Charter

The project charter confirms Bloom Coffee’s purpose, scope, stakeholders, risks, budget assumptions, milestones, and handover requirements. Kim, Kudinova and Kovalova (2025) explain that a project charter helps define key project parameters and supports stakeholder coordination. For Bloom Coffee, the charter confirms that the project is limited to refurbishment and reopening preparation, while major structural work, long-term operations and future marketing campaigns are excluded. The full Project Initiation Document / Project Charter is provided in Appendix A. A limitation of the charter is that it only supports control if changes are formally reviewed. Otherwise, scope creep may still occur.

# 5.1 Project Deliverables

The project deliverables are the direct outputs needed for Bloom Coffee to reopen successfully. According to Bauer (2024) scope and deliverables define the boundaries of the project, define what the customer expects, and help with planning and control. Deliverables for this project include an approved refurbishment plan, cleared premises, completed interior works, installed coffee equipment, furniture, and signage, confirmed suppliers, prepared staff, and final cleaning.

The success criteria agreed prior to handover must be assessed for each deliverable. This is significant because completing the physical refurbishment alone is insufficient, so the shop must also be operationally ready. However, the original plan may need to be reassessed if there are delays from suppliers, equipment breakdowns or hidden defects.

## Table 2. Project Deliverables for Bloom Coffee

| Deliverable | Project Meaning | Success Criteria |
| --- | --- | --- |
| Refurbishment plan approved | Design, layout, budget and schedule confirmed | Owner approves scope before work starts |
| Premises cleared and prepared | Old furniture, waste and unused items removed | Shop ready for refurbishment work |
| Interior works completed | Decoration, flooring, lighting, and counter area finished | Interior meets agreed design and quality standard |
| Coffee equipment installed | Coffee machine, grinder, fridge and till system fitted | Equipment tested and ready for use |
| Furniture and signage installed | Tables, chairs, menu board and external/internal signage fitted | Customer area ready for service |
| Suppliers confirmed | Coffee, milk, bakery items and packaging suppliers arranged | Opening stock and delivery dates confirmed |
| Staff prepared | Staff briefed on service process, safety, and opening duties | Staff ready for reopening |
| Final cleaning and handover | Shop cleaned, checked, and accepted before reopening | Bloom Coffee ready to reopen to customers |

Source: Author’s own work, based on Bauer (2024)

These deliverables serve as the foundation for the work breakdown structure (WBS), as each output must be divided into activities, resources, and milestones.

# 5.2 Work Breakdown Structure

A Work Breakdown Structure (WBS) has been used to break down the work packages for the Bloom Coffee refurbishment into smaller pieces. Project management tools help in planning and controlling scope, schedule, resources, cost, quality, and risk (PMI, 2021). The project includes premises clearance, decoration, equipment installation, supplier preparation, staff readiness, and handover.

The work breakdown structure is related to the project deliverables in that each work package must deliver a specific output before it can be reopened. Scope and deliverables are used to set project boundaries and control expectations (Bauer, 2024). For Bloom Coffee, the WBS emphasises a renovated interior, working service counter, tested equipment, confirmed suppliers, and final handover.

Due to the logical order of refurbishment activities, a sequential WBS occurs. However, the WBS needs to be flexible because supplier delays, equipment adjustments, or layout changes may impact the planned sequence. Shepherd et al. (2023) suggest that project management principles should be adapted to context rather than applied in a mechanical way. Therefore, the WBS should be revisited during delivery and not considered as a static document.

## Table 3. Work Breakdown Structure for Bloom Coffee

| WBS Code | Work Package | Sub-Activities / Tasks | Deliverable |
| --- | --- | --- | --- |
| 1.0 | Project planning | Confirm design, layout, budget, schedule, contractors, and responsibilities | Approved refurbishment plan |
| 2.0 | Premises preparation | Remove old furniture, clear waste, protect reusable items and prepare work area | Premises ready for refurbishment |
| 3.0 | Interior refurbishment | Complete painting, flooring, lighting checks and counter improvements | Refurbished interior space |
| 4.0 | Equipment installation | Install coffee machine, grinder, fridge, till system and small equipment | Equipment installed and tested |
| 5.0 | Customer area setup | Arrange tables, chairs, menu board, decor, and signage | Customer seating and signage ready |
| 6.0 | Supplier and stock setup | Confirm coffee, milk, bakery, packaging, and cleaning supplies | Opening stock and suppliers confirmed |
| 7.0 | Staff and service readiness | Brief staff, test service process, check cleaning and safety duties | Staff ready for reopening |
| 8.0 | Final handover | Complete final cleaning, snagging, quality check and owner approval | Bloom Coffee ready to reopen |

Source: Author’s own work

The WBS improves control by linking deliverables to activities, responsibilities, and resources. However, the WBS cannot remove external uncertainty, so progress should be reviewed weekly.

# 5.3 Resource Breakdown Structure

Resource planning identifies the people, materials, equipment, and services required to perform project activities. Bloom Coffee’s Resource Breakdown Structure (RBS) corresponds to the Work Breakdown Structure (WBS) because each work package involves the use of certain resources such as contractors, suppliers, equipment, materials, and personnel. The PMI (2021) emphasises the importance of resource planning as well as schedule, scope, cost, and quality.

The RBS reveals that the project is dependent not only on labour but also on supplier coordination and equipment availability. This is a limitation because delays to furniture, signage, equipment, opening stock may postpone the reopening.

## Table 4. Resource breakdown structure for Bloom Coffee

| Resource Category | Specific Resources Required | Linked Work Packages |
| --- | --- | --- |
| Project management | Owner/project manager, refurbishment schedule, budget tracker, supplier list | Planning, monitoring, and handover |
| Contractors | Decorator, electrician, plumber if required, flooring fitter | Interior refurbishment, lighting, counter area |
| Suppliers | Coffee equipment supplier, furniture supplier, signage supplier, food, and beverage suppliers | Equipment installation, customer area, opening stock |
| Materials | Paint, flooring materials, light fittings, counter materials, cleaning materials | Decoration, flooring, lighting, final cleaning |
| Equipment | Coffee machine, grinder, fridge, till system, small service equipment | Equipment installation and testing |
| Furniture and customer items | Tables, chairs, menu board, décor, signage | Customer seating and shop presentation |
| Operational staff | Baristas, cleaner, owner/manager | Staff preparation, service testing, final handover |

Source: Author’s own work

# 5.4 Cost Breakdown Structure

A Cost Breakdown Structure (CBS) groups estimated costs by work package. Cerezo-Narváez et al. (2020) argue that integrating work and cost breakdown structures enhances the supervision of project activities and costs. This allows to link every cost item to a refurbishment outcome and helps in budget oversight for Bloom Coffee. 

The estimated projected budget inclusive of contingency provisions is £15,730. It assumes that Bloom Coffee is mainly refurbishing the premises and putting in or reconnecting equipment, rather than buying a new commercial coffee machine. The CBS makes the budget more transparent, but it is still an approximation. Hidden defects, changes in supplier prices or additional regulatory requirements can increase the final cost, so the budget should be reviewed weekly.

## Table 5. Estimated budget for refurbishment of Bloom Coffee

| Cost Category | Main Cost Items | Estimated Cost (£) |
| --- | --- | --- |
| Project planning and coordination | Layout planning, schedule preparation, supplier coordination | 500 |
| Premises clearance | Waste removal, storage, protection of reusable items | 750 |
| Interior decoration | Painting, wall finishes, minor repairs, decoration materials | 2,200 |
| Flooring and lighting | Flooring repairs/replacement, lighting checks and minor improvements | 3,000 |
| Service counter improvements | Counter preparation, minor plumbing/electrical adjustments | 1,000 |
| Equipment installation | Coffee machine setup, grinder, fridge, till system testing | 2,500 |
| Furniture, signage and décor | Tables, chairs, menu board, internal/external signage | 2,500 |
| Opening stock and supplies | Coffee, milk, bakery items, packaging, cleaning supplies | 1,200 |
| Final cleaning and snagging | Deep clean, minor corrections, final readiness check | 650 |
| Contingency allowance | Around 10% for supplier delays, small repairs or extra materials | 1,430 |
| Total estimated budget |  | 15,730 |

Source: Author’s own work

# 5.5 Milestone and Gantt Chart

A milestone is a major point or event in a project which marks the completion of a major phase. According to Verzuh (2021), project schedules should show task sequence, key dates, and milestones to help teams understand what needs to happen. Milestones are important for Bloom Coffee, as renovation works must be executed out in a systematic order before re-opening.

## Table 6:  Milestones for Bloom Coffee

| Milestone | Key Deliverable | Target Date | Success Criteria |
| --- | --- | --- | --- |
| M1: Project approval and supplier ordering completed | Refurbishment plan, layout and supplier orders confirmed | 05/08/2026 | Owner approves layout, budget, suppliers, and schedule |
| M2: Premises cleared | Shop ready for refurbishment | 07/08/2026 | Old items removed, waste cleared, and work area prepared |
| M3: Interior works completed | Decoration, flooring, and lighting checks completed | 14/08/2026 | Interior meets agreed quality and design standard |
| M4: Counter improvements and equipment installation completed | Counter area completed and coffee equipment installed | 20/08/2026 | Equipment installed, connected and ready for testing |
| M5: Customer area completed | Furniture, signage, and seating layout completed | 24/08/2026 | Customer area is clean, functional, and attractive |
| M6: Supplier and stock readiness confirmed | Opening stock and supplier deliveries confirmed | 26/08/2026 | Coffee, milk, bakery items, packaging, and cleaning supplies ready |
| M7: Staff readiness completed | Staff briefing and service preparation completed | 26/08/2026 | Staff understand layout, equipment, cleaning duties and opening process |
| M8: Final handover completed | Bloom Coffee ready to reopen | 28/08/2026 | Final cleaning, snagging, equipment checks, and owner approval completed |
| M9: Contingency end point | Buffer period completed if required | 04/09/2026 | Used only for supplier delays, snagging, equipment issues or final checks |

Source: Author’s own work

The Gantt chart shows the proposed order, duration, and timing of the renovation. According to Larson and Gray (2021), schedules coordinate activities, identify dependencies, and track progress against dates.

## Figure 1. Gantt Chart for Bloom Coffee

Source: Author's own work

According to the Gantt chart, Bloom Coffee is expected to be reopened at the end of Week 4 with Week 5 being a contingency period. The main dependency is that interior works are to be completed before equipment and furniture installation.

A disadvantage of the Gantt chart is that it only shows planned timelines. It cannot deal with uncertainties caused by supplier delays, equipment breakdowns or unexpected problems. Hence, weekly follow-up is required to avoid any delay in the transition to handover phase.

# 6. Stakeholders

Stakeholders are individuals or entities who can affect or be affected by a project. According to Mahajan et al. (2023), stakeholder theory helps organisations understand internal and external stakeholder needs. Bloom Coffee key stakeholders are owner, project manager, contractors, suppliers, employees, customers, and local government agencies.

Effective stakeholder management is critical because the project's success depends on timely decision-making, supplier shipments, contractor cooperation, and staff readiness. Vu et al. (2025) connects the coffee shop experience with the physical ambiance, product excellence, and employee efficiency, so communication should enhance the service delivery and reopening standards. Poor communication can lead to delays, lack of clarity about roles and financial pressure.

## Table 7: Stakeholders Map

| Stakeholder | Power | Interest | Position on Map | Management Approach |
| --- | --- | --- | --- | --- |
| Bloom Coffee owner | High | High | Manage closely | Approve budget, scope, design choices and final handover |
| Project manager | High | High | Manage closely | Control schedule, resources, costs, risks, and communication |
| Decorator / refurbishment contractor | Medium | High | Manage closely | Daily updates during active works and quality checks |
| Electrician / plumber if required | Medium | Medium | Keep informed | Confirm availability, technical requirements, and completion dates |
| Coffee equipment supplier | Medium | High | Manage closely | Confirm delivery, installation, testing and training support |
| Furniture and signage suppliers | Medium | Medium | Keep informed | Confirm order dates, delivery times and installation needs |
| Coffee shop staff / baristas | Medium | High | Keep involved | Brief staff on new layout, equipment, service process and cleaning duties |
| Food and drink suppliers | Medium | Medium | Keep informed | Confirm opening stock, delivery dates and product availability |
| Local authority / compliance bodies | High | Medium | Keep satisfied | Ensure food hygiene, safety and premises readiness requirements are met |
| Customers | Low | High | Keep informed | Communicate reopening date, improved space, and service readiness |
| Neighbouring businesses / residents | Low | Low/Medium | Monitor | Manage noise, waste, access, and delivery disruption |

Source: Author’s own work

Additionally, clear responsibility allocation is needed. A RACI matrix defines who is Responsible, Accountable, Consulted and Informed for project activities (Suhanda and Pratami, 2021). This reduces the risk of duplicated or delayed tasks such as equipment installation, stock ordering and final handover for Bloom Coffee. The complete RACI matrix is contained in Appendix B and should be revisited if any changes to responsibilities occur during delivery.

## Table 8: Stakeholders Communication Plan

| Stakeholder | Information Needed | Method | Frequency | Purpose |
| --- | --- | --- | --- | --- |
| Bloom Coffee owner | Progress, costs, risks, decisions, and handover status | Meeting, phone, email | Weekly and as required | Maintain approval and control scope |
| Project manager | Full project information from all parties | Schedule, budget tracker, calls, site notes | Daily | Control time, cost, quality, and resources |
| Refurbishment contractor | Work sequence, design details, access, and quality expectations | Site briefing, phone, email | Daily during works | Coordinate refurbishment activities |
| Electrician / plumber | Technical requirements, access times and completion deadlines | Phone/email | Before and during required works | Avoid technical delays |
| Coffee equipment supplier | Delivery date, installation requirements and testing plan | Email/phone | Before delivery and installation | Ensure equipment is ready for reopening |
| Furniture and signage suppliers | Order details, delivery dates and installation requirements | Email/phone | Before delivery | Avoid late furniture or signage |
| Coffee shop staff | New layout, equipment uses, service process, cleaning, and safety duties | Staff briefing/training | Before reopening | Prepare staff for customer service |
| Food and drink suppliers | Opening stock quantities, delivery times and product availability | Email/phone | One week before reopening | Ensure stock is ready for trading |
| Local authority / compliance bodies | Food hygiene, safety, and premises readiness information | Email/online forms/site visit if required | Before reopening or as required | Support legal and safe reopening |
| Customers | Reopening date, opening times and improvements | Social media, window notice, website | Before reopening | Build awareness and customer return |
| Neighbouring businesses / residents | Delivery times, noise, or access disruption | Verbal update / notice | As required | Reduce complaints and maintain goodwill |

Source: Author’s own work

The communication plan reduces misunderstanding by defining the information needs of each stakeholder, how information will be shared and how often communication will occur. However, the limitation is that the plan depends on stakeholders responding on time. Bloom Coffee should have written confirmation of key decisions, supplier approval, delivery schedules, cost changes and hand-over checks.

# 7. Risk Management

Risk management is the process of identifying, assessing, and acting on uncertainty to protect project objectives. Bloom Coffee has a fixed reopening deadline, a limited budget, and several dependencies, including contractors, suppliers, equipment delivery and staff availability. According to Ali and Au-Yong (2022), refurbishment projects are difficult to manage because of uncertainty, design changes and coordination problems.

Risk management also safeguards business value. A delayed reopening could reduce income and customer confidence. Reopening before equipment, staff or safety checks are complete could reduce service quality. Hillson and Simon (2020) assert that risk management helps project teams understand uncertainty and choose appropriate responses. Therefore, the risk register should be reviewed on a weekly basis.

## Table 9: Risk Register for Bloom Coffee Refurbishment

| Risk | Likelihood | Impact | Risk Level | Possible Effect | Risk Owner | Response |
| --- | --- | --- | --- | --- | --- | --- |
| Supplier delay for coffee equipment | Medium | High | High | Equipment not ready for reopening | Project manager | Confirm lead time early and keep alternative supplier option |
| Hidden defects in flooring, walls, or services | Medium | High | High | Extra repair cost and schedule delay | Contractor / project manager | Complete early inspection before main works starts |
| Budget overrun | Medium | High | High | Reduced contingency and pressure on owner | Owner / project manager | Use agreed budget, approve variations in writing |
| Contractor availability issue | Medium | Medium | Medium | Refurbishment work delayed | Project manager | Confirm booking dates and backup contractor |
| Poor-quality decoration or finishes | Medium | Medium | Medium | Rework needed before reopening | Contractor | Daily checks and snagging list |
| Equipment fault during testing | Low/Medium | High | Medium/High | Service cannot operate properly | Equipment supplier | Test equipment before reopening and request technical support |
| Opening stock not delivered | Medium | Medium | Medium | Limited menu or delayed opening | Owner / supplier | Confirm stock order one week before reopening |
| Staff not prepared for new layout or equipment | Medium | Medium | Medium | Slow service and poor customer experience | Owner / manager | Staff briefing and service trial before reopening |
| Health, safety, or hygiene issue | Low/Medium | High | High | Reopening may be unsafe or delayed | Owner / project manager | Complete cleaning, safety checks and hygiene preparation |
| Customer disruption or poor reopening communication | Low | Medium | Low/Medium. | Reduced customer return after reopening | Owner | Communicate reopening date through social media and shop notice |

# 8. Recommendations

Bloom Coffee should manage the refurbishment scope and avoid making unnecessary changes once delivery begins. Supplier lead times for equipment, furniture, signage, and opening stock should be confirmed by Week 1. The project manager should review the WBS, schedule, cost tracker and risk register on a weekly basis as there may be issues with suppliers, hidden defects or quality issues that affect the handover process. A small contingency budget and one-week time buffer should be set aside for snagging, minor repairs, or late deliveries. Personnel should be briefed on the layout, equipment, cleaning responsibilities and service procedures before reopening. Finally, Bloom Coffee should conduct a final readiness check that includes cleanliness, equipment testing, signage, seating layout, and owner approvals.

# 9. Conclusion

The Bloom Coffee refurbishment project will be successful if the shop can safely reopen within the four-week delivery timeline, using the one-week contingency only if it is needed. Success depends on fulfilling the requirements, which are the renovated interior, the installed and tested equipment, the seating area, the verified suppliers, the initial inventory, the trained staff, and the final sanitation.

Furthermore, success is supported by scope definition, project charter, deliverables, WBS, milestones, resource planning, stakeholder management, and risk control. These tools help organise activities, manage costs, track progress, and reduce uncertainty. Overall, the project is feasible if scope, budget, suppliers, quality, and communication are actively managed throughout execution.

# References

Ali, A.S. and Au-Yong, C.P. (2022) ‘Risk factors in the refurbishment design process: the case of Malaysia’, International Journal of Building Pathology and Adaptation, 40(4), pp. 622-635. https://doi.org/10.1108/IJBPA-01-2021-0005.

Bauer, P. (2024) ‘Scope and Deliverables’, in A Comprehensive Project Management Guide: Quality Management, Integrated Six-Sigma and Change Management Compilation. Cham: Springer Nature Switzerland, pp. 163-170.

Cerezo-Narváez, A., Pastor-Fernández, A., Otero-Mateo, M. and Ballesteros-Pérez, P. (2020) ‘Integration of cost and work breakdown structures in the management of construction projects’, Applied Sciences, 10(4), article 1386. https://doi.org/10.3390/app10041386.

Hillson, D. and Simon, P. (2020) Practical Project Risk Management: The ATOM Methodology. 3rd edn. Oakland, CA: Berrett-Koehler Publishers.

Kim, O., Kudinova, M. and Kovalova, V. (2025) ‘The importance of a project charter in digital marketing project management’, Bulletin of VN Karazin Kharkiv National University Economic Series, (108), pp. 150-157.  https://doi.org/10.26565/2311-2379-2025-108-13.

Larson, E.W. and Gray, C.F. (2021) Project Management: The Managerial Process. 8th edn. New York: McGraw-Hill Education.

Mahajan, R., Lim, W.M., Sareen, M., Kumar, S. and Panwar, R. (2023) ‘Stakeholder theory’, Journal of Business Research, 166, article 114104. https://www.sciencedirect.com/science/article/pii/S0148296323004629?via%3Dihub

Project Management Institute (PMI) (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edn. Newtown Square, PA: Project Management Institute.

Shepherd, M., Sankaran, S., Shi, Q., Piccard, L.A. and Toma, T. (2023) ‘Principles-based project management: Where to now?’, Project Management Journal, 54(6), pp. 583-587. https://doi.org/10.1177/87569728231211281.

Suhanda, R.D.P. and Pratami, D. (2021) ‘RACI matrix design for managing stakeholders in project case study of PT. XYZ’, International Journal of Innovation in Enterprise System, 5(02), pp. 122-133.

Verzuh, E. (2021) The Fast Forward MBA in Project Management. 6th edn. Hoboken, NJ: Wiley.

- Vu, O.T.K., Alonso, A.D., Tran, T.D., Martens, W., Do, L., Nguyen, T.T., Atay, E. and Akbari, M. (2025) ‘Coffee culture unravelled: exploring the coffee shop experience model in the Vietnamese context’, Tourism Recreation Research, 50(3), pp. 459-477. https://doi.org/10.1080/02508281.2023.2295621.

# Appendix

## Appendix A Project Charter for Bloom Coffee

Project Initiation Document (PID) / Project Charter

Refurbishment and Reopening of Bloom Coffee

Project scope note: Bloom Coffee is responsible for refurbishing and preparing the coffee shop for reopening. Major structural alterations, external building repairs, long-term business operations, payroll and future marketing campaigns are excluded.

# 1. Project Overview

| Project Name | Project Plan for the Refurbishment and Reopening of Bloom Coffee |
| --- | --- |
| Project ID | BC-PID-001 |
| Project Manager | Cristina Borta |
| Organisation | Bloom Coffee |
| Location | Chatham, Kent |
| Team Members | Owner/project manager, decorator, electrician, plumber if required, coffee equipment supplier, furniture/signage supplier, cleaner and coffee shop staff |
| Project Objectives | Refurbish the interior, install, and test equipment, prepare suppliers, and staff, and reopen Bloom Coffee within a four-week delivery period, with one additional contingency week. |
| Project Goals | Deliver a safe, attractive, and customer-ready coffee shop that is prepared for daily trading and customer service. |

# 2. Stakeholder Analysis

| Key Stakeholders | Bloom Coffee owner, project manager, decorator, electrician, plumber if required, coffee equipment supplier, furniture/signage supplier, cleaning team, coffee shop staff, customers and local authority/compliance bodies. |
| --- | --- |
| Roles and Responsibilities | Owner approves scope, budget and final handover; project manager controls time, cost, quality, risks and communication; contractors complete refurbishment works; suppliers provide equipment, furniture and opening stock; staff prepare for service readiness. |
| Communication Strategy | Weekly owner/project update, daily contractor coordination during active works, supplier confirmation before delivery dates, and immediate reporting of risks, delays or scope changes. |

# 3.1 Scope, Boundaries and Deliverables

| Within Scope | Outside Scope |
| --- | --- |
| Internal decoration, painting, and shop appearance improvements | Major structural alterations and building extensions |
| Flooring, lighting checks and minor counter improvements | External repairs, lease/legal negotiations and landlord works |
| Coffee equipment setup, furniture, menu board and signage | Payroll, long-term operations, and full business strategy |
| Supplier setup, opening stock, staff preparation, final cleaning, and handover | Future marketing campaigns, website redesign and ongoing accounting |

3.2Deliverables

Approved refurbishment plan, budget, layout, and schedule confirmed

Premises cleared, waste removed, and work area prepared

Interior decoration, flooring, lighting checks and counter area completed

Coffee machine, grinder, refrigeration, till system and small equipment installed and tested

Customer seating, menu board, décor and signage installed

Coffee, milk, bakery, packaging, and cleaning suppliers confirmed with opening stock available

Staff briefed, final cleaning completed, and Bloom Coffee handed over ready for reopening

# Project Schedule

| Key Milestone | Start | Finish |
| --- | --- | --- |
| Project approval, layout confirmation and supplier ordering | 03/08/2026 | 05/08/2026 |
| Premises clearance and preparation | 06/08/2026 | 07/08/2026 |
| Interior decoration, flooring, and lighting checks | 10/08/2026 | 14/08/2026 |
| Counter improvements and equipment installation | 17/08/2026 | 20/08/2026 |
| Furniture, signage, and customer area setup | 21/08/2026 | 24/08/2026 |
| Supplier setup, staff preparation and opening stock | 25/08/2026 | 26/08/2026 |
| Final cleaning, snagging and handover | 27/08/2026 | 28/08/2026 |
| Contingency period if required | 31/08/2026 | 04/09/2026 |
| Programme assumption: the four-week delivery period is realistic only if contractors are available, supplier lead times are confirmed, key equipment is delivered on time and no major hidden defects or compliance issues are discovered. One additional week is included as contingency. |  |  |

# 5. Risk Assessment and Management

| Identified Risks | Supplier delays, hidden defects, contractor availability, equipment faults, cost increases, poor-quality finishes, health and safety issues, and delayed reopening. |
| --- | --- |
| Risk Impact and Probability | Medium overall. Supplier and equipment delays have medium probability and can affect the reopening date. Health and safety issues or equipment faults may have lower probability but high operational impact. |
| Risk Mitigation Strategy | Confirm suppliers early, check equipment lead times, keep a small contingency budget, inspect the premises before works begin, complete weekly progress checks, record scope changes in writing and complete final snagging before reopening. |

# 6. Quality Management

| Quality Standards | Works should meet the agreed refurbishment design, safe working expectations, equipment manufacturer guidance, food hygiene readiness, cleanliness requirements and customer-ready presentation standard. |
| --- | --- |
| Quality Assurance Plan | The project manager checks design alignment, contractor progress, supplier delivery dates, equipment readiness, staff preparation and final customer-facing presentation before handover. |
| Quality Control Measures | Daily visual checks during active works, equipment testing, snagging list, cleaning checklist, staff readiness check and final owner approval before reopening. |

# 7. Communication Plan

| Channel | Deliverable | Frequency | Notes/Comments |
| --- | --- | --- | --- |
| Owner update | Progress, budget, and issue log | Weekly | Project manager and Bloom Coffee owner |
| Phone/email | Supplier confirmations, urgent decisions, and scope changes | As required | Used when delays could affect reopening |
| Daily briefing | Daily tasks, access needs and safety issues | Daily during active works | Project manager, contractors, and staff where relevant |
| Final handover meeting | Snagging, cleaning, equipment, and readiness sign-off | At project close | Owner approval required before reopening |

# 8. Budget and Resource Allocation

| ID | Task | Duration | Start | End | Resources | Dependency | Est. Budget (£) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Project approval, layout, and ordering | 3 days | 03/08/26 | 05/08/26 | Owner / PM | - | 600 |
| 2 | Premises clearance and preparation | 2 days | 06/08/26 | 07/08/26 | Cleaner / labour support | 1 | 750 |
| 3 | Decoration, flooring, and lighting checks | 5 days | 10/08/26 | 14/08/26 | Decorator / electrician | 2 | 3,200 |
| 4 | Counter improvements and equipment setup | 4 days | 17/08/26 | 20/08/26 | Equipment supplier / plumber if required | 3 | 4,500 |
| 5 | Furniture, signage, and customer area setup | 2 days | 21/08/26 | 24/08/26 | Furniture/signage supplier / PM | 4 | 2,400 |
| 6 | Supplier setup, stock, and staff preparation | 2 days | 25/08/26 | 26/08/26 | Owner / staff / suppliers | 5 | 1,600 |
| 7 | Final cleaning, snagging and handover | 2 days | 27/08/26 | 28/08/26 | Cleaner / PM / owner | 6 | 950 |
| 8 | Contingency allowance | 1 week | 31/08/26 | 04/09/26 | Project team and suppliers | All tasks | 2,000 |
|  | Overall estimated project budget | 4 weeks + 1 contingency weeks | 03/08/26 | 04/09/26 | Project team and suppliers | All tasks | 15,730 |

# 9. Approval

| Prepared by | Cristina Borta |
| --- | --- |
| Approval required from | Bloom Coffee owner |
| Approval statement | This PID authorises the planning and delivery of the Bloom Coffee refurbishment and reopening project within the agreed scope, programme, quality requirements and budget assumptions. |
| Date | 03/08/2026 |

Academic note: this charter supports the assessment by defining project objectives, scope, deliverables, stakeholders, risks, quality controls, communication, and resource assumptions before detailed WBS and schedule planning. It is informed by project charter principles discussed by Kim, Kudinova and Kovalova (2025).

## Appendix B: RACI Matrix for Bloom Coffee

The RACI matrix outlines accountability for the major Bloom Coffee renovation activities. R stands for Responsible; A stands for Accountable; C stands for Consulted; I stand for Informed. This helps to better manage stakeholders in a more transparent way by making clear who owns each activity and who are the required decision makers.

| Project Activity | Owner | Project Manager | Contractor | Equipment Supplier | Staff | Suppliers |
| --- | --- | --- | --- | --- | --- | --- |
| Approve budget and scope | A | R | C | I | I | I |
| Confirm layout and refurbishment design | A | R | C | C | C | I |
| Clear premises and prepare work area | I | A | R | I | C | I |
| Complete decoration and flooring | I | A | R | I | I | I |
| Complete lighting and counter checks | I | A | R | C | I | I |
| Install and test coffee equipment | I | A | C | R | C | I |
| Arrange furniture, signage, and customer area | A | R | C | I | C | C |
| Confirm opening stock and suppliers | A | R | I | I | C | R |
| Prepare staff for reopening | A | R | I | C | R | I |
| Complete final cleaning and handover | A | R | C | I | C | I |

The RACI matrix should be reviewed during the delivery phase, as responsibilities may change based on supplier delays, contractor unavailability or equipment complications that impact the reopening strategy.