## Sheet1
Responsbilities | Appointing Party Information Manager | Project Manager | Project Delivery Manager | Information Manager | Lead Designer | Task Team Manager | Task Team Informatiom Author | Edocuments
Reources
Report any skills gaps within team | I |  | A | R | I | I | I | I
Coordinate specific training |  |  | A | R
Project Stratergy
Establish and maintain Exchange Information Requirements | R |  | I | I | I | I | I | I
Assess project BIM Requirements |  |  | A | R | I | I | I | I
Develop, impliment and update the project BEP |  |  | R | I | I | I | I | I
Establish the CDE and issue appointment documents |  | I | R | I
Monitor the progress against MIDP |  |  | A | R | R | R | R | R
Provide any existing information including historical data | R
Geometry & Modelling
Issue project coordinates | A |  |  | I | R
Assurance of spatial coordination and design model |  |  | A | I | R | I | I
Design coordination with sub-contract models |  |  | A | I | R | R | I
Review models from design team |  |  | I | I | I | A | R
Construction record models |  | C | I | I | R | R | I
Data
Export and publish files in accordance with data exchange protocol |  |  | A | I | R | R | I | R
Populate COBie data into the models |  |  | A | I | R | R | I | R
Ensure assets are modelled in accordance with Asset Information Delivery Plan |  |  | A | I | R | R | I | R
Delivery of data in accordance with the Asset Information Delivery Plan |  |  | A | I | R | R | I | R
Quality Assurance and Control
Ensure that the model issue checklist has been adhered to prior to issue |  |  | A | I | R | R | I
Resolve Clashes |  |  | A | I | R | R | R
Provide BIM progress summary reports |  |  | A | I | R | R | I | R
Check and validate data and models in CDE |  |  | A | R | I | I | I | R
Meetings
Arrange BIM Meetings |  |  | R | I | I | I | I
Attend BIM Coordination meetings / Design Team Meetings |  |  | A | R | R | R | R | R
Attend BIM 'Lessons Learnt' meetings
| R |  | A | R | R | R | R | R