The wedding project report of Happi Goga and Kamsi Richard

Project management

Project report

Assignment two

Claire la joie pechangou kounga

ID: 1601353

Lecturer: Molly Jack

Project closure report

Project name: wedding planning

Data: 01/05/2018

Owner: Claire la joie

Client: Happi Goga and Richard Kamsi

Document Number

prepared by

| Document Owner | Project/Organisation Role |
| --- | --- |
| Claire La Joie | Wedding Planning |

Project Closure Report Version Control

| Version | date | author | Change description |
| --- | --- | --- | --- |
| 1.1 | June 1, 2017 | Claire La joie | 1st draft |
| 1.2 | June 5, 2017 | Claire la joie | Revisions done |
| 1.3 | June 9, 2017 | Claire la joie | Revisions done |
| 1.4 | June 14, 2017 | Claire la joie | Revisions done |

Table of content

Project closure purpose…………………………3

Project closure report goals……………………3

Project closure report summary……………….3

Project metrics performance…………………….4

Project closure tasks………………………………….7

Project closure report approval…………………11

- Project closure report purpose

Project closure report purpose

This project closure report is the final document which produce for the project and is used by management to evaluate the success of the project, come up with the best practices for the future projects, solve all open matters, and officially close the project. (prince2.com, 2018)

- Project closure report goals

Project closure report goals

This project closure report is created to achieve the following goals

- To review and authorise the success and milestones of the project. - To identify project highlights and the most important practices for the future. - To approve the outstanding risk, matters and recommendations. - To outline activities and tasks needed to close the project.

- Project closure report summary

3.1 Project background overview

Project background overview

- The main objective of this project was to plan a memorable wedding, - In six months with a budget of £10000 - Meeting all the requirement and constraints.

  - project highlights and best practices

Project highlights and Best practices

- The project manager together with sponsors and the client plan the budget which is important at the beginning of the project to know where and how much was to be spent in each stage. - The project could enter and exist the initiating phase under one month and a half due to the support of the project team. - Finding the perfect venue for the wedding took us more time because we needed to take into consideration so many things like the number of guests, our budget etc. also the disagreement of the groom and the bride on their different vision of their wedding. - Buying a wedding insurance. thought it was very quick and fast, the client came up with the idea at the middle of the project. - Planning the guests list for the wedding took a little bit of time because trying to figure out people to invite during the day versus the evening and how to handle plus one guest or friends. - Choosing the wedding suppliers was one of the tricking task. The wedding venue recommended some suppliers, the sponsors had their own suppliers and the clients had their own suppliers. Making it very difficult to come to a compromise. - Choosing and Ordering the wedding attire was an exciting and emotional moment but due to time constraint it was difficult to fine the ideal dress for the bride. - Sending out the wedding stationary. Choosing the style and design did not take so much time, since the bride had some ideas of what she wanted hence, the invitations were sent out on time. - Because of the effective communication plan put in place, they were an effective communication among the project team. - The change control process was well identified, prioritize, coordinate and executed as changes arises during this project - All the various affected support groups and stakeholders’ communication could have been implemented better. - The project was achieved within the timeline

3.3

Project closure synopsis

Because the project objectives and deliverables are being met, the project is closing

“A PRINCE2 End Project Report Template is used during project closure to review how the project performed against the version of the Project Initiation Documentation used to authorize it.

The PRINCE2 End Project Report Template is derived from the: Project Initiation Documentation; Business Case; Project Plan; Benefits Review Plan; Issue Register, Quality Register and Risk Register; Lessons Report and End Stage Reports (and Exceptions Reports, if applicable)”. (plaza, 2017)

So this prince2 methodology will be use for the closure of this project.

- project metrices performance

4.1

goals and objectives performance

Project name; section; recommendation; Description. Wedding planning; Goals and objectives performance; Visited different location for the wedding venue and choose one according to the couple demand. Wedding planning; Goals and objectives performance; A guests list was drowned, invitation design selected, printed them and send them out. Also track RSVPS and finalise guests content was done. Wedding planning; Goals and objectives performance; A photographer was chosen, photo rehearsal, photo selection and payment plan were done. Wedding planning; Goals and objectives performance; A caterer was selected and reserved, menu selected and tested. Also, the cake was selected. Payment confirmed. Wedding planning; Goals and objectives performance; Florist selection arrangement was done, bridal bouquet chosen. Delivery coordinated and the venue setup.. Wedding planning; Goals and objectives performance; A DJ was chosen, music selected, and setup done..

4.2

Success criteria performance

- Everybody being where he or she suppose to be at the right time. - No fighting and conflict among family or friends. - Satisfy and happy guests. - Pride feeling beautiful and please. - Being able to choose a wedding supplier who you trust and will deliver it on time. - As a project manager, have a less- stressful wedding planning experience.

4.3

Milestone and deliverables performance

Deliverables/milestone; Persons involved; Time review; List to do. Calendar of commitment; project manager, project sponsor, project team, groom and pride; One day; For all the project members to confirm that the feedback dates are variable for them. The definition of the project document; Project manager, Project sponsor Groom and pride; One day; To make sure that all the requirements are included. The project content and scope are precise. A study and a look into the proposal in depth; Project manager, project team; Three days; Go through the proposal to ensure you well informed of what you are demanded. Draft the storyboard; Project manager, Groom and pride; Two and a half months; Feedback on the Ceremony and reception reservation, guests list for ceremony and reception, deciding on the wedding theme and décor, on the invitation designed, choosing and reserving a florist, music, photographer, caterer. Wedding dresses review. Revised the calendar commitment; Project manager; Four days; To check and confirm the feedback back are viable for all the project members in the future.. Draft storyboard (second); Project manager, pride and groom; Two months; Feedback on the invitation sent out, cake ordered, on the wedding dresses, decors, transportation for the wedding day and the hotel for the wedding night.. Provisional release; Project manager, project sponsor Project team, bride and groom; One week; To confirm that they all satisfy and please with what has been done so far and if there is anything the will like to add or remove.. Finalise adjustment; Project team, project manager; Two weeks; Feedback on makeup and hair dresser, décor, guests list. Dress fitting. Final checks; Project team, project manager, bride and groom; Five days; All reservation confirmed. No more changes will be done and if that happen, then we will need more money and time.. Wedding day; Stakeholders; One day; Wedding ceremony.

4.4

Schedule performance

Project control process

- Put in place the baseline plan and start ordering the materials - Calculate the updates project schedule, scope, budget. - Review every four days for some tasks - Review every three hours on the wedding day

Performance evaluation

- Make sure the electricity is backup like the generator, ensuring that the lighting and sound system are working well or not - Checking if the materials ordered are used within the budget scope or not - Checking whether all the tasks/event are within the schedule time

4.5

Budget performance

Project name; section; recommendation; Description. Wedding project; Budget performance; The project budget was well managed and monitored often. The project end cost is £9050 with a surplus left of 950. The figure above includes the adjustment made during the project initiation, planning and execution stage.

4.6

Metrics performance summary

Project name; section; recommendations; Description. Wedding project; Metrics performance summary; Cost variances; the project was achieved within the budget. Notwithstanding the project was not in charge of the bridal dresses, wedding ring, honeymoon, bachelor party, which if it was included would have cause an over budget.. Wedding project; Metrics performance summary; Scope variance; during the change process management the project team had to change the project scope by going for a modest invitation card. The project was achieved within the scope baseline.. Wedding project; Metrices performance summary; Schedule variance; the schedule was not adjusted but was maintain till the wedding day. Hence the project was achieved within the schedule baseline..

- project closure tasks

5.1

resources management

Project name; section; Recommendation; description. Wedding project; Resources management; All the project stakeholders (wedding guests), were listed, their details and the track of their statue. All stage decoration, catering, electricians.

5.3

Risk and Issue management

Project name; section; recommendation; Description. Wedding project; Risk and issue management; The project manager need to make sure there is air conditioning; The weather condition; it was very hot which led to some unhappy guests. Wedding project; Project team responsible for the stationary need read through the sample before printing the rest and will have to report it to the project manager; Inaccurate information on the invitation which led to guests’ confusion. Wedding project; Risk and issue management; It is not usually documented, and the project manager can be responsible for that; Groom and pride nowhere to be found on the wedding. Mitigation; sent out people to look for them and have suitable people who can replace the bride and the groom standing by,.

5.4

Quality management

Project name; section; recommendation; Description. Wedding planning; Quality management; Mostly done by the bride, in terms of cost, the baseline was made, regarding the time, the wedding took place at the said day and time..

5.5

Communication management

Project name; section; recommendation; Description. Wedding planning; Communication management; Project team have a weekly meeting all through the planning stage and later to bi-weekly when the project reached the execution phase. The communication was done via email, meeting, memo, hard copy and phone.. Wedding project; Communication management; Bride and groom meeting with the core project team (bridesmaids and bachelors) to walk through the plan and agree on each other role and responsibility.

5.6

Customer expectation management

Project name; section; category; recommendation; Description. Wedding project; Customer expectation; Regular email was sent to the clients to update them and go via the project to check if there are on schedule and discuss the next plan of action. Meeting was also held with the sponsor to review the budget.

5.7

Asset management

Project name; section; category; recommendation; Description. Wedding project; Asset management.

5.8

Lessons learned

Project name; section; category; recommendation; Description. Wedding project; Lessons learned; Project management administration; Focus and try to delegate as you can. choose what is most important and make compromise where necessary. Make things easy where possible. The bride should avoid being the wedding planner on the wedding day.; Learned how to deal with an unforeseen Tasks, how to take care of such events so it should not repeat itself in the future..

5.9

Post project tasks

Project name; Section; category; recommendation; Description. Wedding project; Post project task; Breakdown allocation of the budget, carry out some research on the cost of different reservations, services and other things concerning the wedding. Wedding project; Post project task; Identifying the best people to form your team.

5.10

Project closure recommendations

Making sure that the project closure is approve by the project sponsor, the bride and the groom and include an agreement that all the requirement of the project charter has being met by the project.

- project closure report approvals

the people below have agreed that they have gone through this document and approved the plan outlined

Approved by

Role; Name; Signature; Date. Project manager; Kounga Claire. Project sponsor; Mr and Mrs Kamsi. Bride; Happi Goga. Groom; Kamsi Richard.

# References

plaza, m., 2017. PRINCE2 End Project Report Template. [Online] 
Available at: https://mplaza.pm/prince2
[Accessed 3 may 2018].

prince2.com, 2018. PRINCE2 Methodology. [Online] 
Available at: https://www.prince2.com
[Accessed 5 May 2018].

Callaway, N. (2007). Easy wedding budget worksheet. About, Inc. [Online] Available at: http://weddings.about.com/library/blbudgetworksheet.htm. [Accessed 4 May 2018]

Erickson, T. (2007, Feb 22). And the date is? Cape Brenton Post. Cape Brenton, N.S. p. 11. Retrieved May 4, 2018, from ProQuest database.