BMIH6007

International Meetings Management for the Hotel Industry

Traian Roibulescu

2215953

Table of Contents

Introduction	2

Event cycle	2

Aim and SMART Objectives	3

Event Concept	3

Event Management	4

Event Budget	5

Industry Trends / Issues / Impacts	6

Situational and Cultural Considerations	7

Introduction

The Croeso Incentive Sampler Weekend is a 48-hour excursion to Cardiff Bay to get to know the area. It is for forty international incentive travel planners from important outbound markets including Germany, France, the US, and the Netherlands. The event is a carefully planned series of brief, immersive experiences that show what it means to be Welsh, such as seaside expeditions, cultural performances, and workshops conducted by artisans. The approach fits with Visit Wales' Year of Croeso 2025 campaign, which wants to strengthen the idea of croeso, which is a friendly, multilingual welcome based on community values (Visit Wales, 2024). In the MICE (Meetings, Incentives, Conferences, and Exhibitions) industry, incentive travel is a high-value niche. The quality of the experience and the emotional connection may frequently affect future business choices (Fenich, 2015). Recent study in the sector shows that people who purchase incentives after Covid want short, meaningful vacations that exhibit authenticity and sustainability (SITE, 2023). Cardiff Bay is the perfect place to stay since it has a lot of places to eat, sleep, and see cultural sites all within walking distance. It is a good example of waterfront redevelopment that helps cultural tourism and event infrastructure (Gonçalves and Thomas, 2012). The goal of the event is to make people more aware of Wales as a great location to visit, get quality leads for local suppliers, and build a strong, place-based brand around croeso.

Event cycle

The Croeso Incentive Sampler Weekend is a short-format, immersive event designed to introduce forty international incentive-travel planners to the cultural, geographic and experiential strengths of Wales through a two-day curated itinerary based entirely in Cardiff Bay (Berridge, 2014). The design reflects the increasing value placed on emotional engagement and locality in business events, especially in incentive travel, where authenticity now outranks luxury as a primary motivator (Getz and Page, 2016). Cardiff Bay, as a site of sustained cultural-led urban regeneration, provides a compact environment rich in hospitality infrastructure, creative industries and waterfront public space, making it highly suitable for hosting low-carbon, high-impact familiarisation events (Smith, 2016). Delegates will take part in activities that emphasise cultural participation—such as bilingual storytelling, artisan pottery, and choral performances—all of which respond to the growing demand for meaningful, place-based incentive design (Arcodia and Whitford, 2017). The event uses a blended delivery model, balancing formal supplier meetings with informal shared experiences, which supports social capital-building among planners and increases post-event booking potential (Crowther, 2014). A speed-networking session with vetted Welsh suppliers will anchor commercial outcomes while reinforcing the destination’s readiness for incentive business (Mair and Weber, 2019). Each touchpoint is selected to highlight croeso—the Welsh concept of a warm, inclusive welcome—as a brand asset that differentiates Wales in the MICE landscape and aligns with current destination branding strategies (Richards, 2018). The programme avoids multi-site travel and instead leverages Cardiff Bay’s walkability, a strategy aligned with current event sustainability practices that minimise emissions without compromising experience quality (Laing and Frost, 2017). Activities conclude with a collaborative feedback session and digital contact exchange, building forward-looking relationships between planners and local suppliers in line with best practice in B2B event design (Ferdinand and Kitchin, 2017). Through this format, the event balances cultural narrative, market logic, and logistical simplicity, creating a feasible prototype for wider incentive campaigns under Visit Wales’s Year of Croeso 2025 initiative (Visit Wales, 2024).

Aim and SMART Objectives

The primary aim of the Croeso Incentive Sampler Weekend is to position Wales as a viable, memorable, and culturally distinctive destination for high-value incentive travel by offering international planners a short-format, experience-rich site visit (Getz and Page, 2016). Events with well-defined aims are more likely to meet stakeholder expectations and support long-term destination marketing strategies (Ferdinand and Kitchin, 2017). To operationalise this aim, three SMART objectives are proposed, each designed to be specific, measurable, achievable, relevant, and time-bound (Allen et al., 2011). The first objective is to attract forty qualified incentive planners from Europe and North America by March 2025 through targeted B2B outreach campaigns and association partnerships (Mair, 2013). The second objective is to achieve at least a 90% satisfaction rate from delegates in post-event evaluations using Likert-scale and open-ended feedback tools (Laing and Frost, 2017). The third objective is to generate ten or more confirmed business leads for Welsh suppliers within six months of event delivery (Crowther, 2014).

Event Concept

The Croeso Incentive Sampler Weekend is a short-format event for forty international incentive travel planners. It will take place in Cardiff Bay and will be focused on high-impact, low-carbon travel, which is in line with the growing demand for experiential and sustainable incentive travel (Laing and Frost, 2017). The event concept is based on research that shows a change from conventional luxury-focused incentives to more real, place-based experiences that show the values and culture of the location (Getz and Page, 2016). Delegates will participate in a two-day program that includes seaside excursions, cultural performances, and craft-led workshops. These activities will help them feel more connected to the location and make it stand out, which are important elements in deciding where to go on an incentive trip (Richards, 2018). Cardiff Bay is chosen because it has a small infrastructure, is easy to walk about, and has a lot of cultural and entertainment options, which meets the requirements for good logistics and a low environmental effect (Smith, 2016). The event starts with a multilingual welcome and a networking session with a local theme at the Senedd. This helps people get to know one other and strengthens Wales's cultural identity (Arcodia and Whitford, 2017). Activities include a high-speed RIB ride, a pottery workshop conducted by local craftsmen, and an evening reception with Welsh music and regional food, which is in line with the best practices for multimodal destination marketing (Berridge, 2014). Day two includes meetings with suppliers in an organised speed-networking approach, which is a well-known way to boost B2B connections and bookings after the event (Mair and Weber, 2019). Delegates also take part in a Welsh storytelling session and a sustainable gin-blending experience, which are both examples of requests for immersive, ethically sound incentive packages (Ferdinand and Kitchin, 2017). The last part of the schedule is a group feedback session, which lets people evaluate the event in real time and keep track of future involvement, in line with event legacy planning frameworks (Crowther, 2014). Visit Wales's 2025 plan (Visit Wales, 2024) uses the Welsh word croeso (welcome) as a thematic anchor and a way to market the country as a destination. Each touchpoint—accommodation, cuisine, language, and entertainment—has been carefully chosen to show this word. The event's goal is to turn awareness into reservations by combining cultural authenticity, business usefulness, and operational efficiency. It also wants to boost Wales's position in the European and North American incentive travel markets (SITE, 2023).

Event Management

For the Croeso Incentive Sampler Weekend to go well, there needs to be good management in four key areas: operations, human resources, risk management, and marketing. Each area should be planned to meet professional standards for event delivery and destination promotion (Tum, Norton, and Nevan Wright, 2013). Cardiff Bay's concentrated infrastructure makes logistics easier, keeping all events, venues and accommodations within walking distance. This is seen as a key way to cut down on transportation emissions and make event tourism more enjoyable for participants (Jones, 2014). The event will use two contracted four-star hotels for lodging and meals. It will also use existing local venues like the Senedd, the Norwegian Church, and the Wales Millennium Centre. This will cut down on the need for extensive staging or temporary builds, which helps with lean budgeting and efficient resource allocation (Raj, Walters, and Rashid, 2013). Human resource planning involves a core event management team of six professionals and ten trained student volunteers from local colleges. This staffing method has worked well for medium-sized commercial events because it strikes a good balance between competence and cost control (Silvers, 2014). Key duties will include coordinating delegates, working with suppliers, running the hospitality desk, and managing risks on-site. These are all positions that are common in modern event planning (Bladen et al., 2018). Risk management will use a tiered strategy that includes a pre-event risk register, real-time on-site monitoring, and a communication plan to deal with problems. This will be backed by Cardiff's easy-to-reach emergency infrastructure and current venue compliance requirements (Lashley and Best, 2015). A 10% budget reserve will be set up for things like bad weather, sickness, or a supplier going out of business. This is in line with best practices for financial planning for incentive and hosted buyer events (Bowdin et al., 2014). Six months before the event, marketing will start. It will use digital platforms, association mailing lists, and Visit Wales's contacts for international business events to get the right people to come. This is based on the idea that early targeted engagement increases B2B event attendance (Lee and Back, 2013). A branded campaign with the theme "Croeso in Action" will be adapted for email, LinkedIn, and industry media. It will also include teaser videos and destination assets to make it more relevant and reach more people, in line with current strategies for incentive market positioning (Hernandez-Maskivker, Lapointe, and Aquino, 2020). All management decisions, including staff planning and communication strategies, are based on the larger strategic goal of showing that Wales can host high-quality, long-lasting, and culturally relevant incentive programs that meet the needs of today's business event buyers (Pereira, Correia, and Schutz, 2015).

Event Budget

| Income | Amount (£) |
| --- | --- |
| Visit Wales strategic grant | 12,000 |
| Supplier showcase fees (10 × £500) | 5,000 |
| Delegate contribution (40 × £100) | 4,000 |
| Sponsorship (branding & in-kind) | 6,000 |
| Total Income | £27,000 |
| Expenditure | Amount (£) |
| Venue hire & AV (3 locations) | 5,500 |
| Accommodation (2 nights × 40) | 8,000 |
| Catering (6 services) | 4,000 |
| Activities & workshop fees | 3,000 |
| Marketing & comms | 1,500 |
| Staff fees (3 staff × 2.5 days) | 2,000 |
| Contingency (10%) | 2,000 |
| Total Expenditure | £26,000 |

The planned budget for the Croeso Incentive Sampler Weekend shows that the financial plan is tight and well-balanced, which will help both strategic goals and operational practicality. The main sources of money are a £12,000 grant from Visit Wales, which shows how the event fits with the Year of Croeso 2025 campaign, and £5,000 from fees for suppliers to take part. Extra money from delegate fees and local sponsorship helps cover delivery expenses even further. The spending plan shows a reasonable price structure that was worked out with local venues and, where available, in-kind donations, especially for marketing and supplies. The two biggest expenditures are still housing and food, which is a sign of the event's high quality. Activities are chosen to provide cultural value without needing a lot of infrastructure. There is a 10% contingency built in to cover any possible risk occurrences, such cancellations or shortages of supplies. The event is expected to make a tiny profit of £1,000, which shows that costs are being kept under control and that the event may be financially feasible as part of a destination-led incentive display.

Industry Trends / Issues / Impacts

The incentive travel sector has changed a lot since 2020. Now, buyers seek more authenticity, wellness, and sustainability, which has changed how suppliers do business (Mair and Weber, 2019). Academic study indicates that planners are progressively inclined towards places that provide emotional and cultural depth, together with significant group experiences, rather as conventional high-end incentives predicated purely on luxury (Getz and Page, 2016). This change is part of a bigger trend in tourism and events towards more active participation and identity-based experiences, rather than just passively consuming (Richards, 2018). The COVID-19 pandemic also sped up the need for shorter, more compact events that cut down on travel time and danger, notably in European and transatlantic markets (Liu and Lee, 2021). In this situation, hosted buyer programs and familiarisation events have become more strategically important since they help planners make sure that a destination is ready and that a provider is a good match before signing a contract (Lee and Back, 2013). Also, studies from the industry show that sustainability is no longer a "value-add" but a basic necessity. This is especially true for European customers, who increasingly anticipate emissions reduction, waste minimisation, and socially responsible procurement as standard characteristics of events (Pereira et al., 2015). The walkability and compact infrastructure of Cardiff Bay immediately assist these goals. This lets incentive planners do several activities without having to switch coaches, which is in line with the principles of sustainable event design (Jones, 2014). In addition, incentive customers are more and more looking for experiences that match with their brand and show their personal and organisational values. This means that cultural relevance and emotive storytelling are at the heart of program design (Berridge, 2014). This fits well with the Welsh tourism strategy, which sees croeso, or "warm welcome," as a unique national story and a way to use soft power in a competitive European incentive market (Smith, 2016). The growth of digital communications has not diminished the necessity for in-person site experiences; instead, hybrid marketing strategies now employ pre-event digital touchpoints to facilitate conversion into live attendance, thereby enhancing the feasibility of small, targeted events such as this weekend (Hernandez-Maskivker et al., 2020). The Croeso Incentive Sampler Weekend is a direct response to these changes since it offers international planners a values-driven, efficient, and culturally relevant experience. It also shows how the MICE industry as a whole is affected, such as by more focus on delegate wellness, a variety of experiences, and post-event reporting as important measures of success (Arcodia and Whitford, 2017). All of these things together make the event more likely to help with strategic destination branding objectives while also meeting the changing needs of buyers.

Situational and Cultural Considerations

A PESTEL study of the Croeso Incentive Sampler Weekend shows how the macro-environment and culture affect its viability and fit with Wales's business events strategy. The Welsh Government has put money into business tourism as a way to strengthen the economy. They have done this by include events in plans for regional economic development and giving direct assistance via Visit Wales and the Event Wales program (Thomas and Tallontire, 2015). The UK's tourist economy has been unstable since Brexit, but Wales's lower operational costs and easier-to-reach infrastructure make it a better place to develop incentives than London or Dublin (Jones and Munday, 2016). There is an increasing demand among consumers in travel experiences that are culturally unique and significant, which fits with the event's emphasis on croeso and Welsh identity (Richards, 2018). Destination marketing is becoming more dependent on mixed delivery formats, such as digital pre-engagement and post-event material. This makes it easier for small events to reach people all over the world while yet allowing for human connection during delivery (Hernandez-Maskivker et al., 2020). The event takes use of Cardiff Bay's small size and walkability to promote low-carbon mobility between venues. This is becoming more and more important as the world pushes for tourism and MICE operations to become less carbon-intensive (Laing and Frost, 2017). Wales follows the UK’s rules for licensing events and keeping people safe, which are well-known and consistent throughout public spaces. This makes it easier for event planners to know what to expect from the law (Raj et al., 2013). From a cultural point of view, the Welsh word "croeso" means more than just hospitality. It is a kind of soft power that is based on community, bilingualism, and national identity, which makes tourists feel more connected to the region and more devoted to it (Griffiths, 2011). The program stands out in a crowded incentive travel market by incorporating this cultural story into every event touchpoint. This also fits with the ideals of the national brand. The PESTEL and cultural factors together show that the event is possible and fits strategically with both local government systems and worldwide incentive travel trends.

References

Allen, J., O’Toole, W., Harris, R. and McDonnell, I. (2011) Festival and Special Event Management. 5th ed. Milton: Wiley.

Arcodia, C. and Whitford, M. (2017) ‘Festival attendance and the development of social capital’, Event Management, 21(1), pp. 21–32.

Berridge, G. (2014) Events Design and Experience. 2nd ed. London: Routledge.

Bladen, C., Kennell, J., Abson, E. and Wilde, N. (2018) Events Management: An Introduction. 2nd ed. London: Routledge.

Bowdin, G., Allen, J., O’Toole, W., Harris, R. and McDonnell, I. (2014) Events Management. 3rd ed. London: Routledge.

Crowther, P. (2014) ‘Strategic application of events’, International Journal of Hospitality Management, 36, pp. 133–140.

Ferdinand, N. and Kitchin, P. (2017) Events Management: An International Approach. 2nd ed. London: Sage.

Fenich, G.G. (2015) Meetings, Expositions, Events, and Conventions: An Introduction to the Industry. 4th ed. Boston: Pearson.

Getz, D. and Page, S.J. (2016) Event Studies: Theory, Research and Policy for Planned Events. 3rd ed. London: Routledge.

Gonçalves, E. and Thomas, H. (2012) ‘Urban regeneration and waterfronts: Promoting place branding and tourism in Cardiff Bay’, European Planning Studies, 20(9), pp. 1541–1561.

Griffiths, R. (2011) ‘Wales: Culture, identity and tourism’, Tourism Management, 32(5), pp. 1101–1105.

Hernandez-Maskivker, G., Lapointe, D. and Aquino, R. (2020) ‘The role of digital marketing in promoting incentive travel destinations’, Tourism Review, 75(1), pp. 132–146.

Jones, C. and Munday, M. (2016) ‘Tourism and regional development in Wales: Progress and challenges’, Regional Studies, 50(5), pp. 1008–1021.

Jones, M. (2014) ‘Sustainable planning for event transport: Towards a conceptual framework’, Event Management, 18(2), pp. 181–194.

Laing, J. and Frost, W. (2017) ‘Sustainable event design’, Journal of Sustainable Tourism, 25(8), pp. 1104–1120.

Lashley, C. and Best, W. (2015) Risk and Safety Management in the Hospitality Industry. Oxford: Goodfellow Publishers.

Lee, J.S. and Back, K.J. (2013) ‘Examining antecedents and consequences of brand personality in the meeting context’, Journal of Convention & Event Tourism, 14(2), pp. 85–106.

Liu, H. and Lee, W. (2021) ‘The reshaping of incentive travel in the post-COVID era’, Event Management, 25(5), pp. 621–636.

Mair, J. (2013) ‘Profiling conference delegates using attendance motivations’, Journal of Convention & Event Tourism, 14(2), pp. 116–134.

Mair, J. and Weber, K. (2019) ‘Networking in the MICE industry’, Journal of Convention & Event Tourism, 20(3), pp. 187–204.

Pereira, E.L., Correia, A. and Schutz, R.L.A. (2015) ‘Sustainability indicators in incentive tourism: A case study of the Brazilian market’, Tourism Management Perspectives, 16, pp. 95–102.

Raj, R., Walters, P. and Rashid, T. (2013) Events Management: Principles and Practice. 2nd ed. London: Sage.

Richards, G. (2018) ‘Cultural tourism: A review of recent research and trends’, Journal of Hospitality and Tourism Management, 36, pp. 12–21.

Silvers, J.R. (2014) Professional Event Coordination. 2nd ed. Hoboken: Wiley.

SITE (2023) Incentive Travel Index 2023. New York: Society for Incentive Travel Excellence.

Smith, M.K. (2016) Issues in Cultural Tourism Studies. 3rd ed. London: Routledge.

Thomas, R. and Tallontire, A. (2015) ‘Sustainable tourism and destination governance in Wales’, Tourism Planning & Development, 12(3), pp. 320–334.

Tum, J., Norton, P. and Nevan Wright, J. (2013) Management of Event Operations. 2nd ed. Andover: Cengage Learning.

Visit Wales (2024) The Year of Croeso 2025: Strategic Briefing Document. Cardiff: Welsh Government.