Method Statement 1 – Piling
	Contract
	Contract No
	Prepared By
	Date
	Checked By
	Date

	NPTCBC - Bridge
	DC 5/27
	R.Murray
	04/2020
	J. Smith
	04/2020

	
	
	
	
	
	

	Operation
	Plant

	Install Driven Concrete Piles at locations specified in accordance with drawing No.D30168/PA/0008
	[bookmark: _GoBack]360 JCB Excavator
9 ton Dumping Truck
Piling Rig
9ton Impact Hammer

	Work Sequence
	Supervision and Mentoring

	Installation of Piling will confirm to requirements of BS EN 12699. Sequence of work will be as below;
· Excavate for Pile Cap.
· Erect Piling Rig
· Connect Piling Rig to Pre Cast Pile
· Using drop hammer and competent machine operator use hammer to insert pile
· Cut top of pile for Pile Cap.
· Cast Pile Cap (leaving enough reinforcement to tie into bridge support
	Site Engineer
Site Foreman
Piling Foreman
Operation to be monitored by Site Agent
Daily Check of Plant to be carried out.

	
	Controls

	
	Only Authorised personally to be allowed on site at all times.
When installing Piling care is to be taken to avoid HV Overhead Cables
Every ‘even’ numbered pile to be missed from first run through to prevent risk of damaging pile.
Care is to be taken when working near the Token Train Track, track is not to be disturbed during works.

	Emergency Procedures
	First Aid
	PPE Schedules

	Site Air Horn to be sounded and first aider to be called. Emergency Services to attend as required. All Site work to be stopped until determined safe to continue by Site Foreman.
	Air Horn to be kept in Welfare Compound.
Level 3 Qualified First Aider to be onside at all times.
First Aid box located in Welfare Compound.
	Hard Hats
Gloves
High Visibility Clothing
Steel Toe Capped Boots
Ear Defenders


(Layout - Cooke and Williams (2009, pp242)

Method Statement 2 – Bridge Module Installation
	Contract
	Contract No
	Prepared By
	Date
	Checked By
	Date

	NPTCBC - Bridge
	DC 5/27
	R.Murray
	04/2020
	J. Smith
	04/2020

	
	
	
	
	
	

	Operation
	Plant

	Pre-fabricated bridge sections to be brought to site and installed by Modular Transporter in accordance with drawing No.D30168/PA/0008
	SPMT - Modular Transporter

	Work Sequence
	Supervision and Mentoring

	1. SPMT arrives on site with Bridge Module.
2. Bridge module is lifted into place using the SPMT (operated by SPMT Qualified operator)
3. Moved into position with banksman.
4. Attached to bridge supports by working gang.
	Site Engineer
Site Foreman
SPMT Foreman and Operator
Site Working Gang

	
	Controls

	
	Only Authorised personally to be allowed on site at all times.
Only authorised and competent personal to be authorised to operate SPMT
Site Engender to inspect connections to bridge support
Care is to be taken when working near the Token Train Track, track is not to be disturbed during works.

	Emergency Proceedures
	First Aid
	PPE Schedules

	Site Air Horn to be sounded and first aider to be called. Emergency Services to attend as required. All Site work to be stopped until determined safe to continue by Site Foreman.
	Air Horn to be kept in Welfare Compound.
Level 3 Qualified First Aider to be onside at all times.
First Aid box located in Welfare Compound.
	Hard Hats
Gloves
High Visibility Clothing
Steel Toe Capped Boots
Ear Defenders


(Layout - Cooke and Williams (2009, pp242)
Method Statement 3 – Highway Construction
	Contract
	Contract No
	Prepared By
	Date
	Checked By
	Date

	NPTCBC - Bridge
	DC 5/27
	R.Murray
	04/2020
	J. Smith
	04/2020

	
	
	
	
	
	

	Operation
	Plant

	Lay new Highway in accordance with drawing No.D30168/PA/0008
	360 Degree Excavator
Tipper Lorry
Compaction Plate
Pedestrian Roller
TM Equipment

	Work Sequence
	Supervision and Mentoring

	One bridge modules are fitted and locked in place.
1. Lay new Granular Subbase Type 1, and consolidate to required depth.
2. Install proposed drainage and required by Site Engineer.
3. Install Street Lighting Utility Services in accordance with Site Engineer
4. Install new kerb line through use of mechanical lifting aids
5. Machine Lay binder course for carriageway and footway.
6. Machine lay surface course with additional compaction and surface course as required.
	Site Engineer
Site Foreman/Supervisor
Working Gangs (2 Qualified Trades Persons – 2 Labourers -TBC)

	
	Controls

	
	Only Authorised personally to be allowed on site at all times.
Care to be taken when installing kerbing, use mechanical lifting aids.
Drop Column Street Lighting to be installed (see HV Voltage Cables Risk Assessment).
Safety fencing to be erected along bridge until Pedestrian fencing can be installed.
PPE to be worn at all times.

	Emergency Procedures
	First Aid
	PPE Schedules

	1. Stop work immediately
2. Remove all personal from danger Area
3. Call First Aider or emergency services if required.
4. If emergency involves injury to persons or other property, follow company safety procedures
	Air Horn to be kept in Welfare Compound.
Level 3 Qualified First Aider to be onside at all times.
First Aid box located in Welfare Compound.
	Hard Hats
Gloves
High Visibility Clothing
Steel Toe Capped Boots
Ear Defenders


(Layout - Cooke and Williams (2009, pp242)
