## GANTT CHART
GANTT CHART
| TASK NAME | START DATE | END DATE | DURATION | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
1- 1.3
| Research local charities within Swansea area | 2019-10-14 | 2019-10-14 | 1/2 day | Lareesa, Ella and Rebecca | 100% | bar: WEEK 1 Th
| Come to an agreement with what chairty to work with | 2019-10-14 | 2019-10-14 | 1/2 day | Lareesa, Ella and Rebecca | 100% | bar: WEEK 1 Th
| contcat the charity to see if they would like us to fund raise for them for any specific items that they may need | 14/10/19 | 17/10/19 | 4 days | Lareesa | 100%
2-2.5
| Research the most effective ways of fundraising | 21/10/19 | 21/10/19 | 1/2 day | Ella | 100% | bar: WEEK 2 M to WEEK 3 M
| Pick the ideas best suited to own timescale and resources | 23/10/19 | 23/10/19 | 1/2 day | Lareesa, Ella and Rebecca | 100% | bar: WEEK 3 W
| Finalise a date for all the fundraising ideas | 23/10/19 | 23/10/19 | 1 day | Lareesa, Ella and Rebecca | 100% | bar: WEEK 3 W
3-3.5
| Contact the leader of the charity to organise a meeting date and time that suits both parties | 21/10/19 | 23/10/19 | 3 days | Lareesa | 100% | bar: WEEK 2 M to WEEK 3 W
| Gather all of our fundraising ideas in a presentable format in order to discuss these with the charity representative | 22/10/19 | 22/10/19 | 1 day | Rebecca | 100% | bar: WEEK 3 T
| Prepare a list of questions we need to ask during the meeting | 22/10/19 | 22/10/19 | 1 day | Ella | 100% | bar: WEEK 3 T
| During the meeting, we will establish how much physical involvement the charity wishes to have in the fundraising itself | 30/10/19 | 30/10/19 | 1/2 day | Lareesa, Ella and Rebecca | 100%
| We will finalise all fundraising ideas and dates with the charity | 23/20/19 | 23/10/19 | 1/2 day | Rebecca | 100% | bar: WEEK 3 W
4-4.4
| Secure event locations in Swansea | Mid November | Mid November | 1 week | Lareesa, Ella and Rebecca | 15%
| Gather equipment needed for various events including any food or drink needed for the cinema day and also raffle tickets, etc. | Mid November | Mid November (20-25th) | 1 Week | Lareesa, Ella and Rebecca | 10% | bar: WEEK 7 T to WEEK 7 F
| Gather equipment needed for various events including any food or drink needed for the cinema day and also raffle tickets, etc. | Mid November | Mid November | 1 Week | Lareesa, Ella and Rebecca | 10% | bar: WEEK 6 M to WEEK 7 F
| Promote events through social media, posters and word of mouth | Mid November | Mid November | Throughout | Lareesa, Ella and Rebecca | 10%
5-5.5
| Hold cinema day at the university | Mid November | Mid November | 1 day | Lareesa, Ella and Rebecca | 0% | bar: WEEK 7 T
| Hold raffle | Mid November | Mid November | 1 day | Lareesa, Ella and Rebecca | 0% | bar: WEEK 7 W
| Have a bake sale | Mid November | Mid November | 1 day | Lareesa, Ella and Rebecca | 0% | bar: WEEK 7 T
| Hold a chrismas jumper day | Mid November | Mid November | 1 day | Lareesa, Ella and Rebecca | 0% | bar: WEEK 7 W
| Carry out any other events that may be added closer to the time fo fundraising | Mid November | Mid November | 2 days | Lareesa, Ella and Rebecca | 0% | bar: WEEK 7 T to WEEK 7 W

## PROJECT SCHEDULE
| WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 5 | WEEK 6 | WEEK 7 | WEEK 8 | WEEK 9 | WEEK 10
| 29th Sep - 6th Oct | 6th Oct - 13th Oct | 13th Oct - 20th Oct | 20th Oct - 27th Oct | 27th Oct - 3rd Nov | 3rd Nov - 10th Nov | 10th Nov - 17th Nov | 17th Nov - 24th Nov | 24th Nov - 1st Dec | 1st Dec - 8th Dec
Project Stage
1.1 Research local charities within the Swansea area | bar: WEEK 1
1.2 Come to an agreement on which charity to work with | bar: WEEK 1
1.3 Contact the charity to see if they are happy to work with us and find out if there is any specialist equipment that they need | bar: WEEK 1
2.1 Research the most effective methods of fundraising | bar: WEEK 2
2.2 Make a list of all the ideas that best suited our timescale and resources | bar: WEEK 2
2.3 Make a final list of the fundraising ideas we have chosen to use | bar: WEEK 2
2.4 Finalise a date for the fundraising ideas we choose | bar: WEEK 2
3.1 Contact the leader of the charity and get a response in order to organise a meeting date and time that suits both parties | bar: WEEK 3
3.2 Gather all of our fundraising ideas in a presentable format in order to discuss these with the charity representative | bar: WEEK 3
3.3 Prepare a list of questions we need to ask during the meeting | bar: WEEK 3
3.4 During the meeting, we will establish how much physical involvement the charity wishes to have in the fundraising itself | bar: WEEK 4 to WEEK 5
3.5 We will finalise all fundraising ideas and dates with the charity | bar: WEEK 4 to WEEK 5
4.1 Secure event locations in Swansea | bar: WEEK 7
4.2 Gather equipment needed for various events including any food or drink needed for the cinema day and also raffle tickets, etc. | bar: WEEK 7
4.3 Promote events through social media, posters and word of mouth | bar: WEEK 5 to WEEK 10
5.1 Hold cinema day at the university | bar: WEEK 10
5.2 Hold raffle | bar: WEEK 10
5.3 Have a bake sale | bar: WEEK 10
5.4 Hold Christmas jumper day | bar: WEEK 10
5.5 Carry out any other events that may be added closer to the time of fundraising | bar: WEEK 10