Problem Solving and Decision Making

Green Haven Florist

Name of the university: University of Wales Trinity Saint David (London Campus)

Student Name: Cherelle Egan

Student ID: 2443051

Module Code: LCLM4004

Module: problem Solving and Decision Making

Lecturer: Anita Nan

Introduction

Social media has become a critical marketing tool for small businesses, particularly within visually driven industries such as floristry. Green Haven have a had a 30% decrease in sales and low foot traffic into their store. Social media platforms such as Instagram and Facebook offer an effective way to showcase products, engage customers and increase sales.

This assignment presents an action plan, alongside a monitoring and evaluation. This is to help improve the social media performance of a florist business. The plan focuses on identifying key issues, prioritising products for promotion, recruiting appropriate expertise and establishing a consistent content strategy. Monitoring and evaluation are then used to assess effectiveness and help to support improvement.

By applying work focused business planning techniques, this assignment demonstrates how strategic decision making supported by data and evaluation can enhance a businesses performance.

The florist industry is highly competitive, with many businesses offering similar products and services. As a result, differentiation and brand visibility are essential for attracting customers. Social media provides florists with a cost effective platform to promote floral arrangements. Implementing a well-planned social media strategy has the potential to increase visibility, improve customer engagement and ultimately support the recovery and growth of Green Haven Florist.

Problem;

- 30% decrease in sales as low foot traffic into store

Chosen Solution:

- Use social media to boost sales

Action plan

| Actions | Description | Time frame | Staff responsible |
| --- | --- | --- | --- |
| Identify and document the main issues | Managers need to meet and identify the main issues affecting the florist’s social media presence, such as low engagement and lack of online orders. Key areas that need the most attention should be clearly recorded. | 8th Dec 2025 – 12th Dec 2025 | Liam and Priya |
| Identify what needs to be promoted the most on the social media account. | Management needs to agree on which products and services should be prioritised for promotion on social media, such as floral arrangements, seasonal offers or special events. This will ensure that such things get greater online visibility. | 15th Dec 2025 -18th Dec 2025 | Liam and Priya |
| Recruit a social media manager | Managers need to set up interviews and recruit a suitable social media manager who has experience promoting small businesses and visually driven products such as flowers. | 19th Dec 2025 | Liam and Priya |
| Decide how often things are online | Develop and agree on a posting schedule that outlines how often content will be uploaded to social media platforms. | 22nd Dec 2025 | Social media manager |
| Deliver Staff Training session. | Training will be delivered to relevant staff on how to support social media activity, including taking high quality photos of floral arrangements, responding to customer enquiries. | 29th Dec 2025 (3 hours) | Internal/ External Trainer |
| Evaluate social media accounts | Questionnaire and provide feedback on whether social media is helping with bringing in more customers and boosting sales. | 29th Dec 2025 (30 minutes) | Social Media Manager/ Liam and Priya |

SAMPLE MONITORING AND EVALUATION PLAN

| MONITORING |  |  |  |
| --- | --- | --- | --- |
|  | Description | Time frame | Staff responsible |
| Participation | Number of followers gained and reach of social media posts (e.g. views on Instagram/Facebook posts and stories). | Daily | Social Media Manager |
| Engagement | Keep track of the level of customer engagement on social media, including likes, comments, shares, saves and direct messages about floral arrangements, promotions and seasonal content. | Daily | Social Media manager/ Liam and Priya |
| Sales impact | Number of enquiries and sales generated through social media, such as orders for floral arrangements, events or special offers. | Weekly | Manager |
| Sales conversation | Monitor the number of confirmed sales that can be directly linked to social media activity, such as orders placed via links, messages or promotional codes. | weekly | Social Media Manager |
| Content Performance | Analyse the performance of different content types (e.g. bouquets, weddings, sympathy flowers, seasonal offers) to identify which posts contribute most effectively to sales. | weekly | Social Media Manager |
| Effectiveness of social media strategy | Evaluate whether the social media strategy has met its objectives in terms of increasing brand awareness, customer engagement, and online sales. Performance data will be assessed to determine whether targets are being met and if any adjustments are needed. | Weekly | Social Media Manager |
| Evaluation |  |  |  |
| Success Indicator(s) | Data source / Information collection method | Time frame | Staff responsible |
| Customer Feedback | Review customer comments, messages and reviews to evaluate customer satisfaction and identify areas for improvement in product presentation or online communication. | Weekly | Social media manager/ Liam and Priya |

The overall Aim of this action plan is to improve Green Haven Florists sales and to build on customer engagement and brand awareness.

The specific objectives are to:

- Improve brand visibility

- Increase foot traffic and online enquires through social media platforms.

- Establish a consistent content strategy supported by monitoring and evaluation.

- Sale improvement