Structure of the project plan:

- A table of content

- A brief introduction about the project you selected.

- Aim, objectives, scope of the project you selected.

- Main body should include explaining the following areas with the use of sub-headings

- Listing the project outputs (deliverables and other direct results)

- Identify all stakeholders and deliverables associated with your project.

- Develop a communication plan and establish type of information that must be transmitted to each stakeholder

(See learning week 3 teaching materials)

- Identify the activities required to deliver the outputs (keeping on mind that Work Breakdown Structure to be developed)

List and group all activities related to your project plan and chose a suitable breakdown structure for your project:

- WBS: Work Breakdown Structure

  - A hierarchy of work

- PBS: Product Breakdown Structure

  - A hierarchy of products

- OBS: Organisation Breakdown Structure

  - More than an organisation chart

- Dividing these activities into sub activities and tasks and showcase through a Work Breakdown Structure.

- Identifying the deliverable and milestone(s) of each task (timeline to complete)

Use a responsibility matrix to assign task

- Consider the usage of the resources (personnel and material) required to complete each task

- Use all available resources and generate a cost account

(See week 4 teaching materials)

- A reference list using Harvard style.