Mehek Sayeed 1709656

Executing Process of the Project Life Cycle

Team leader Nasima allocated me the Execution Process of the Project Life

Cycle. Execution is the stage that is most generally associated with the actual

project management. Project Management must count on intensive activity in

the course of this time, from allocating resources and constructing

deliverables. This growing improvement updates repute critiques and overall

performance reports (Office Timeline, 2017). In this stage the activities

completed were printouts of the survey, which was distributed to BAME

Graduates, we team members already know. Promoted the survey using Social

Media, emailing the survey links to peer students and lecturer, which helped

us to reach out to as many BAME Graduates possible and lastly one to one

phone interview as this was the BAME Graduates preferred method to

respond.

Work Breakdown Structure (WBS) (First Slide)

During the project planning phase, an essential tool we utilised was the WBS

Framework. According to Rouse (2019), a WBS tool shortly known as the Work

Breakdown Structure in project management is a deliverable-orientated

breakdown of a task into smaller components. Malsam (2019), refers to, a

work breakdown structure additionally provides an important framework for

designated value estimating and manage along with offering guidance for

timetable development and control. This framework was a key to a good

technique for me to achieve the project’s deliverables (Tutorials point, 2019).

Our main three deliverables were Online Survey, One to One Interview and

arranging a Focus Group Meeting for the BAME Graduates in Wales. According

to Malik (2014), the benefit of creating a WBS Framework helped me to

identify and value the tasks that are involved in this project, which requires

what needs to be done step by step. For the project we took a top down

approach to follow the planning structure of the tool. In the initial stage of the

WBS was the Online Survey.

Advertising on Social Media (Second Slide)

Week two, the team had distributed the printouts of the survey as planned,

which then I had decided to deliver via Social Media, as the printouts were not

the best option for the Graduates. However, very few had only taken part in

filling the questionnaires. Therefore, I had promoted the survey links with a

small message to spread the word on Facebook, LinkedIn, Instagram and using

WhatsApp. All the responses we received via Facebook and other media were

liked, shared, with comments from the people who had browsed the survey

link. The link was passed onto the peer students and lecturer via LinkedIn and

emails for acknowledgement. On WhatsApp, some of the Graduates we knew

had sent the screenshots of their responses for our feedback.

As part of our constant monitoring of the project we held a meeting with

Stakeholder Ginger from EYST. The purpose of this meeting was to get an idea

of the BAME Graduate responses and to receive feedback from Ginger

regarding our contribution to the desired target she had in mind, as well as to

keep regular communication with the organisation.

The second element of our WBS was a One to One interview over the phone.

As this Graduate resides outside of Wales, a telephone interview was a more

appropriate method to obtain the response. In order to carry out the

interview, I arranged a convenient time with the Graduate, which was best

suited to him. In this interview, I used the guideline questionnaire from EYST

and then recorded the responses by filling in the survey myself.

As our third branch of WBS we planned to do a focus group meeting in week

four. Conducting the element would have been beneficial, as it shows a clear

understanding and concerns being raised by each member while giving their

views and opinions. Also, the Graduates would feel comfortable and relaxed,

to share their experiences and stories with all group members without

hesitation (Eccleston, 2013). Unfortunately, due to the lack of availability of

BAME Graduates we were unable to execute this task. To improve better in

future, I would advertise more on Social Media, look for convenient venues,

more convenient times for Graduates and may be offer transport if necessary.

However, this did not prevent the responses coming through as the other

available options were proving to be more popular.

References

Eccleston, C.H. (2013) The EIS Book: Managing and Preparing Environmental Impact Statements, United states: CRC Press.

Malik, N. (2014) ‘What are the Key Benefits of a WBS?’ [Online] https://www.quora.com, (Accessed Date: 23rd October 2019).

Malsam, W. (2019) ‘3 Best Project Management Charts for Project Planning’ [Online] https://www.projectmanager.com, (Accessed Date: 24th October 2019).

Office timeline. (2017) ‘Conquer the 5 Phases of the PM Life Cycle’ [Online] https://www.officetimeline.com, (Accessed Date: 24th October 2019).

Rouse, M. (2019) ‘Work Breakdown Structure (WBS)’ [Online] https://searchsoftwarequality.techtarget.com, (Accessed Date: 24th October 2019).

Tutorials Point. (2019) ‘Estimation Techniques – WBS’ [Online] https://www.tutorialspoint.com, (Accessed Date: 24th October 2019).