Qualification: CIPD Diploma in Applied Human Resources

Module Name: Contributing to the Management of Change

Word Count: 2900

Student Name: Sarah Mills

Student Number: 1907114

CIPD Membership Number: 54832957

By signing below, I confirm that the work/evidence presented is my own, unaided work. I understand the regulations pertaining to candidate malpractice and the action that may be taken as a result.

Signed: S L Mills

Date: 19/01/2021

Contents Page

Evidence Matrix	2

LO1 Personal Statement	3

Evidence for LO1	6

References for LO1	7

LO2 Personal Statement	8

Evidence for LO2	10

References for LO2	10

LO3 Personal Statement	12

Evidence for LO3	14

References for LO3	14

# Evidence Matrix

# LO1 Personal Statement

Be able to plan for the implementation of change processes within an organisation.

According to the APM Body of Knowledge (n.d.) change management is ‘a structured approach to moving an organisation from the current state to the desired future state’. Furthermore, research has shown that how this change process is managed is pinacol to its success, with failure rates sitting at 70% (CIPD, 2020a).

The biggest impact of organisational change is on its people, they are the most valuable asset to an organisation, so it would make sense that people/HR professionals are best equipped to support and drive effective change in the workplace. (CIPD, 2020a)

1.1 Establish the need, objectives, and potential benefits in relation to a specific change requirement.

In December 2018 Tai Tarian introduced an Employee Assistance Programme to support the Organisations Health and Wellbeing agenda. In its first year of launch, the programme was extremely successful with high usage levels and gained fantastic feedback from employees and Managers. However, in November 2019, I was asked to lead a project in changing from our initial EAP provider to a new one entirely.

Like many change initiatives the main driver for this was based around internal financials and identified as a cost saving initiative. (Abukhames, 2015) The change came following a contract renewal discussion in October 2019 with our Group Income Protection (GIP) Insurance provider Unum. They offered a free EAP programme, which also included an employee discount scheme as part of the contract that we were already paying for.

Unfortunately, I was not part of the decision to initiate this change as this was made at a more senior level. I personally feel that the decision to switch EAP providers was made with lack of thought or analysis, simply changing due to the benefit of cost savings.

If I had been part of identifying the case for change, I would have utilised a SWOT analysis to evaluate the strengths, weaknesses, opportunities, and threats represented by the impending change. This would have provided a broad and simple perspective on the case for change, supporting the outcome decision. (CIPD, 2020b)

The main objective of the project was to switch across to the new provider efficiently and effectively minimising any impact to employees.

1.2 Analyse who will be affected by the changes and their potential information and support needs.

Mindtools (n.d) explain the importance of stakeholders within project management, they can be extremely supportive and influential, or equally they can be a major blocker of a change initiative, therefore it is important to identify, prioritise and understand all stakeholders. This can be analysed through a stakeholder mapping tool, which I have utilised in (EV1).

The map identifies the priority stakeholders as frontline staff and first line managers. See Figure.1 to identify the impact level, information needed, and support required.

Figure 1. Analysis of needs

| Stakeholder | Stakeholder Grouping (from map) | Impact level | Information Required | Support Required |
| --- | --- | --- | --- | --- |
| Frontline Workforce | Key player | High | Full detail of new EAP offering, benefits of the change, website/app/telephone details. | Instructions on how to sign up to new website. Follow up support if needed. Demonstrations on navigating the new site. |
| First level management | Key player | High | Full detail of new EAP offering, benefits of the change, website/app/telephone details. Need a good understanding to promote to teams. | Instructions on how to sign up to new website. Follow up support if needed. Demonstrations on navigating the new site. Information booklets to have to hand to sign post team members when required. |
| Senior management | Keep satisfied | Medium | Full detail of new EAP offering, benefits of the change, contact details. | Reactive support when/if required |
| Executive management | Keep satisfied | Medium | Basic information of the new EAP offering, simply be aware of the new provider and what they can offer. | Reactive support when/if required |
| Board | Keep satisfied | Low | Basic information of the new EAP offering, simply be aware of the new provider and what they can offer. | Reactive support when/if required |
| Trade Unions | Key player | High | Full detail of new EAP offering, benefits of the change, any negative impact to employees. | Reactive support when/if required |
| Occupational Health Partners | Minimal effort | Low | Basic information of new EAP offering so that medical practitioners can sign post employees if required during medical appointments. | Reactive support when/if required |
| Benefits Partners | Minimal effort | Low | Basic information of new EAP offering to advertise on Benefits portal. | Reactive support when/if required |

In relation to the specific stakeholders, it is important to note that if the pending change was going to impact employees’ terms and conditions, then I would have consulted with the Trade Union representatives, however in this case it was appropriate to just advise. (Gov, n.d.)

The change initiative itself is a relatively small-scale change with an overall low impact to the organisation. The main aim was to ensure all the required information about the new EAP provider was communicated effectively and made available and accessible to all. If this aim was achieved, then I anticipated proactive follow up support would be minimal.

I identified that potential follow up support may be required in relation to signing up to the new website and navigating the pages. Therefore, I planned that for the first 2 weeks of the launch I would drop in on team meetings to provide demos of the website, along with facilitating open drop-in sessions over lunchtime for anyone to attend.

In anticipation to any resistance to the change, the opportunity of open discussions was in place with the aim to resolve the conflict quickly and effectively, as suggested by CMI (2014). Failing this, the grievance procedure was also readily available to follow.

  - Identify the resources required for the change process and how these will be made available.

I identified the main resource for the initiative as administration time. Given the short timeline between planning and implementation, I needed the support from the rest of the HR Team. A project plan was drafted which assigned actions and timelines to each member of the team, it was then expected that individuals book out appropriate timeslots into their calendars to ensure the actions were completed by the deadlines set. Meetings were planned in to review progress.

IT support was required in order to update the internal intranet with the new EAP providers details and to ensure the new App was downloaded and available on all work desktops and Ipads. I contacted the IT Manager in advance to understand how long the actions would take and who would be responsible from the team to support. (EV2)

I knew that effective communication was key for this change to be successful, therefore I planned time in with the communications team to discuss the change and support resource required from them. (EV3)

Promotional materials were needed to advertise around the office building, I ordered these via email through our broker Willis Towers Watson.

  - Devise a plan, including objectives, actions, and timescales for implementing the required change.

As mentioned above, I drafted a project plan which can be found in (EV4). However, following the learnings through this model, if I were to plan the change again, I would utilise the 3 phases as set out by SHRM (2015) design, enact, and sustain. This would involve a much deeper level of planning utilising a change plan as found in (EV5).

  - Communicate the change plan, and gain agreement for its implementation, from decision makers.

My project plan, inclusive of the required actions, were put forward to my line manager during a meeting on Monday 18th November 2019. See (EV6) evidencing the calendar invite for the meeting. Unfortunately, my manager is no longer in the Organisation, so I am unable to ask her to provide a witness statement about the content of meeting. I can confirm that she agreed the actions as I then set up a meeting for the full HR team to delegate actions and timelines to each team member. See (EV7) of calendar invite of meeting.

# Evidence for LO1

Evidence 2 & 3 are emails that would not attach to this document, therefore have been emailed directly to Julie Thomas.

# References for LO1

Abukhames. H (2015) LinkedIn Article. ‘Internal Factors that May Affect the Business Organisation’. Available at: https://www.linkedin.com/pulse/internal-factors-may-affect-business-organization-hatim-abukhames/  (Accessed on: 06th January 2021)

APM (n.d.) Introduction to Managing Change. Available at: https://www.apm.org.uk/media/6860/introduction-to-managing-change.pdf  (Accessed on: 11th January 2021)

Association for Project Management (2017) Introduction to Managing Change. Available at: https://www.apm.org.uk/media/6860/introduction-to-managing-change.pdf (Accessed on: 09th January 2021)

CIPD (2020a) Change Management Factsheet. Available at: https://www.cipd.co.uk/knowledge/strategy/change/management-factsheet  (Accessed on: 11th January 2021)

CIPD (2020b) SWOT Analysis. Available at: https://www.cipd.co.uk/knowledge/strategy/organisational-development/swot-analysis-factsheet (Accessed on: 06th January 2021)

CMI (2014) Implementing an effective change programme. Available at: https://www.managers.org.uk/wp-content/uploads/2020/03/CHK-040-Implementing_an_effective_change_programme.pdf  (Accessed on: 11th January 2021)

Gov.UK. (n.d.) Working with trade unions: employers. Available at: https://www.gov.uk/working-with-trade-unions/informing-and-consulting-with-unions  (Accessed on: 11th January 2021)

Mindtool (n.d.) Stakeholder analysis. Available at: https://www.mindtools.com/pages/article/newPPM_07.htm (Accessed on: 08th January 2021)

SHRM (2015) Leading Effective Change: A Primer for the HR Professional. Available at: https://www.shrm.org/learningandcareer/learning/pages/cm-lrt.aspx (Accessed on: 12th January 2021)

# LO2 Personal Statement

Be able to implement a change.

2.1 Follow the agreed plan to implement change processes.

The turnaround time between plan and implementation was noticeably short for this change, I was first informed of the plan to change on 04/11/2019 (EV8) with an aim to launch on 01/12/2019. Due to the time constraints, I needed to utilise good project management skills to keep the process on track. (SHRM, 2015) This included excellent communication skills to ensure everyone that was part of the project team knew the vision and benefits, along with the actions and timelines that they were responsible for. (APM, n.d)

I considered using a Gannt Chart to monitor the implementation, according to the Association of Project Management (n.d.) this is one of them most popular used tools as they can simplify a complex project by providing a visual display of the overall project. However, due to the fact that this was a relatively quick and simple change, and the fact that the gannt chart can sometimes be overcomplicated with so much detail (Naybour, 2014) I decided to use a simple excel spreadsheet with actions, responsibilities, and deadlines (EV4).

I arranged weekly meetings with the rest of the HR Team to understand progression and any potential delays to the milestones. When an action was complete, the date was added to the project plan and the cell turned green if the action was completed on time or red if it passed the initial deadline date.

2.2 Provide information and support to stakeholders in line with their identified requirements.

Prior to the communications going live to all employees, in line with the stakeholder mapping exercise I needed to inform a number of stakeholders first, see (EV 9-11) evidencing the emails sent out to the relevant stakeholders explaining the change.

Prosci (n.d.) highlight the importance of having managers onboard with the changes especially as they are the usual route of communication to employees. Therefore, during a monthly Team Leader catch up, I spoke in depth about the change, the impacts, and how they could support with ongoing communication to their teams. See (EV12) of powerpoint slides and a follow up email (EV13).

In line with the project plan and communications strategy (EV14) the information of the change was communicated out to all employees via an internal magazine ‘The Advisor’ the week of the launch (EV15). This was followed by me uploading all employees’ emails to the admin portal to trigger an email from the new EAP provider to all staff inviting them to sign up to the new website.

As mentioned in the planning phase, I dropped in on team meetings to provide demos and held open sessions for the first 2 weeks, although these did not prove popular, with only one employee attending for support with signing up. I would like to think that this was down to the fact that the sign-up process was very straight forward so my support was not required.

2.3 Apply techniques for maintaining positive working relationships throughout the change processes.

Although ACAS (2015, Pg.14) suggest that to maintain positive relationships you should be completely honest with employees as to the rationale behind the change, I did not feel it was appropriate to communicate out to employees that the instigating factor of the change was financial gain, therefore the communication focus was around the benefits of the change. If I were to repeat the exercise, I would definitely adapt the initial communication (EV15) as I feel not enough emphasis was put on the extra benefits that came with the new provider.

I was aware of a small number of employees who were in the middle of blocks of counselling sessions with the current provider. With the announcement of the changeover, I anticipated they would be concerned about what would happen with their remaining sessions. I reached out to them individually via telephone to put their mind at ease by confirming the rest of the sessions would not be impacted. See (EV16 & 17) for a witness statement and a follow up email from one of the employees.

As the change was a relatively small initiative in relation to impact, I did not anticipate there being any resistance to the change. However, if I were working on a large-scale change project which had increased people impact, I would utilise a change model such as the ‘Kubler-Ross Change Curve’ to anticipate the potential reactions to change and dependent on the findings, put support mechanisms in place to effectively manage these (Harrison, 2020).

With the support of the communications team, I ensured the communication remained regular. The details of the new scheme, along with instructions on how to access the service, were advertised bi-monthly in the Organisations internal communications magazine ‘The Advisor’. This made sure the momentum was maintained (CIPD, 2015).

2.4 Monitor the effectiveness of implementation, agreeing and making justified adaptions where required.

Utilising the project plan to monitor progression was important to ensure the implementation action remained on track. However, I was flexible with the understanding that, as suggested by CMI (2014) I needed to remain honest with my assessments of progress and be open to make adaptions if and when required.

The first blocker at the start of the implementation phase was that the promotional materials which needed to be located around the building were lost in the post (EV18). Due to the importance of the information needing to be available and accessible, we printed our own version until a newly sent batch arrived.

Initially one of the only ways to measure whether communications had been successful was to look at how many employees had signed up to the new website. When I checked the figures on 20th January 2020, 7 weeks after the comms launched, only 55 employees had signed up. I tried not to feel disappointed in the figures as according to Armstrong (2016, P.678) ‘change initiatives will always involve failure as well as success. The failures must be expected and learnt from.’ Instead, this led to a change in the communication focus, sending out another article in the ‘Advisor’ this time focusing more on the website content (EV15) and arranging for the communications to be shared via the private ‘Team Tai Tarian’ social media group (EV19). Both actions led to a surge in uptake and I continued to monitor the uptake on a monthly basis, manually releasing reminder sign up details quarterly or when appropriate (EV20).

Another adaption came in the way of new starters and leavers to the organisation, it became apparent that I had not thought about this during the planning phase, therefore needed to adapt the recruitment and leaving processes to include adding/removing employees from the service via the admin portal.

2.5 Maintain records of the change process in line with the organisational requirements.

See (EV21) highlighting the location for all records in relation to this change initiative.

# Evidence for LO2

Evidence 8-11, 13, and 17-19 have been emailed directly across to Julie Thomas as they would not successfully transfer across to this main document.

# References for LO2

ACAS (2015) How to Manage Change Advisory booklet. Available at: https://archive.acas.org.uk/index.aspx?articleid=4669  (Accessed on: 9th January 2021)

APM (n.d.) What is a Gantt chart. Available at: https://www.apm.org.uk/resources/find-a-resource/gantt-chart/ (Accessed on: 16th January 2021)

APM (n.d.) What skills do you need to become a project manager? Available at: https://www.apm.org.uk/jobs-and-careers/career-path/what-does-a-project-manager-do/skills-you-need-to-become-a-project-manager/  (Accessed on: 13th January 2021)

Armstrong, M., and Taylor, S. (2017) ARMSTRONG’S HANDBOOK OF HUMAN RESOURCE MANAGEMENT PRACTICE. (14th Ed). New York: Kogan Page

CIPD (2015) Landing transformational change: closing the gap between theory and practice. Available at: https://www.cipd.co.uk/Images/landing-transformation-change_2015-gap-theory-practice_tcm18-9050.pdf  (Accessed on: 09th January 2021)

CMI (2014) Implementing an effective change programme. Available at: https://www.managers.org.uk/wp-content/uploads/2020/03/CHK-040-Implementing_an_effective_change_programme.pdf  (Accessed on: 17th January 2021)

Harrison, T. (2020) Mind Journal - The Kubler Ross Change Curve: Understanding the 5 Stages of Change. Available at: https://themindsjournal.com/kubler-ross-change-curve/ (Accessed on: 9th January 2021)

Naybour, P. (2014) Using a Gantt Chart to manage a project schedule. Available at: https://www.apm.org.uk/blog/using-a-gantt-chart-to-manage-a-project-schedule/ (Accessed on: 16th January 2021)

Prosci (n.d.) Organisational Change Management Checklist. Available at: https://www.prosci.com/resources/articles/change-management-planning-checklist (Accessed on: 16th January 2021)

SHRM (2015) Leading Effective Change: A Primer for the HR Professional. Available at: https://www.shrm.org/LearningAndCareer/learning/PublishingImages/Pages/Forms/AllItems/Leading%20Effective%20Change%20-%20SHRM%20Foundation.pdf  (Accessed on: 16th January 2021)

# LO3 Personal Statement

Be able to assess the impact of change processes within an organisation.

3.1 Measure the effectiveness of the change process in meeting the required objectives.

The main objective of this initiative was to switch over to the new EAP provider efficiently and effectively minimising any impact to employees, while saving financially. It was always going to be difficult to measure the success of the new EAP provider as employees will only use the service when it is needed. However, I utilised other measures of success as suggested by Prosci (n.d.)

Measures of success:

- Execution of project plan was successful with no major delays.

- Since launch, there has been no resistance to the change from anyone.

- Minimal follow up support required from employees which would suggest the communications were effective with instructions.

- Financials – An annual saving of £4422.00. This was the cost of 12 months with our previous EAP provider (EV22). The new EAP was free as part of a current GIP contract.

- Within 12 months of launch, 189 employees out of 513 have signed up for the new website. (EV23)

Considerations:

The metrics show that in 2020, 19 employees utilised a specific service of the EAP, a breakdown can be found in (EV24). However, this compared to 12 months data with the previous EAP provider, which was 99 calls, would suggest the uptake has fallen considerably. I find this concerning as due to the pandemic I would imagine that the EAP services have been needed now more than ever.

3.2 Identify further work required to embed changes/and or further developments required.

Due to the dramatic drop in usage figures, I would suggest the potential of focus groups with employees who are happy to share their experiences with new EAP service. However, due to the sensitivity of the service, which is completely confidential, this may not appeal to many employees, therefore a confidential pulse survey may be more effective.

Evaluate the differences between the two offerings. This is something that I would have spent considerable time on when considering the initial change, however as I explained I was not part of the decision-making process.

During the pandemic I personally I have spent a lot of time on the EAP website searching through content which has proved to be invaluable. I am hugely impressed with the content on the website, however, appreciate it can be difficult to navigate through as there is so much on there. I believe targeted advertising will be beneficial, for example, as part of the wellbeing strategy, advertise the meditation/yoga sessions that can be accessed via the website, providing screenshots on how to navigate to the sessions.

3.3 Communicate the key outcomes and the impact of change to stakeholders.

See attached (EV25) which is an email from myself to the HR Manager and OD Manger summarising the findings and my thoughts.

Following the email, I have been asked to draft a formal business case comparing both offerings, especially from a financial perspective. For example, looking at how much has been spent on funding private counselling sessions vs the annual spend of the health assured contract.

3.4 Evaluate the effectiveness of own performance in contributing to the management of the change.

Change is one of the core knowledge elements on the new CIPD Profession Map (CIPD, 2020). Therefore, I have measured myself against the criteria set in the standards section.

Prior to undertaking this qualification, I had no knowledge of the different change models/theories and simply undertook change within my role based on a common sense approach. The learnings from this module however have given me confidence that I have been following a number of the best practise elements of the change management process. E.g. planning, communication and participation (CMI, 2014). It has also provided me with key learnings in terms of models to anticipate differing reactions to change and how important agility is for successful transformation.

In previous change initiatives, including this one, I do not feel I have put enough planning and emphasis into the communication strategy, this module has taught me the importance of tailoring communication to differing stakeholders (ACAS, 2015) as this element can be crucial to success or responsible for the failure of the whole process (Forbes, 2017).

My current Organisation are very averse to change, therefore I need to work on Manager capability and strong procedures in relation to the elements of a change ready culture, such as:

- Encouraging employees to question the status quo.

- Influence the idea that mistakes should be utilised as learning opportunities.

- Provide praise and recognition for ideas.

- Encourage open and honest communication.

(Macpherson, n.d.)

At this point I would evaluate myself between the Foundation and Associate Level on the standards section, however, by embracing all I have learnt, I believe going forward I will confidentially be working at the Associate Level.

# Evidence for LO3

Evidence 24 & 25 have been emailed directly to Julie Thomas as they would not successfully transfer onto this document.

# References for LO3

ACAS (2014) How to Manage Change. Available at: www.acas.org.uk (Accessed on: 18th January 2021)

Chartered Institute of Personnel and Development (2020a) New Profession Map. Core Knowledge – change. Available at: https://peopleprofession.cipd.org/profession-map/core-knowledge/change  (Accessed on: 18th January 2021)

CMI (2014) Change Management ‘Checklist’. Available at: https://www.managers.org.uk/knowledge-and-insights/resource/change-management/ (Accessed on: 18th January 2021)

Forbes (2017) 6 Principles For Communicating A Powerful Vision For Change. Available at: https://www.forbes.com/sites/brentgleeson/2017/03/15/6-principles-for-communicating-a-powerful-vision-for-change/?sh=7a5da0a43097 (Accessed on: 18th January 2021)

Macpherson, C. (n.d.) Change and Strategy – Is your culture ready for change? Available at: www.changeandstrategy.com/culture-ready-change (Accessed on: 18th January 2021)

Prosci (n.d.) Thought Leadership Article ‘Metrics for Measuring Change Management’. Available at: https://www.prosci.com/resources/articles/measuring-change-management-effectiveness-with-metrics (Accessed on: 17th January 2021)