University of Wales Trinity Saint David

Ordnance, Munitions and Explosives

Determination of the TNT equivalence of Nitromethane in charges of 15kg or less

Research Proposal

Natalie Coplin – 2113351

Date – 06/2025

Contents

1. Introduction	2

2. Background to the Proposed Research	2

3. Aims & Objectives	4

4. Experimental Design	5

4.4 Risks & Limitations	5

4.5 Ethical Issues	6

6. Resources & Planning	7

6.1 Resources Required	7

6.1.1 Physical Resources	7

6.1.2 Human Resources	7

6.2 Gantt Chart	8

References	9

Appendix 1	10

# 1. Introduction

Det Norske Veritas (DNV) Spadeadam Research and Testing conducts full-scale blast research and testing, assessing protective infrastructure against accidental explosions and terrorist attacks. Until recently, this was conducted using Plastic Explosive 4 (PE4). However, the current economic and military climate has resulted in PE4 being difficult to source at reasonable costs and timelines. As such, alternatives are being considered.

Nitromethane (NM) (CH3NO2) has been used on-site as an alternative explosive, but only for large-scale tests. DNV now requires the feasibility of using it in small scale tests to be examined, and to find how comparable it is to PE4. In doing so, a Trinitrotoluene (TNT) equivalence value will be determined, allowing a direct comparison of energy released – also ensuring validity of future testing using nitromethane.

# 2. Background to the Proposed Research

Nitromethane is a clear, colourless liquid at room temperature, commonly used as a fuel in drag cars - but it has also been used in mining as an explosive [1]. Nitromethane is not classed as an explosive, rather as a flammable liquid, but if given the correct stimulus will detonate [2] [3]. However, this requires an appropriate booster - meaning it is relatively safe to handle [4].

Comparing explosive performance of different materials requires a reference point. As the effects of TNT blasts are well understood and documented, it became the baseline for comparisons – hence “TNT Equivalence” (TNTeq) [5]. However, there are many methods to calculate it due to a range of test methods, often producing a spread of values [6] [7]. When considering TNT equivalence, understanding of which parameter is being assessed is essential. A common method is measuring the peak pressure from a spherical bare charge at different distances from the charge [8]. It has been shown that far-field TNT equivalence values do not vary significantly as the effect of the interactions of the rapidly expanding products of detonation and shocked atmosphere is no longer a factor [9]. However, to confirm this and have confidence in the results, pressure gauges will be placed at a range of distances from the charge.

The author intends to use the methodology mentioned above; it is the existing process used at DNV, allowing a comparable TNT equivalency to be calculated for all common explosives used on site in blast tests. DNV has access to a vast collection of data, and where appropriate, this will be utilised to enhance the data set that will be produced by this project.

Jaansalu et al [8] and Xiao [9], also note that TNT equivalency can be influenced by factors other than the explosive. Confinement of the explosive and geometry of any container may play a part depending on the material properties. This has been considered, and the NM container is of light weight plastic construction which will not influence the detonation. The geometry will not vary between charges.

A completed ethics form can be found in Appendix 1.

# 3. Aims & Objectives

This project aims to:

- Establish a TNT equivalence for nitromethane in charges of 15 kg.

The objectives of this project are:

- Conduct a literature review into the use of nitromethane as an explosive.

- Perform a series of blast tests to collect pressure-time data.

- Analyse data and calculate a TNT equivalence for nitromethane.

- Undertake a blast test to validate the test procedure.

# 4. Experimental Design

DNV has an established blast test standard for the use of nitromethane in 100kg charges. As the aim of this project is to investigate if the charge size of nitromethane can be scaled down, the same test procedure will be followed, albeit with a smaller charge.

All tests will be performed at DNV Spadeadam. The tests will be conducted in line with the requirements of the site explosives licence and established safe procedures [10]. For each test, pressure gauges will be mounted at appropriate distances from the charge (i.e. 5m, 7.5m and 10m). Each gauge will be connected to a data logger. The nitromethane will be contained in specifically designed vessels and only transported by those qualified to do so.

It is suggested that as a minimum two tests are conducted:

- 15kg of nitromethane.

- 0.5kg TNT

The TNT test allows confirmation the procedure was conducted correctly, as the TNT is the standard for TNT equivalence. DNV has previously collected data for 15kg charges of PE4 therefore this will not be repeated

The data will be analysed by comparing the peak pressure and specific impulse, to derive a comparison between nitromethane, PE4 and TNT.

Repeat tests will be conducted subject to resource availability. It is envisaged these tests will be completed by the end of December 2025, allowing sufficient time for data collection, analysis and report writing.

## 4.4 Risks & Limitations

Explosives are hazardous. All explosives handling will be performed in accordance with the established site Safe System of Work [11]. A Control of Substances Hazardous to Health (COSHH) assessment for nitromethane has been conducted [12] and relevant precautions will be followed.

The test will generate overpressure and noise. To ensure safety of personnel, DNV has established exclusions zones dependant on charge size which ensures no individual shall be exposed to overpressure greater than 15 mbar. Where charge sizes lie between values, the greater distance is enforced. This exclusion zone also extends upwards (air danger area), and permission to fire must be given by the Royal Air Force.

No fragmentation will be produced from the charge as it is not cased. To prevent fragmentation occurring from the pad, all charges are elevated to a minimum of 1m.

## 4.5 Ethical Issues

Environment impact of the tests has been given consideration. The quantity of detonation products produced will be minimal due to the low number of tests to be conducted. All products will disperse quickly as tests are conducted outdoors.

Noise impact will be considered prior to testing, with a noise evaluation forecast obtained from the met office. No test may produce noise above 135dB in populated areas. Permission to test will not be given by control if anticipated noise levels will be too high.

# 6. Resources & Planning

Following completion of the testing, a report will be produced detailing the TNT equivalence of nitromethane at small charge sizes. To do this, a preliminary list of resources is suggested in 6.1.1 and 6.1.2. A proposed timeline is provided in 6.2.

## 6.1 Resources Required

### 6.1.1 Physical Resources

- Nitromethane

- TNT

- Containment vessels

- Explosive pad time

- Non-electric detonators and shock cord

- Pressure gauges

### 6.1.2 Human Resources

- Firing Officer

- Researcher (the author)

- Potential need for site operatives

## 6.2 Gantt Chart

# References

| [1] | J. Lord-Garcia, “Nitromethane,” in Encyclopedia of Toxicology (Third Edition), Bethesda, Elsevier Inc, 2014, pp. 573-574. |
| --- | --- |
| [2] | G-Max Chemitech, “Material Safety Data Sheet - Nitromethane,” 2013. [Online]. Available: www.gmaxresearh.com. |
| [3] | R. Menikoff and M. S. Shaw, “Modeling detonation waves in nitromethane,” Combustion and Flame, vol. 158, no. 12, pp. 2549-2558, 2011. |
| [4] | P. F. M. a. D. Barker, “Blast Phenomena,” in Handbook for Blast-Resistant Design of Buildings, Hoboken, John Wiley & Sons, Inc, 2010, pp. 161-182. |
| [5] | C. N. Kingery and G. Bulmarsh, “Airblast parameters from TNT spherical air burst and hemispherical surface burst,” US Army Armament and Development Centre, Ballistic Researh Centre, 1984. |
| [6] | J. L. Maienschein, “Estimating Equivalency Of Explosives Through A Thermochemical Approach,” in 12th International Detonation Symposium, San Diego, 2002. |
| [7] | G. M. M. James, R. L. Bauer, E. M. Johnson and C. E. Johnson, “Experimental determination of TNT equivalence values for binary energetic materials,” Scientific Reports, vol. 15, 2025. |
| [8] | K. M. Jaansalu, C. Collet, E. L. Baker and V. van der Voort, “TNT Equivalency Testing for Energetic Materials,” in AIP Conference Proceedings, 2020. |
| [9] | W. Xiao, M. Andrae and N. Gebbeken, “Air blast TNT equivalence concept for blast-resistant design,” International Journal of Mechanical Sciences, vol. 185, 2020. |
| [10] | DNV Spadeadam Research and Development, “Test Procedure Number STN0110 Bare Explosive Charges on Pad C,” DNV, Spadeadam, 2025. |
| [11] | DNV Spadeadam Research and Development, Spadeadam Explosives and Ballistics Safety Handbook - OP-OEG-5-SPA-005, Spadeadam: DNV. |
| [12] | DNV Spadeadam Testing and Research, Nitromethane COSHH Assessment, Spadeadam: DNV, 2025. |

# Appendix 1

APPLICATION FOR ETHICAL APPROVAL

In order for research to result in benefit and minimise risk of harm, it must be conducted ethically.

The University follows the OECD Frascati manual definition of research activity: “creative work undertaken on a systematic basis in order to increase the stock of knowledge, including knowledge of man, culture and society, and the use of this stock of knowledge to devise new applications”. As such this covers activities undertaken by members of staff, postgraduate research students, and both taught postgraduate and undergraduate students working on dissertations/projects.

The individual undertaking the research activity is known as the “principal researcher”.

This form must be completed and approved prior to undertaking any research activity.

SECTION A: About You (Principal Researcher)

| 1 | Full Name: | Natalie Coplin |
| --- | --- | --- |
| 2 | Student Number: | 2113351 |
| 3 | Email address: | 2113351@student.uwtsd.ac.uk |
| 4 | Programme of Study: | Ordnance, munitions and explosives |
| 5 | Director of Studies/Supervisor: |  |

SECTION B:  Internal and External Ethical Guidance Materials

|  | Please list the core ethical guidance documents that have been referred to during the completion of this form (including any discipline-specific codes of research ethics, location-specific dodes of research ethics, and also any specific ethical guidance relating to the proposed methodology). Please tick to confirm that your research proposal adheres to these codes and guidelines. You may add rows to this table if needed. |  |
| --- | --- | --- |
| 1 | UWTSD Research Ethics & Integrity Code of Practice | ☒ |
| 2 | UWTSD Research Data Management Policy | ☒ |
| 3 |  | ☐ |

SECTION C: Details of Research Activity

| 1 | Indicative title: | Determination of TNT equivalence of Nitromethane in charge sizes of 15kg or less. |  |  |
| --- | --- | --- | --- | --- |
| 2 | Proposed start date: | August 2025 | Proposed end date: | End of Dec 2025 |
|  | Introduction to the Research (maximum 300 words in each section) Ensure that you write for a Non-Specialist Audience when outlining your response to the three points below: - Purpose of Research Activity - Proposed Research Question - Aims of Research Activity - Objectives of Research Activity Demonstrate, briefly, how Existing Research has informed the proposed activity and explain - What the research activity will add to the body of knowledge - How it addresses an area of importance. |  |  |  |
| 3 | Purpose of Research Activity To establish if a plastic mouldable explosive (PE4) can be replaced by the fuel nitromethane, in small charge sizes. To do so, when nitromethane is made to detonate, it will need to produce the same blast effect as PE4 for it to be useable in future tests. DNV Spadeadam have already performed this test on larger charge sizes, but now there is a requirement to see if the tests can be scaled down, providing justification to replace PE4 with nitromethane. The requirement has been generated due to poor lead times and rising costs of PE4. |  |  |  |
| 4 | Research Question What is the TNT equivalence of Nitromethane in charges of 15kg and less. |  |  |  |
| 5 | Aims of Research Activity To determine the TNT equivalence value of nitromethane and compare this value to that of PE4. |  |  |  |
| 6 | Objectives of Research Activity The objectives of this project are: - Conduct a literature review into the use of nitromethane as an explosive. - Perform a series of blast tests to collect pressure-time data. - Analyse data and calculate a TNT equivalence for nitromethane. - Produce an 8000-word report on the trial and data. - Document blast tests and results in a poster presentation |  |  |  |
|  | Proposed data collection methods (maximum 600 words) Provide a brief summary of all the methods that may be used in the research activity to collect data, making it clear what specific techniques may be used. If methods other than those listed in this section are deemed appropriate later, additional ethical approval for those methods will be needed. You do not need to justify the methods here, but should instead describe how you intend to collect the data necessary for you to complete your project. |  |  |  |
| 7 | Pressure data from nitromethane (and potentially TNT) detonations will be collected. This is done by attaching pressure gauges to data loggers and measuring the over pressure generated during a blast test. Video recordings of the detonations may take place using go-pro like cameras on the test site. There will no recordings of individuals. |  |  |  |

SECTION D: Scope of Research Activity

|  | Will the research activity include: | YES | NO |
| --- | --- | --- | --- |
| 1 | Use of a questionnaire or similar research instrument? | ☐ | ☒ |
| 2 | Use of interviews? | ☐ | ☒ |
| 3 | Use of focus groups? | ☐ | ☒ |
| 4 | Use of participant diaries? | ☐ | ☒ |
| 5 | Use of video or audio recording? | ☒ | ☐ |
| 6 | Use of computer-generated log files? | ☒ | ☐ |
| 7 | Participant observation with their knowledge? | ☐ | ☐ |
| 8 | Participant observation without their knowledge? | ☐ | ☒ |
| 9 | Access to personal or confidential information without the participants’ specific consent? | ☐ | ☒ |
| 10 | Administration of any questions, test stimuli, presentation that may be experienced as physically, mentally or emotionally harmful / offensive? | ☐ | ☒ |
| 11 | Performance of any acts which may cause embarrassment or affect self-esteem? | ☐ | ☒ |
| 12 | Investigation of participants involved in illegal activities? | ☐ | ☒ |
| 13 | Use of procedures that involve deception? | ☐ | ☒ |
| 14 | Administration of any substance, agent or placebo? | ☐ | ☒ |
| 15 | Working with live vertebrate animals? | ☐ | ☒ |
| 16 | Procedures that may have a negative impact on the environment? | ☒ | ☐ |
| 17 | Other primary data collection methods. Please indicate the type of data collection method(s) below. | ☐ | ☒ |
|  | Details of any other primary data collection method: |  |  |

If you have ticked NO to every question then the research activity is (ethically) low risk and you may skip section E and continue to section F.

If YES to any question, then no research activity should be undertaken until full ethical approval has been obtained.

SECTION E: Intended Participants

|  | Who are the intended participants: | YES | NO |
| --- | --- | --- | --- |
| 1 | Students or staff at the University? | ☐ | ☒ |
| 2 | Adults (over the age of 18 and competent to give consent)? | ☐ | ☒ |
| 3 | Vulnerable adults? | ☐ | ☒ |
| 4 | Children and Young People under the age of 18? (Consent from Parent, Carer or Guardian will be required) | ☐ | ☒ |
| 5 | Prisoners? | ☐ | ☒ |
| 6 | Young offenders? | ☐ | ☒ |
| 7 | Those who could be considered to have a particularly dependent relationship with the investigator or a gatekeeper? | ☐ | ☒ |
| 8 | People engaged in illegal activities? | ☐ | ☒ |
| 9 | Others. Please indicate the participants below, and specifically any group who may be unable to give consent. | ☐ | ☒ |
|  | Details of any other participant groups: |  |  |

|  | Participant numbers and source Provide an estimate of the expected number of participants. How will you identify participants and how will they be recruited? |  |
| --- | --- | --- |
| 10 | How many participants are expected? | N/A |
| 11 | Who will the participants be? | N/A |
| 12 | How will you identify the participants? | N/A |

|  | Information for participants: | YES | NO | N/A |
| --- | --- | --- | --- | --- |
| 13 | Will you describe the main research procedures to participants in advance, so that they are informed about what to expect? | ☐ | ☐ | ☒ |
| 14 | Will you tell participants that their participation is voluntary? | ☐ | ☐ | ☒ |
| 15 | Will you obtain written consent for participation? | ☐ | ☐ | ☒ |
| 16 | Will you explain to participants that refusal to participate in the research will not affect their treatment or education (if relevant)? | ☐ | ☐ | ☒ |
| 17 | If the research is observational, will you ask participants for their consent to being observed? | ☐ | ☐ | ☒ |
| 18 | Will you tell participants that they may withdraw from the research at any time and for any reason? | ☐ | ☐ | ☒ |
| 19 | With questionnaires, will you give participants the option of omitting questions they do not want to answer? | ☐ | ☐ | ☒ |
| 20 | Will you tell participants that their data will be treated with full confidentiality and that, if published, it will not be identifiable as theirs? | ☐ | ☐ | ☒ |
| 21 | Will you debrief participants at the end of their participation, in a way appropriate to the type of research undertaken? | ☐ | ☐ | ☒ |
| 22 | If NO to any of above questions, please give an explanation |  |  |  |
|  | You should be able to tick YES for all of these questions. If not, then explain why not in this box. |  |  |  |

|  | Information for participants: | YES | NO | N/A |
| --- | --- | --- | --- | --- |
| 24 | Will participants be paid? | ☐ | ☐ | ☒ |
| 25 | Is specialist electrical or other equipment to be used with participants? | ☐ | ☐ | ☒ |
| 26 | Are there any financial or other interests to the investigator or University arising from this study? | ☐ | ☐ | ☒ |
| 27 | Will the research activity involve deliberately misleading participants in any way, or the partial or full concealment of the specific study aims? | ☐ | ☐ | ☒ |
| 28 | If YES to any question, please provide full details |  |  |  |
|  | You should be able to tick NO for most of these questions. For any cases that you have ticked YES then provide details in this box. If you are using cameras/voice recorders to record interviews then please state that in this box. |  |  |  |

SECTION F: Anticipated Risks

|  | Outline any anticipated risks that may adversely affect any of the participants, the researchers and/or the University, and the steps that will be taken to address them. |  |
| --- | --- | --- |
| 1 | Risks to participants For example: sector-specific health & safety, emotional distress, financial disclosure, physical harm, transfer of personal data, sensitive organisational information. If you have identified in section D that there are no participants then enter N/A and go skip to question 3. |  |
|  | Risk to participants: N/A | How you will mitigate the risk to participants: N/A |
| 2 | If research activity may include sensitive, embarrassing or upsetting topics (e.g. sexual activity, drug use) or issues likely to disclose information requiring further action (e.g. criminal activity), give details of the procedures to deal with these issues, including any support/advice (e.g. helpline numbers) to be offered to participants. Note that where applicable, consent procedures should make it clear that if something potentially or actually illegal is discovered in the course of a project, it may need to be disclosed to the proper authorities |  |
|  | N/A |  |
| 3 | Risks to the investigator For example: personal health & safety, physical harm, emotional distress, risk of accusation of harm/impropriety, conflict of interest |  |
|  | Risk to the investigator: Contact with nitromethane (skin, eyes, inhalation, ingestion). Blast and fire risk. | How you will mitigate the risk to the investigator: A COSHH assessment for nitromethane been completed. Protective measures are outlined in detail in there and will be followed: - Wear PPE, including chemically resistance gloves, full arm/leg covering, safety glasses. - Use only in well-ventilated areas. - Do not transport with explosives. - Strict adherence to site exclusion zones for 15kg blasts. - Strict adherence to the blast testing protocol. - Only those trained in test set up will be allowed to handle material. - Permission to fire must be obtain from the control room before testing can occur. This enables control room to ensure the exclusion zone is clear of all personnel. - No lone working, test only between 9-5. |
| 4 | University/institutional risks For example: adverse publicity, financial loss, data protection |  |
|  | Risk to the University: Reputational damage due to student injury (this box should expand as you type) | How you will mitigate the risk to the University: Workplace test procedures will be followed, including exclusion zones and control room permission before any test takes place. No lone working will take place. Testing will only be conducted between 9-5. |
| 5 | Environmental risks For example: accidental spillage of pollutants, damage to local ecosystems |  |
|  | Risk to the environment: Noise impact to the area local to the test site. Detonation products. Accidental spillage. | How you will mitigate the risk to environment: The student’s workplace has a uses a noise forecast technique based on the weather. Anticipated noise pollution will be checked prior to any testing and if above the limit, no testing will take place until such time that the noise will not be a nuisance. Any detonation products will dissipate quickly and are not considered to be an environmental risk. Only small quantities will be used and minimal testing will be performed. Nitromethane is stored in a fully bunded site. All staff who may handle nitromethane are trained to deal with any spills. |

SECTION G: Feedback, Consent and Confidentiality

If you have identified in section D that there are no participants, then enter skip this section and continue to section H.

| 1 | Feedback What de-briefing and feedback will be provided to participants, how will this be done and when? |
| --- | --- |
| 2 | Informed consent Describe the arrangements to inform potential participants, before providing consent, of what is involved in participating. Describe the arrangements for participants to provide full consent before data collection begins. If gaining consent in this way is inappropriate, explain how consent will be obtained and recorded in accordance with prevailing data protection legislation. |
| 3 | Confidentiality / Anonymity Set out how anonymity of participants and confidentiality will be ensured in any outputs. If anonymity is not being offered, explain why this is the case. |

SECTION H: Data Protection and Storage

|  | Does the research activity involve personal data (as defined by the General Data Protection Regulation 2016 “GDPR” and the Data Protection Act 2018 “DPA”)? | YES | NO |
| --- | --- | --- | --- |
| 1 | “Personal data” means any information relating to an identified or identifiable natural person (‘data subject’). An identifiable natural person is one who can be identified, directly or indirectly, in particular by reference to an identifier such as a name, an identification number, location data, an online identifier or to one or more factors specific to the physical, physiological, genetic, mental, economic, cultural or social identity of that natural person. Any video or audio recordings of participants is considered to be personal data. | ☐ | No |
|  | If YES, provide a description of the data and explain why this data needs to be collected: |  |  |
| 2 | This includes audio/video data of participants, but can also include IP addresses and usernames. Names, addresses and emails also count, as do consent forms. |  |  |
|  | Does it involve special category data (as defined by the GDPR)? | YES | NO |
| 3 | “Special category data” means sensitive personal data consisting of information as to the data subjects’ – (a) racial or ethnic origin, (b) political opinions, (c ) religious beliefs or other beliefs of a similar nature, (d) membership of a trade union (within the meaning of the Trade Union and Labour Relations (Consolidation) Act 1992), (e) physical or mental health or condition, (f) sexual life, (g) genetics, (h) biometric data (as used for ID purposes), | ☐ | No |
|  | If YES, provide a description of the special category data and explain why this data needs to be collected: |  |  |
| 4 | What counts as ‘sensitive’ will differ between cultures. Any information on behaviour that is not in accordance with cultural norms would count as sensitive personal data. |  |  |

|  | Will data from the research activity (collected data, drafts of the thesis, or materials for publication) be stored in any of the following ways? | YES | NO |
| --- | --- | --- | --- |
| 5 | Manual files (i.e. in paper form)? | ☐ | ☒ |
| 6 | University computers? | ☐ | ☒ |
| 7 | Private company computers? | ☐ | ☒ |
| 8 | Home or other personal computers? | ☒ | ☐ |
| 9 | Laptop computers/ CDs/ Portable disk-drives/ memory sticks? | ☒ | ☐ |
| 10 | “Cloud” storage or websites? | ☐ | ☒ |
| 11 | Other – specify: | ☐ | ☒ |
| 12 | For all stored data, explain the measures in place to ensure the security of the data collected, data confidentiality, including details of backup procedures, password protection, encryption, anonymisation and pseudonymisation: |  |  |
|  | If possible, save your data on computers that are secure and regularly backed up. Many cloud services only provide GDPR-compliant storage for business customers. An example of suitable text is given below. All test data will be kept on a password protected network at the student’s workplace which will not be shared with anyone who does not require access. There are no confidentiality issues. |  |  |

|  | Data Protection |  |  |
| --- | --- | --- | --- |
|  | Will the research activity involve any of the following activities: | YES | NO |
| 13 | Electronic transfer of data in any form? | ☒ | ☐ |
| 14 | Sharing of data with others at the University outside of the immediate research team? | ☐ | ☒ |
| 15 | Sharing of data with other organisations? | ☐ | ☒ |
| 16 | Export of data outside the UK or importing of data from outside the UK? | ☐ | ☒ |
| 17 | Use of personal addresses, postcodes, faxes, emails or telephone numbers? | ☐ | ☒ |
| 18 | Publication of data that might allow identification of individuals? | ☐ | ☒ |
| 19 | If YES to any question, please provide full details, explaining how this will be conducted in accordance with the GDPR and Data Protection Act (2018) (and/or any international equivalent): |  |  |
|  | No personal data will be collected or stored. Experimental data collected will be shared with my workplace. (this box should expand as you type) |  |  |
| 20 | List all who will have access to the data generated by the research activity: |  |  |
|  | Researcher, university supervisor, workplace team, external examiner, second marker, endpoint assessment team. (this box should expand as you type) |  |  |
| 21 | List who will have control of, and act as custodian(s) for, data generated by the research activity: |  |  |
|  | Principal researcher. (this box should expand as you type) |  |  |
| 22 | Give details of data storage arrangements, including security measures in place to protect the data, where data will be stored, how long for, and in what form. |  |  |
|  | N/A (this box should expand as you type) |  |  |
| 22 | Confirm that you have read the UWTSD guidance on data management (see https://www.uwtsd.ac.uk/library/research-data-management/) | ☒ |  |
| 23 | Confirm that you are aware that you need to keep all data until after your research has completed or the end of your funding | ☒ |  |

SECTION I: Declaration

|  | The information which I have provided is correct and complete to the best of my knowledge. I have attempted to identify any risks and issues related to the research activity and acknowledge my obligations and the rights of the participants. In submitting this application I hereby confirm that I undertake to ensure that the above named research activity will meet the University’s Research Ethics and Integrity Code of Practice which is published on the website: https://www.uwtsd.ac.uk/research/research-ethics/ |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| 1 | Signature of applicant: | Natalie Coplin | Date: 16/06/2025 |  |  |
| 2 |  | Director of Studies/Supervisor: |  |  | Date: |
| 3 |  | Signature: |  |  |  |

FOR INTERNAL USE ONLY:

|  | Ethical approval given |  |  |
| --- | --- | --- | --- |
| 1 | Signature of assessor: |  | Date: |
| 2 | Name: |  |  |
| 3 | Role: |  |  |