[bookmark: _GoBack]EXERCISE 5
LINE OF BALANCE
We have to carry on with the development of an urban plan including 20 detached houses. The activities programmed for these houses (rates per detached house) are as follows:
	Num
	Activity
	Duration per detached house

	1
	Excavation
	2 days

	2
	Foundation
	5 days

	3
	Block walls
	5 days

	4
	Roof frame
	5 days

	5
	Roof tiles
	5 days

	6
	Windows and exterior doors
	2 days

	7
	Plumbing and electrical wiring
	3 days

	8
	Insulation and dry wall
	3 days

	9
	Painting
	2 days

	10
	Tiles, carpet and finishing
	5 days



Draw a line-of-balance diagram to calculate the earliest deadline to finish these works.
