## Sheet1
Event: Swansea Triathlon |  |  |  | Date of event: 31st May 2020
Locations: Prince of Wales Dock - Castle Square |  |  |  | Asssessed by: Sasha White
Date of review: 6th April 2020
What are the hazards? | Who is at risk? | Worst outcome (1-5) | Likelihood (1-5) | Level of risk (AxB) | Action taken | New level of risk | Who's responsible
Weather- Rain could create slipping hazards | Everyone | 2 | 2 | 4 | If raining, more use of non slip mats should be put into effect, especially when getting out of water | 3 | Sasha White
Stage electrics could be made fire hazards by rain | MC, Staff whom install the electrics | 4 | 2 | 8 | Make sure that any electrics in as covered as possible/ not in the weather. | 2 | Sasha White
Crowd management and flow: Spectators being clear of course | Spectators and athletes | 3 | 2 | 6 | Make sure that prior to any waves beginning spectators are behind barriers. Start waves later then the event to ensure that spectators coming to the event. | 2 | Staff at the barriers
Stewards falling into the water when going to monitor swimmers | Stewards | 4 | 4 | 16 | Make sure when selecting stewards they are able to swim. In addition, have lifeguards on stand by for stewards. Have a boat take them to the cannoes to lower risk of them turning over. | 3 | Sasha White and stewards
Ramps getting in and out of water being slippy between waves | Athletes | 5 | 4 | 20 | Invest in non slip mats. Make sure between waves and athletes to try and keep the area as dry as possible. Swap mats during waves. | 3 | Sasha White
Swimmers hitting buoys whilst swimming | Athletes | 3 | 2 | 6 | Bright coloured buoys. First aiders in water. Make buoys out of softer material. Provide goggles for racers. | 1 | Sasha White
Samba band performing on stage in the water: Could get slippery causing them to fall in | Samba band members | 3 | 2 | 6 | Making sure to use non slip mats for the staging. Having a life guard nearby incase they fall in | 1 | Sasha White
Transition areas being clear for the athletes between waves | Athletes | 5 | 2 | 10 | Ensuring that the next waves start when majority of athletes from prior wave have finished. Barriers for spetators. Communicating to staff when wave is coming in. Banning people from standing on course. | 3 | Sasha White
Running with no shoes on bare road could lead to injuries on feet. | Athletes | 5 | 4 | 20 | Walk the course before and between waves to ensure there are no sharp objects/hazards. Cleaning road. Ensuring road is closed | 3 | Sasha White
Disposing of layers between waves such as wetsuits, could slip on wet clothes | Athletes | 4 | 2 | 8 | Separate transition areas between activities. Having a specified area for wet clothes and trainers | 3 | Sasha White
When getting bicycles, lots of people in one area at one time | Athletes | 3 | 2 | 6 | Separate waves . Ensuring that bicycles are spaced enough so people are seperated more. Also separate areas between each activity will space participants | 2 | Cleaning team
Cycling, road should be clear of any tripping hazards | Athletes | 4 | 2 | 8 | Road closures. Making sure someone walks the course prior to the first wave staring and inbetween. Clearing of road prior to start. Minimising rubbish by providing bins. Not allowing anyone on the course inbetween, except cleaners | 2 | Sasha White
Speeds on bicycles, participants can fall | Athletes | 3 | 1 | 3 | Put a speed limit on the cyclists. Make sure road is clear. Minimise the amout of turns | 1 | Sasha White
Lots of bicycles in one area, which are expensive. Theft | Athletes | 4 | 2 | 8 | Have bicycles locked away. Have security guard the bikes. Have a way of the particpants having to prove they own the bicycle, with numbers and bands to ensure they only take their own bike | 1 | Sasha White
Terrorism | Everyone | 5 | 3 | 15 | Make sure there are evacuation plans in place. Have security on alert. Inform all spectators/participants of a hotline where they can report anything. Checking of bags. Have police on site | 2 | Sasha White and security
All staff should know when waves are happening to ensure they are on alert for any wrong happenings | Staff and athletes | 3 | 1 | 3 | Have a staff breifing. Inform all the staff of when each wave is happening/when first and last athletes from each wave have began and finished. During the day have open lines of communication between staff and organisers. | 1 | All staff and organisers
Risk of injury could result in lawsuit | Organisers | 2 | 1 | 2 | Sign non disclosures. Ensure that if an injury does happen there are first aiders whom are able to treat injuries quickly. Also have ambulance on site. | 1 | Sasha White
Road closures not being honoured by public | Athletes | 2 | 1 | 2 | Ensure that council is contacted ASAP. Ensure signage is up. Have people monitor beginning and end of roads. Barriers for roads | 1 | Sasha White
Food and drink, ensuring reach the health and safety standards | Everyone | 4 | 2 | 8 | Ensure food provided on site reaches the food hygiene standards. Alternatively guide attendees to restuarants in local area which comply with stardards | 1 | Sasha White