| Why | Who | Where | How | When | Cost |
| --- | --- | --- | --- | --- | --- |
| Recommendation 1: |  |  |  |  |  |
| Support for prior consideration (PC) applicants – develop guidance notes and direct assistance on how best to complete an application form and interview preparation to achieve success. This will particularly support those long-standing employees who may not have been part of a recruitment and selection process. | Prior consideration applicants / Training and Development Team (T&D)/ HR Officers / Talent Management Team. | Guidance could be made available via NPT internal SharePoint page or discussed as part of any 1:1 redeployment process meetings held with HR Officers. | Sharing guidance notes as well as incorporating in 1:1 redeployment meetings with individuals. Explore if training of a similar nature is currently offered by T&D. | December 2024 – Budget discussions are due to take place in October and it is anticipated that there will be further redundancies in the next financial year (April 2025). | Utilising HR Officers current time resource spent in 1:1 redeployment meetings with prior consideration applicants. Training and Development Support Officer time resource to support with devising guidance notes. Digital Services – time resource to publish guidance notes on NPT SharePoint. HR Talent Management Team – time resource to support with retention. |
| Recommendation 2: |  |  |  |  |  |
| Re-establishment of the Redeployment Action Group. Service specific officer’s to review prior consideration register and current vacancies before advertising. | Heads of Service / HR representative | Group can meet virtually or in person. | Fortnightly meetings in the first instance, to be reviewed depending on continued numbers of PC applicants/vacancies. | As soon as possible. | Time resource – in-direct cost of officer’s time to attend meeting. |
| Recommendation 3: |  |  |  |  |  |
| Further research on NPTC’s current redeployment process, in particularly, on manager’s roles and responsibilities/understanding of process. To support any recommendations for improvement. | HR Officer / identifying managers who regularly recruit/support PC applicants. | Focus groups to be held in person or virtually. | Prepare questions that will support the researcher in gaining insight of their roles in the process. | As soon as reasonably possible. | Time resource – HR Officer – policy review incorporated into current job description. Time resource – in-direct cost of manager’s time to attend focus groups. |