Research Project Timeline - 
The effect of AI on reducing officer time in local government
	Date
	Anticipated tasks

	September 2026
	Refine title, aims, objectives and research questions. Discuss draft with supervisor.
Submit Research proposal for approval.

	October 2026
	Prepare and submit Ethics form for approval. Discuss draft with supervisor.

	September - November 2026
	Produce literature review – Submit to supervisor end of November 2026.

	October 2026
	Finalise the methodology and write up for dissertation – Submit to supervisor end of October 2026.

	November 2026
	Produce and design research tools.

	December 2026 
	Identify final audiences for research. Discuss tools and audiences with supervisor.


	February 2027
	Timetable interviews and questionnaires for conclusion.  

	March 2027
	Complete data collection.

	April 2027
	Complete data analysis – Discuss with supervisor after completion.

	May 2027
	Compare findings with the literature.  

	June 2027
	Identify any further areas for research to finalise outcomes – Discuss with supervisor before final write up.

	July 2027
	Write up findings.

	August 2027
	Complete first draft, conclusions and final recommendations.  Produce strategy to reflect the findings – submit draft to supervisor.
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				Refine title, aims, objectives and research questions		9		1

				Submit Research proposal for approval.		9		1

				Prepare and submit Ethics form for approval.		10		1

				Produce literature review.		9		2

				Finalise  methodology and write up for dissertation.		10		1

				Produce and design research tools.		11		1

				Identify final audiences for research. 		12		2

				Timetable interviews and questionnaires for conclusion.  		2		1

				Complete data collection. 		3		1

				Complete data analysis.		4		1

				Compare findings with the literature.  		5		2

				Identify any further areas for research to finalise outcomes.		6		1

				Write up findings.		7		1

				Complete first draft, conclusions and final recommendations.  Produce strategy to reflect the findings.		8		1
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