# Research Project Timeline -

The effect of AI on reducing officer time in local government

| Date | Anticipated tasks |
| --- | --- |
| September 2026 | Refine title, aims, objectives and research questions. Discuss draft with supervisor. Submit Research proposal for approval. |
| October 2026 | Prepare and submit Ethics form for approval. Discuss draft with supervisor. |
| September - November 2026 | Produce literature review – Submit to supervisor end of November 2026. |
| October 2026 | Finalise the methodology and write up for dissertation – Submit to supervisor end of October 2026. |
| November 2026 | Produce and design research tools. |
| December 2026 | Identify final audiences for research. Discuss tools and audiences with supervisor. |
| February 2027 | Timetable interviews and questionnaires for conclusion. |
| March 2027 | Complete data collection. |
| April 2027 | Complete data analysis – Discuss with supervisor after completion. |
| May 2027 | Compare findings with the literature. |
| June 2027 | Identify any further areas for research to finalise outcomes – Discuss with supervisor before final write up. |
| July 2027 | Write up findings. |
| August 2027 | Complete first draft, conclusions and final recommendations. Produce strategy to reflect the findings – submit draft to supervisor. |

# Gantt Chart