Planning an International Meeting:

Charity fundraiser diner Report.

Student: Mukhlishah Raja (2020782)

Module: International meetings Management for the Hotel Industry (BMIH6007).

Lecturer: Kathryn Flynn

Contents page:

Page:

3.		Introduction
3.		Events Cycle

4.		Aims and objective of event

4.		Events operation

5.		Itinerary

5.		Evaluation

6.		Summary

7.		Reference

Introduction

This report is a plan of a mice charity dinner event. The plan will look at events planning, Industry trends, Aims and objective of event, events operation.

MICE stand for:

- Meetings,

- Incentives,

- Conferences

- Exhibitions/Events

MICE can also be called Business Tourism or Business Events (Evens, 2015).

According to Mice magazine (2023) the mentality of a mice event should be an innovative one, this is essential to capture the attention of your audience/guests in order to make the event as successful as possible.

The Charity being hosted for in this MICE event is The Angelou Centre which is a charity that helps women escaping domestic violence and sexual abuse, the charity has been empowering women specifically of ethnic backgrounds for over 30 years and relies heavily on both government funding as well as donations raised through charity events (Angelou Centre, 2023).

The goal is to raise money for the above charity through a charity dinner event alongside a comedy night of laughter. The event will be advertised through social media and e-mail lists to cut costs and attract new sponsors as well as re-invite current sponsors to display how donations can positively impact survivors and change lives.

The event will be held at the Grand Hotel Gosforth Park, formally a Mariott Hotel it is now a Britannia Hotel; the Hotel is a beautiful 4-star Hotel with plenty of parking facilities (Britannia Hotel, 2023). According to Adams, et al (2022) parking facilities are necessary when seeking events venues as they can put people off such events, specifically evening events.

Events Cycle

The Event cycle (Lück, 2013) consists of five stages from the date the event is announced to the event day, these stages are important as Event Cycle helps implement the process, these stages are:

- Promulgate.

- Presale.

- Sell.

- Maintain.

- Closure.

Using the Above Cycle Promotions and presales will be carried out digitally through social media such as Facebook and event listing sites, e-mail lists will be used to contact and invite pre-existing sponsors and supporters. Tickets will both be sold online and in person through supporting businesses. Communication will be maintained through e-mail and mobile contact till the day of the event when a follow-up will be made to announce the amount made followed by a courtesy thank you.

Aims and objective of event

The Aim is to raise money for the Angelou Centre Based in Newcastle Upon Tyne. This will be adhered to through a dinner and comedy evening. The Merah group (2023) is one of the events companies the Angelou Centre uses regularly for fundraising. The Merah group often experiments with new venues and has good relationships with many hotels to keep costs low for charity events. According to Venue scanner (2023) the racecourse suite can hold up to 120 guests and costs £1200, this would be an ideal suite as it can fit a lot of people and the venue is nice, there is plenty of parking to facilitate the event.

The aim is to raise money for the Angelou Centre, this will be done through a charity event however the objective is to build brand awareness through these initiatives, acquire new reoccurring sponsors and doners, increase average monthly donation and increase awareness (Durbin, 2022). As mentioned above, charities rely heavily on both government funding and donations however many charities have had major cuts in government grants and funding and are having to find creative ways to run their organizations; leaning stronger towards sponsors and doners (Little lives, 2023); this make events such a charity fundraising event more important for both awareness and funds required in order for great charities to continue their work.

The target Audience will be previous sponsors, local business owners and any adults who like to have a laugh at a charity events, a guilt free evening for a worthy cause.

Events operation

The Event will be held at the Grand Hotel Gosforth Park and is a 4-star prestigious Venue occurring the following calculated costs:

Budget estimates:

- The racecourse suite (capacity: 120 people) = £1,200

- Simple Meal by Newcastle Vujon Biryani is £10 a head= £1,200 (V insights, 2023)

- Entertainment hired comedian (Local comedians and entertainers)- £200-£1000 (pop top, 2023)

- Marketing tools- £0-£200

- Extra splendours: £0-£200

- Total: £3,800 (Max £32 per head)

- The event will cost attendees between £50-£100 per seat: 120 seats: 20 seats will be VIP seats which will cost £100
80 seats will be sold at £50 and 20 seats will be used for marketing. This will total to £10k (£6.2k profit)

- There will also be fundraising at the end so the end should make a lot more then 10k, Fundraising will have a raffle through donations and if donations are short then money from the £200 extra will be used to buy prizes.

According to Brenner (2023) The VIP seats to create Hype specially alongside videos and digital marketing is necessary measure for a successful event. Neus (2020) suggests using digital marketing for economic reasons specially for smaller budgets and charities, although digital marketing can be cost effective it can also be costly depending on which means is used and how much is paid to create traffic, this will not be required as the event is not big.

According to Lauth (2023) Thursday is the best day to have a charity event as it is statistically proven to have better results. So, this plan will recommend keeping the event on a Thursday. The event was planned to be on the 4th of July 2024 however according to Paskaleva (2024) it is better to avoid major dates such as election dates, therefore due to elections the suggested date has been changed to 11th July 2024.

Itinerary

Schedule: Thursday 11th July 2024.

- 5pm Doors open to start: Drinks and snacks will be available to early guests.

- 5.30pm start warm up to comedy entertainment, light chat, and seating guests.

- 6pm- starters handed out (comedy in the background and ice breakers)

- 6.30pm- meals served with full on comedy

- 7pm comedian continues whilst everyone eats

- 7.30pm break to clear up and set up charity fundraiser which will continue until 8-8.30pm

- 9pm start wrapping up and finishing event.

This may need re-adjusting as this is a suggested itinerary for the 11th July 2024 and will have to be confirmed by the Hotel regarding availability.

Evaluation

A plan of a mice charity dinner event. The plan will look at events planning, Industry trends, Aims and objective of event, events operation.

MICE stand for:

- Meetings,

- Incentives,

- Conferences

- Exhibitions/Events

According to Mice magazine (2023) the mentality of a mice event should be a innovative one, this is essential to capture the attention of your guests and make the event successful.

The Charity being hosted for is the Angelou Centre which is a charity that helps women escaping domestic violence and sexual abuse, the charity has been empowering women specifically if ethnic backgrounds for over 30 years. The goal is to raise money for the above charity through a charity dinner event alongside a comedy night of laughter.

The event will be held at the Grand Hotel Gosforth Park, preferably on a Thursday. An estimated total of £3,800 (£32 per head) will be spent to acquire over 10k

SWOT (Harvard Business School Press, 2005):

- Strength: Easy target market for likeable charitable cause, Angelou Centre will organize guests with their contacts list via e-mail and other Digital marketing means (i.e. Facebook ads). Prestigious area alongside plentiful parking facilities.

- Weakness: Vis in the pricey side for a charity cause and can be delivered at a more accessible and cheaper venue.

- Opportunities: attract elite people due to venue and parking facilities.

- Threats: adjusting from laughter to fundraising can be tricky at times.

Pestle Analysis (Baron & Armstrong, 2007):

- Political: the event may be affected due to the local elections a week before the event

- Economical: the funding is currently affected through organizations around the UK due to governmental cutbacks

- Social: The charity works towards breaking taboo and social norms within ethnic communities where woman can be treated badly

- Technological: the use of social media

- Legal: Educating woman on their rights int he UK

- Environmental: Parking facilities at event.

The Angelou Centre is a Culturally sensitive organization as they deal diverse range of woman from many backgrounds, from domestic abuse due to cultural belonging to religious belongings, hence it is extremely important to keep this in mind when the event is organized as the right comedian/ entertainer is hired to keep these victims in mind. It is important to be very mindful as many of the sponsors of this charity are previous victims who have been helped, prospered, and returned to return the Favour they once received.

The Hotel has been carefully selected due to location and accessibility; it is in a quiet location with plenty of parking in a prestigious neighborhood which should attract the right sponsors enabling a successful event.

Summary

The aim is to raise money for the Angelou Centre on a Thursday; the suggested date is 11th July 2024. This will be done through a charity event. However, the objective is to build brand awareness through these initiatives, acquire new reoccurring sponsors and doners, increase average monthly donations and increase awareness. Charities rely heavily on both government funding and donations however many charities have had major cuts in government grants and funding and are having to find creative ways to run their organizations; leaning stronger towards sponsors and doners, this makes events such as charity fundraising events more important for both awareness and fundraising

The target Audience will be previous sponsors, local business owners and any adults who like to have a laugh at a charity events, a guilt free evening for a worthy cause.

The chosen Venue for this event is the Grand Hotel Gosforth Park which was previously a Marriotts Hotel but is now owned by Britannia Hotel; the Hotel is a beautiful 4-star Hotel with plenty of parking facilities

This Comedy and awareness evening is projected spend around £3,800 in total with venue, entertainment and food, and bring in an excess of £10,000 through donations and new sponsor sign-ups.

Reference:

Adams, D. et al (2022). Developing Hospitality Properties and Facilities. (2022). (n.p.): Taylor & Francis.

Angelou Centre. (2023). Home. Available at: https://angelou-centre.org.uk/ (Accessed: 20 May, 2023).

Baron, A. And Armstrong, M. (2007). Human capital management. London: Kogan Page

Britannia Hotel. (2023). The Grand Hotel Gosforth Park. Available at: https://www.britanniahotels.com/hotels/grand-hotel-gosforth-park-newcastle#:~:text=Formerly%20a%20Marriott%20hotel%2C%20the,assortment%20of%20first%2Drate%20amenities. (Accessed: 20 May, 2023)

Brenner, M. (2023). 11 Ways to Generate Pre-Event Hype with Content Marketing

https://marketinginsidergroup.com/content-marketing/8-ways-to-generate-pre-event-hype-with-content-marketing/ (Accessed: 20 May, 2023)

Durbin, H. (2022). 6 Measurable Fundraising Goals To Consider for Your Nonprofit. Available at: https://www.classy.org/blog/6-fundraising-goals-that-your-nonprofit-shouldnt-ignore/#:~:text=While%20fundraising%20campaigns%20are%20primarily,raise%20brand%20awareness%20as%20well. (Accessed: 20 May, 2023)

Evans, N. (2015). Strategic Management for Tourism, Hospitality and Events. (n.p.): Taylor & Francis.

Neus, F. (2020). Event Marketing in the Context of Higher Education Marketing and Digital Environments. Germany: SpringerGabler.

Lauth, I. (2023). THURSDAY IS THE NEW SATURDAY: 3 REASONS TO PLAN YOUR EVENT ON A WEEKDAY. Available at: https://blog.winspireme.com/3-reasons-to-plan-your-event-on-a-weekday (Accessed: 20 May, 2023)

Little Lives. (2023). The UK government’s support to the public sector and charities. Available at: https://www.littlelives.org.uk/blog/uk-government-charities-how-is-it-working/ (Accessed: 20 May 2024)

Lück, M. (2013). Events, Society and Sustainability: Critical and Contemporary Approaches. United Kingdom, Routledge.

Mice magazine. (2023). OUR SELECTION OF MICE EVENTS. Available at: https://www.micemag.com/mice-events/ Accessed: 2 May, 2023)

Paskaleva, V. (2024). Column: When NOT to Schedule Your Event? Available at: https://www.eventplanner.net/news/6780_column-when-not-to-schedule-your-event.html (Accessed: 20 May 2023).

Pop top. (2023). Hire comedians in Newcastle. Available at: https://www.poptop.uk.com/newcastle-upon-tyne/suppliers/comedian-or-comedy-act/ (Accessed: 20 May, 2023)

The Merah group (2023). The Angelou Centre. Available at: https://www.themerahgroup.com/angeloucentre (Accessed: 20 May, 2023)

Venue scanner. (2023). The grand Hotel Gosforth Park. Available at: https://www.venuescanner.com/north-brunton/grand-hotel-gosforth-park-newcastle/the-racecourse-suite (Accessed: 20 May, 2023)

V insights. (2023). Vujon Biryani. Available at: https://vinsights.co.uk/Business/607766 (Accessed: 20 May, 2023)