02.10.2025

Independent Project

Research Proposal

Jamie Richards (0852036)

ACCA6020 – Independent project

# Contents

- Introduction									Page 3

- Background to the Proposal							Page 3

- Problem statement								Page 5

- Aim & Objective									Page 5

- Methodology									Page 6

5.1 – Methods									Page 6

5.2 – Materials									Page 6

- Project Plan									Page 7

- References									Page 9

# 1. Introduction

Autism Spectrum Disorder (ASD) is characterised by an individual’s differences in communication, cognitive processing and emotion, as stated on the national autistic society website “More than one in 100 people are autistic and there are at least 700,000 autistic adults and children in the UK.” [1]

In a recent conference paper titled Identification of Autism Spectrum Disorder (ASD) in Adults through Various Machine Learning Algorithms [2] written by S. Yuvaraj, S. Sugavanaesh, C. Tharun Kumar, G. Saran and R. Subha suggests Autism as a development disorder which generally appear in children around two years old.

Gaming in recent years has drastically expanded in people’s lives, gaming provides more than just entertainment.

Figure 1 to the left taken from the game quitters website, illustrates the amount of individuals in the UK who play video games and on average how long for. [3]

With figures like these there is no surprise that there is a growing accessibility of the use of games to help support the development of individuals with ASD.

The importance of this project will fall into the potential of improving the quality of life and development for individuals with autism, more so on a personal level the motivation for this project branches on to the desire to further the research and advancements in aid for people with ASD using game-based interventions.

# 2. Background to the Proposal

With ASD, traditional approaches often face limitations in engagement which has led to an increased interest in games-based interventions.

Serious games are digital or physical games designed for the purpose beyond entertainment, for instance education or training. Serious games unlike commercial games intentionally integrate learning or development objectives within the environment so it can achieve real world outcomes. [4]

In conference paper [5] where the usability of serious games for health was presented, it was concluded that a serious game had more satisfaction than an entertainment game, even though only a small number of volunteers participated.

People with ASD often experience difficulties in social interactions such as challenges in understanding the social parameters and even forming relationships. Game based interventions have shown promising advances in addressing these challenges by providing an organised environment where the user can practise different scenarios.

In a journal by O’Keeffe and McNally it was identified that in nine studies, which explored play-based interventions targeting social communication skills in an educational environment. It was suggested that the game-based interventions were effective in improving the social outcomes. [6]

However, a conference paper by Ian Dunwell, Kate Torrens, Samantha Clarke and Stella Doukianou, titled Game-based lifestyle interventions for adolescents: An evidence-based approach found such interventions required more time to produce viable results. [7]

Cognitive deficiencies such as attention and memory are common with individuals with ASD and game-based interventions offer an interactive platform which can target these cognitive needs. A journal article on science direct, written by Suzanne Derks, Agnes M. Willemen and Paula S. Sterkenburg reported that a serious game was associated with improved cognitive skills in children with ASD and highlighted the potential of game-based interventions in their development. [8]

Emotional responses are challenging for individuals with ASD, meaning their ability to manage things like stress and respond appropriately to others become difficult. Game-based interventions can provide a controlled environment where the users can learn and practise emotional responses or strategies to use in the real world. A conference paper titled Autism Screening Using a Video Game Based on Emotions used a serious game with four algorithms to screen children to attempt to identify if any had ASD. The report indicates many subjects were not familiar with emotions and could not properly play the game suggesting the difficulty in using this method for research. [9]

Furthermore, an article by Sara Peretti, Maria Pino, Federica Caruso and Tnia Mascio on evaluating the potential of immersive virtual reality based serious games with autism found that there is an importance on the accessibility on such intervention and whether its effectiveness needs to be questioned. [10]

A conference paper on the Design and development of console-based gaming for balance training in Autism Spectrum Disorder Children showed the possibility of success where a console-based game was used to improve the physical balance of children with ASD. [11]

With all these promising findings there still are several gaps remaining in the field of game-based interventions and individuals with ASD, one being the need for more research into play-based interventions in an educational setting which was mentioned in the O’Keeffe and McNally paper [6]. Additionally with current technological innovations offering new avenues for intervention there is a need for more thorough evaluation framework to assess the effectiveness of these new interventions, as [10] expressed the need for this and the importance of developing such frameworks to allow future research.

Several gaps found in this area are as follows:

- Cognitive Skills and Game-Based Intervention

Even though many game-based interventions exist very few specifically aim to improve the cognitive functions of an individual with ASD, for instance their attention or working memory. Therefore, an actionable application gap would be to use existing techniques and design a game-based intervention that directly exercises these cognitive areas.

- User Design

Current games often don’t adapt to a users cognitive or sensory understanding of an individual with ASD, meaning using a contextual gap would be to develop a customisable game or application with adjustable settings, similar to an entertainment game but with more personalised settings for an individual with ASD.

- Real world usability and engagement testing

Majority of studies measure the cognitive outcomes in certain conditions but don’t track the engagement, motivation or enjoyment during the testing, an implementation gap here would be, including the user testing and feedback loops to assess these areas.

- Accessible technology

Advances in technology setups can be expensive and complex especially for implementation therefore a mobile or tablet-based intervention would be more practical and easily accessible making this limitation gap more plausible.

# 3. Problem statement

Game-based interventions have shown potential for supporting individuals with autism, there is as previously mentioned a lack of tailored games that address the specific cognitive, social and emotional challenges faced by these individuals. Current interventions often fail to adapt to the individual’s needs, and this project will address this gap by investigating these challenges, evaluating the current approaches and developing a prototype mini game which will assess its impact on engagement, emotional responses and interaction skills.

# 4. Aim & Objectives

The aim of this project is to design, develop and evaluate a tailored mobile game that supports the cognitive, social and emotional development of individuals with autism spectrum disorder by addressing their specific challenges and assessing the engagement, usability and impact.

The research objectives for this project are:

- Investigate the challenges faced by individual with ASD in the cognitive, social and emotional areas through literature review.

- Evaluate existing game-based interventions and mobile application to identify effective strategies and features which can be produced into the prototype.

- Design and develop a prototype incorporating a mini game or games which target attention, memory and executive functions with adjustable setting to allow engaging feedback.

- Assess the impact of the prototype by user engagement, user performance, possible emotional response and social interaction via user testing and feedback

# 5. Methodology

This section of the project proposal outlines the research methodology which will be adopted to achieve the projects aim and objectives, it will detail the methods and strategies which will be used to design and develop the mobile game prototype for individual with autism.

The methodology will be structed in a way so that a practical and user centered approach can be taken, ensuring both quantitative and qualitative data can be used to assess the outcomes, with ethical considerations, tools and hardware requirements considered.

## 5.1 Methods

This project will use a mixed method approach where the combination of quantitative and qualitative techniques will address the research objectives. This will be appropriate because it will allow the research to be captured by both the objective outcomes and the subjective experiences, the research strategy will follow both a software development and research approach allowing the implementation and evaluation of a prototype.

Quantitative data will be analysed in a descriptive statistics manner, while the qualitative feedback will be used to evaluate the usability and engagement in a thematic analysis way.

## 5.2 Materials

The data sources include individuals with Autism and input from possible care givers, the collection methods would comprise of in game metrics a structured observation and a brief feedback survey. The ethical considerations could include consent from the participants and only present a low risk factor where the individuals involved may become stressed during participation, this can be overcome by allowing the participant to withdraw at anytime but ensuring the mini games and settings take into consideration different possible triggers.

Tools needed would be sufficient software such as unity or the MIT app inventor which would help with development of the prototype, Microsoft excel and Nvivo can be used for the data analysis while a standard mobile phone or tablet will be used for the gameplay testing.

This methodology will ensure an evidence and user centered approach which will address the cognitive, social and emotional development needs of individuals with ASD.

# 6 Project Plan

Project Timeline and Milestones (October 2025 – May 2026)

| Week Commencing | Task / Milestone | Details / Deliverables |
| --- | --- | --- |
| WC 6 Oct 2025 | Literature Review & Needs Analysis | Begin reviewing game-based interventions, identify cognitive/social/emotional challenges to determine project proposal |
| WC 13 Oct 2025 | Finalise Proposal Draft | Prepare aim and objectives, methodology and proposal for submission. |
| Mon 20 Oct 2025 | Project Proposal Submission | Submit completed project proposal by deadline. |
| Await feedback from project proposal |  |  |
| Nov 2025 | Game Architecture & Storyboarding | Develop wireframes, gameplay flow, and define data collection and feedback mechanisms. |
| WC 1 Dec 2025 | User Engagement Planning | Develop evaluation plan, design feedback forms, and testing |
| WC 5 Jan 2026 | Data Analysis & Interim Viva Preparation | Summarise preliminary research and prepare slides for Interim Viva presentation. |
| Thurs 15 – Fri 16 Jan 2026 | Interim Viva | Present progress, prototype design concept, and development strategy. |
| Jan 2026 | Prototype Development – Phase 1 | Begin coding core mini-games (attention & memory), basic UI, and data logging. |
| WC 2 Feb 2026 | Prototype Development – Phase 2 | Add executive function mini-game, feedback/reward system, and refine gameplay. |
| WC 2 Mar 2026 | User Testing & Data Collection | Conduct sessions with ASD participants, collect engagement and performance data. |
| WC 16 Mar 2026 | Data Analysis & Evaluation | Analyse quantitative and qualitative data, assess usability and outcomes. |
| WC 6 Apr 2026 | Final Adjustments | Conduct final adjustments |
| WC 13 Apr 2026 | Final Report Writing | Compile findings, discussion, and conclusions. Prepare for final submission. |
| Thurs 1 May 2026 | Final Report Submission | Submit final project deliverables and documentation. |

Timetable will adjust dependant on feedback from project proposal and ethics results.

# 7. References

[1] Anonymous . What is autism. Available: https://www.autism.org.uk/advice-and-guidance/what-is-autism.

[2] S. Yuvaraj, S. Sugavanaesh, C. T. Kumar, G. Saran and R. Subha. S. Yuvaraj, S. Sugavanaesh, C. T. Kumar, G. Saran and R. Subha. Identification of autism spectrum disorder (ASD) in adults through various machine learning algorithms. Identification of autism spectrum disorder (ASD) in adults through various machine learning algorithms. Presented at 2024 2nd International Conference on Intelligent Data Communication Technologies and Internet of Things (IDCIoT). Presented at 2024 2nd International Conference on Intelligent Data Communication Technologies and Internet of Things (IDCIoT). 2024, . DOI: 10.1109/IDCIoT59759.2024.10467893.

[3] C. Adair. C. Adair. Video game addiction statistics 2023. Video game addiction statistics 2023. Available: https://gamequitters.com/video-game-addiction-statistics/.

[4] L. Kars. L. Kars. What are serious games? - grendel games. What are serious games? - grendel games. 2025. Available: https://grendelgames.com/what-are-serious-games/.

[5] G. P. Tolentino, C. Battaglini, A. C. V. Pereira, R. J. d. Oliveria and M. G. M. d. Paula. G. P. Tolentino, C. Battaglini, A. C. V. Pereira, R. J. d. Oliveria and M. G. M. d. Paula. Usability of serious games for health. Usability of serious games for health. Presented at 2011 Third International Conference on Games and Virtual Worlds for Serious Applications. Presented at 2011 Third International Conference on Games and Virtual Worlds for Serious Applications. 2011, . DOI: 10.1109/VS-GAMES.2011.33.

[6] C. O’Keeffe and S. McNally. C. O’Keeffe and S. McNally. A systematic review of play-based interventions targeting the social communication skills of children with autism spectrum disorder in educational contexts. A systematic review of play-based interventions targeting the social communication skills of children with autism spectrum disorder in educational contexts. Rev J Autism Dev Disord Rev J Autism Dev Disord 1010(1), pp. 51–81. pp. 51–81. 2023. Available: https://doi.org/10.1007/s40489-021-00286-3. DOI: 10.1007/s40489-021-00286-3.

[7] I. Dunwell, K. Torrens, S. Clarke and S. Doukianou. I. Dunwell, K. Torrens, S. Clarke and S. Doukianou. Game-based lifestyle interventions for adolescents: An evidence-based approach. Game-based lifestyle interventions for adolescents: An evidence-based approach. November 1, 2014, Available: https://ieeexplore.ieee.org/document/7011146. DOI: 10.1109/IMCTL.2014.7011146.

[8] S. Derks, A. M. Willemen and P. S. Sterkenburg. S. Derks, A. M. Willemen and P. S. Sterkenburg. Improving adaptive and cognitive skills of children with an intellectual disability and/or autism spectrum disorder: Meta-analysis of randomised controlled trials on the effects of serious games. Improving adaptive and cognitive skills of children with an intellectual disability and/or autism spectrum disorder: Meta-analysis of randomised controlled trials on the effects of serious games. International Journal of Child-Computer Interaction International Journal of Child-Computer Interaction 3333pp. 100488. pp. 100488. 2022. Available: https://www.sciencedirect.com/science/article/pii/S2212868922000228. DOI: 10.1016/j.ijcci.2022.100488.

[9] A. Irani, H. Moradi and L. K. Vahid. A. Irani, H. Moradi and L. K. Vahid. Autism screening using a video game based on emotions. Autism screening using a video game based on emotions. 2018-11, Available: https://ieeexplore.ieee.org/document/8712053. DOI: 10.1109/DGRC.2018.8712053.

[10] S. Peretti, M. C. Pino, F. Caruso and T. Di Mascio. S. Peretti, M. C. Pino, F. Caruso and T. Di Mascio. Evaluating the potential of immersive virtual reality-based serious games interventions for autism: A pocket guide evaluation framework. Evaluating the potential of immersive virtual reality-based serious games interventions for autism: A pocket guide evaluation framework. Education Sciences Education Sciences 1414(4), pp. 377. pp. 377. 2024. Available: https://www.mdpi.com/2227-7102/14/4/377. DOI: 10.3390/educsci14040377.

[11] P. R, N. N, M. V. Menon, G. M, D. A. Kumar, G. S. U and V. Karthik. P. R, N. N, M. V. Menon, G. M, D. A. Kumar, G. S. U and V. Karthik. Design and development of console-based gaming for balance training in autism spectrum disorder children. Design and development of console-based gaming for balance training in autism spectrum disorder children. 2025-04, Available: https://ieeexplore.ieee.org/document/11042391. DOI: 10.1109/ICTEST64710.2025.11042391.