Macbeth Production Meeting Agenda.

Date: 23/02/16

Time: 18:00-19:00

Location: PA001

Attendee(s): Amber Cole-Pendrey, Julie Brathwaite, Dave Atkinson, Stacey-Jo Atkinson, Steve Dennis, Becky Ellard, Becca Moore, Conor Manning, Chris Rio, Anthony Wicks, Erin Jones, Louisa Hickman, Lucie Mitchell, Bruce Guthrie.

Topics:

Introductions

Any Apologies:

Recap on how this week’s rehearsals have gone:

Set:

-The set is built in the theatre and has been sanded down as much as possible.

-the Side infills have been made.

-More infills are to be made.

-Schedule for paint call. Date and Time.

-Paint has been ordered and costs Approx £250

Set Construction:

-Side treads may need to be redone.

-Making Banquos table

-Schedule for adding in the traps.

Props:

-Props bible has been presented (Monday 22/02/16)

-The props team have already been to Celtic props hire and will arrange another date for pick up of chosen props

-5Xbroad swords and 7X daggers will be rented from Kevin McCurdy. A Borrow Form will be drawn up for this.

-When are the Torches arriving?

-Thrones.

-Crowns.

-Pigs head

-Doctors Scroll

-Gun

-How many of the murderers need blood (packs and capsules)

Costume:

-Costume fittings have been completed and a document with the amendments to be made has been sent to Bruce.

-Costume had a meeting with Bruce to discuss the costumes, this went well.

-There was lots of feedback for costume which will be worked on through the week.

-Alice and Conor will be in helping Becky.

-Some items have been dyed today and there will be more fittings tonight to change elements.

-Costume parade 4pm on Friday?

Make-Up:

-Trials will be made over the week to investigate some bloods/looks.

-Banquo’s Ghost Make up

-Heads

-Do we need to order anything?

Lighting:

-The rig is up and Becca will be in as much as possible throughout rehearsals to get some possible lighting states.

- Schedule for adding the rest of LX and focusing.

-Do we need to order birdies?

Sound:

-Sound has been in rehearsals and has been working on the soundscapes after the meeting with Bruce yesterday 22/02/16.

-Hooligan spirit will be used as the opening scene music because it fits better and the ending might be changed/edited to work better for the following scene 1.2.

- Schedule for Sound and Plot.

Stage Management:

-Amelia’s availability is on Dropbox and Bruce has been made aware

-What is the rough Rehearsal Schedule for this week?

-Are the cast rehearsing on the weekend? What is the weekend schedule?

Budget How is each departmental budget? Please produce outstanding receipts by the end of the day.

Publicity: Programme progress. Poster to print?

Any Other Business

Any CPC orders?

Set Time and Date of next production meeting:

Time and date of design meeting:

Questions/Concerns/Discussion – other.