## DL_FM_039
Business Management System (BMS)
PROJECT DELIVERY PROCESS
Risk and Opportunity Register
Document Date: |  |  |  | 2020-10-01 | [5 empty] | Project Phase: |  |  | Tender Phase
Version No. |  |  |  | 1
Project Name: |  |  |  | Riverside Wharf
ID. | Risk (R)/ Opportunity(O) | Category | Risk/ Opportunity Area (include details of specific risk) | Consequences of Event (e.g. Time/Quality/ Cost/ Environment etc) | RATING |  |  | Current Risk/ Opportunity Owner (Organisation e.g. Principle Contractor, Client, Subcontractor etc.) |  | AGREED ACTION TO (a) MITIGATE AND/OR REMOVE RISK OR (b) REALISE OPPORTUNITY
[5 empty] | Probability | Impact | Overall Priority |  | IK Comments | ACTION | BY WHOM? | BY WHEN? |  | (Cost)/ Value | Note any residual risk (as appropriate). | Notes & Comments
[9 empty] | Pre construction (PC) STAGE ACTION |  |  | proposed | actual
SITE ABNORMALS
1` | R | Physical | Geotechnical. Ground conditions | Tender information will likely assume favourable ground conditions. Additional engineering work would result in additional costs | Medium | High | High | Principle contractor | Further Soil investigating (SI) during Pre constuction (PC) stage to eliminate any unknown factors in finalising sub-structure design solutions for all areas. Understand all costs and incorporate these into work packages. engineering consultant should prepare a schedule of further investigation works. Review the current SI information records | SI to be detailed and carried out at earliest opportunity during and after demolition. | Project Director | Week 6
2 | R | Physical | Geotechnical. Groundwater | Additional costs through requirement to treat/discharge groundwater. Implications on construction method and programme | Medium | Medium | Medium | Principle contractor | Further SI during PC stage to eliminate unknown factors in finalising sub-structure design solutions for all areas. Understand all costs and incorporate these into work packages. Discuss groundwater with consultant engineer. Suitable allowance for construction-stage water management costs. | SI to be detailed and carried out at earliest opportunity during and after demolition. | Project Director | Week 6
3 | R | Physical | Geotechnical. Contamination | Potential for significant additional costs if remediation or disposal of contaminated material is required | Low | High | Medium | Principle contractor | Further SI during PC stage to eliminate unknown factors in finalising sub-structure design solutions for all areas. Understand all costs and incorporate these into work packages. Check suitability of arisings with local tips. Confirm anticipated quantities? | Ground investigation to be scoped and carried out at earliest opportunity. | Project Director | Week 6
| R | Physical | Drainage. Capacity/Attenuation/ SUDS | Attenuation required to restrict discharge into water course to acceptable levels but minimal space on site to accomadate | Medium | Medium | Medium | Principle contractor | approval of the drainage scheme solutions required during PC stage to allow cost certainty. | Tender stage assessment has been made. | Design and Technical Manager | Week 3 PC
6 | R | Statutory | Drainage. Adoption Agreements sections 104/106/185 | Final legal agreements can significantly affect the overall programme. | High | Medium | Medium | Principle contractor | focuss on Progressing development of the sectional agreements during PC stage to technical approval. | Design team to engage with Local Authority Drainage board and welsh water to determine preferred option for discharge. | Design and Technical Manager | Week 2 PC
7 | R | Physical | Highways. sections 38/278 works | Technical Approval will be required with Highways for entrance alterations and on site 38 works | Medium | Medium | Medium | Principle contractor | focuss on Progressing development of the sectional agreements during PC stage to technical approval. | having Early engagement with Highways essential. | Design and Technical Manager | Week 2 PC
8 | R | Physical | services. Capacity and New Connections | Potentially very costly in particular if local infrastructure does not have capacity | Medium | Medium | Medium | Principle contractor | Utility enqueries will be obtained. Verify loadings for new service requirements during pc stage. | Tender Stage searches conducted. Loadings/requirements to be frozen at an early stage to allow quotations to be procured. | Design and Technical Manager | Week 3 PC
9
PLANNING
13 | R | Statutory | Planning Programme | Planning process is on critical path of pre-construction programme. Delays will effect project delivery | High | Medium | High | Principle contractor | Planning officer eing novated to maintain progression of planning application. Planning officer to report on level of risk at progress points through the building stage. | Team includes Planning Consultant and Design Manager with vast experience of managing complex planning applications-contract programme to be closely monitored. | Design and Technical Manager | Week 1 PC
14 | R | Statutory | Ecological Surveys/Tree Surveys/ Bat Surveys | Further ecology works will be required. Presence of protected species likely to affect programme | High | Medium | Medium | Principle contractor | ecological survey to be Carried out by 3rd party consultant. And act on any findings asap | PC to allow 10 days watching brief during early demolition/investigation works to determine any mitigation required. | Project Manager | Week 3 PC
COMMERCIAL/ FINANCIAL/ CONTRACTUAL
18 | R | Contractual | Contractual certainty and agreement. | Lack of collaboration | Low | Low | Low | All | Collaborative working and transparecncy through the PC stage. | it is envisaged that via active collaboration and communication during the PC stage there will be Contractual certainty which will negate risk for all parties. | Commercial Manager | PC STAGE
19 | R | Construction | Managing the Budget | Throughout the project development budget will need to be managed to ensure scheme viability | Medium | Medium | Medium | Morganstone | In close collaboration with commercial dept | Stage 1 tender will be costed using live data for schemes of similar construction including known abnormals, supplemented by market tested key packages. Changes and abnormals will be identified and reported throughout scheme development. | Commercial Manager | PC STAGE
20 | R | Programme | Change | Change to design through stakeholder engagement, unforeseen conditions, planning requirements will impact on project costs | Medium | Medium | Medium | Employer | Suggest we agree any potential changes quickly during early stages of PC to allow correct pricing and allocation. Propose a decision deadline for changes. Any post-contract changes would be covered by the contract. | the contractor is experienced at managing 2-stage projects through this process. Robust change control process to be utilised. Balanced approach to risk and opportunity and application of Value Engineering to keep within budget. | Commercial Manager | Week 12
CONSTRUCTION (including Health & Safety & Procedural)
22 | R | Physical | Main HV cable to be diverted | Time, Cost, | High | High | High | Morganstone | correspondance with western power to commence asap, lock in quotes and timescales | Main HV Cable to be diverted to allow construction. Payment to be made by the client, currently 12 weeks lead time with 1 week of works. | Project Director | Prior to works commencing
23 | R | Construction | Fire/arson during the construction of the site. | Time, Cost | High | High | High | Morganstone | ensure comprehensicve security is priced into welfare and prelims | Due to the risk of fire during the construction phases and the consequence of such a event contractor would construct the key terraced units using traditional build methods masonry to all structural walls. | Project Director | Week 1 PC
24 | R | Construction | Construction Noise during site works | Environmental | Medium | Medium | Medium | Morganstone | ensure subbies contracts include keeping track of and monitoring sound levels of their own work | • Engage with the local authority and enter into a Section 61 Consent during and after planning to ensure noise restrictions suit our programme of works | Project Director | Prior to works commencing
25 | R | Physical | Managing the interface with residents during early construction works | Environmental | Low | Low | Low | Morganstone | letter drops / social media posts should go out to residents before any work commences | Initial engagement with local residents and councillors to inform all parties of the proposed works using various communications techniques such as:- letter drops, community meetings, social media, site information boards etc… Regular updates will be provided to residents in the vicinity with further updates provided to the wider occupants of the area. | Project Director | Prior to works commencing
27 | R | Construction | Community | Time | Low | Low | Low | Morganstone | ensure plan templates are in place and csr manager to commence reaserch on local area to ensure relevance | • Risk of bad publicity for contractor and client during the construction phases. • Stake holder management plan (SMP) and Corporate Social Responsibilities(CSR) plan will be developed to inform engagement and drive community benefits. | Project Director | Prior to works commencing
28 | R | Construction | Community Engagement | Time | Low | Low | Low | Morganstone | ensure plan templates are in place and csr manager to commence reaserch on local area to ensure relevance | • Excellent record for delivering the CSR Plan • Opportunities for local employment and supply chain | Project Director | Prior to works commencing
29 | R | Construction | Site Security | Time | Low | Medium | Low | Morganstone | make sure adequate pricing for security includes full coverage and call outs costed for security | • Break-ins and damage will cause disruption to the scheme. A dedicated CCTV System will be installed to cover the whole site including a web camera for monitoring progress and timeline for the scheme. | Project Director | Prior to and as works progress

## Validation (hidden)
Probability and Impact | Select: | Select from the list below: | Select:
Select from the list: | R | Tender Phase | Construction
High | O | Construction Phase | Programme
Medium |  | Completion Phase | Statutory
Low |  |  | Physical