EXERCISE. METHOD STUDY

- Explain the procedure for method study, stages to implement and possible techniques you can use. Put one example of a common situation in which you can use one of these techniques in the construction industry.

- There is a gang of 3 bricklayers + 1 assistant. The assistant is in charge of mixing and providing mortar to the bricklayers, who are working in a scaffold. Besides, the assistant also supply with bricks. Although they are a gang, the bricklayers are supplied independently. According to the time study developed, the following activities and times were calculated:

Mortar mixing: 5 minutes

Supply mortar to scaffold: 5 minutes (including time to go back to mortar mixer)

Supply with bricks (per bricklayer independently): 5 minutes

Time for a bricklayer to run out of mortar : 45 minutes

Time for a bricklayer to run out of bricks: 2 hour

- Draw your own multiple activity chart and design an optimum solution to organise the work of this gang.

- Considering each bricklayer can lay 10 bricks per minute (size 440x215mm + 10mm joints), calculate the area of wall that can be constructed in one day (8 hrs a day)