These are the screenshots of my completed Coursework 2  which showed all added roles and features and represents my topology.
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