PRODUCTIVITY EXERCISES

- A gang of 2 bricklayers and 1 assistant can make an average of 20 m2 of wall per day (working 8 hrs/day). Calculate the following:

  - Labour hours.

  - The duration of works if we need to build 550 m2 of wall.

  - The weighted wage rate if the salary of a bricklayer is £18/hour and of an assistant is £12/hour.

  - The labour unit cost.

- We need to build the steel reinforcement for a foundation of 2,000 m2 with 1 gang of 4 labourers. If the production rate is 50 m2/day (working 8hr/day), calculate the following:

  - Work duration

  - Labour hours

- The budget for the maintenance of one road with 50 Km is £80,000. For that purpose we need to pay a gang of 5 labourers (£15/hour) that can repair 1 Km per day (working 8hr/day). Calculate the following:

  - Money available to pay for the equipment.

  - Weighted wage rate.

  - Labour unit cost.

- We need to finish the construction of one slab (5,000m2) in 4 days. one gang (3 labourers) can make 200m2/day (working 8hr/day). If the salary of one labourer is £16/m2, calculate the following:

  - Number of gangs needed to finish these works on time.

  - Labour cost for the construction of this slab.

  - We can increase one more labourer to every gang. In that case, the production rate achieved per gang is 250m2/day. Compare the labour hours in each case and say if it is a good solution to save money (supposing the same duration of works).