Client: Green haven florist Norwich

Prepared for: Liam and Priya Patel

Prepared by: Devon Wilson

Date:

Module:

- OVERVIEW OF GREEN HAVEN FLORISTS & THE PROBLEM

Green Haven Florists is an independent Norwich business founded in 2016, known for bespoke designs, eco-friendly practices and strong community ties. Over the last year, it has faced a 30% drop in in-store sales; modest online growth has failed to offset this decline. Reduced high street footfall, rising supply and operational costs, outdated digital systems, and intensifying competition from online discounters and new local rivals have eroded profitability. Customers also seek better digital functionality and flexible services. The business must modernise and differentiate its offering to survive in an evolving retail landscape.

## 2. PROPOSED SOLUTIONS

### Solution 1: Digital Transformation & Subscription Service

This solution involves upgrading the website to be mobile-friendly, adding secure e-commerce, flexible delivery slots, and introducing tiered subscription models (weekly/monthly seasonal blooms, corporate contracts, event packages). It also builds a consistent social media presence to showcase the shop’s creative, sustainable strengths. This directly addresses customer feedback, captures the shift to online purchasing, and creates predictable recurring revenue to stabilise cashflow.

### Solution 2: In-Store Experience & Community Hub

This option reconfigures the shop as a destination space: hosting flower-arranging workshops, seasonal pop-ups, and collaborating with local businesses. It retains and amplifies Green Haven’s personal touch and eco-ethos, encouraging footfall and word-of-mouth. It differentiates the business from faceless online competitors, builds loyalty, and opens new revenue streams from ticket sales and cross-promotion.

## 3. EVALUATION OF SOLUTIONS

### 3A. PMI Analysis

Table

| Solution | Pluses | Minuses | Implications |
| --- | --- | --- | --- |
| Digital & Subscription | - Addresses customer complaints about outdated systems - Recurring revenue improves cashflow - Reaches customers who no longer visit the high street - Scalable without extra physical space | - Requires upfront cost for web design & marketing - Needs time to build online audience - Margins may be lower on discounted subscriptions | - Aligns with long-term retail trends - Protects against further footfall decline - Reinforces sustainable brand identity |
| In-Store & Community Hub | - Leverages existing strengths & local reputation - Creates unique experience online rivals cannot match - Low upfront investment compared to full digital overhaul | - Limited by reduced high street activity - Dependent on local attendance - Revenue growth is slower and less predictable | - Boosts brand loyalty but does not resolve core digital weaknesses - Offers only partial protection against market shifts |

### 3B. RATIONALE FOR PREFERRED SOLUTION

Preferred Solution: Digital Transformation & Subscription Service

This option is chosen because it directly tackles the root causes of decline: lost online sales opportunities, changing customer habits, and unpredictable revenue. It combines modernisation with the shop’s core strengths of quality and sustainability, rather than relying on footfall that may not recover. It also creates stable income, which is critical amid rising costs, and can be run alongside existing in-store operations without replacing them.

## 4. RISK ANALYSIS

### 4A. RISK REGISTER

Table

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Upfront costs exceed budget | Medium | High | Phased implementation; use local web developers for competitive rates; apply for small business digital grants |
| Low uptake of subscriptions | Medium | Medium | Launch with discounted trial offers; partner with local offices to secure corporate contracts |
| Website launch delays | Low | Medium | Set realistic deadlines; use pre-built, customisable e-commerce platforms to reduce development time |
| Increased competition copying offers | High | Low | Differentiate via eco-certifications, locally sourced blooms and custom designs that mass retailers cannot replicate |

### 4B. OUTCOME OF RISK ANALYSIS

The analysis confirms the solution is viable: all high-impact risks have clear, affordable mitigation steps, and low-impact risks are easily managed. The phased rollout limits financial exposure, while the shop’s established reputation and unique sustainable positioning reduce the threat of copycat competition. Overall, the benefits of stabilising revenue and adapting to market changes far outweigh the manageable risks involved.

## 5. IMPLEMENTATION PLAN

### 5A. PLAN

Table

| Phase | Timeline | Activity | Responsible Party |
| --- | --- | --- | --- |
| 1: Preparation | Weeks 1–4 | Audit current website; consult web designer; define subscription tiers & pricing; research local business grants | Liam & Priya + freelance web developer |
| 2: Build & Test | Weeks 5–8 | Build responsive e-commerce site; set up delivery & payment systems; test user experience; finalise subscription terms | Web developer + Priya |
| 3: Launch | Weeks 9–10 | Launch website & subscriptions; run social media campaign; offer launch discounts; contact corporate clients | Liam & Priya |
| 4: Review & refine | Ongoing | Monitor sales & feedback; update content; adjust subscription options; grow social media channels | Liam & Priya |

### 5B. JUSTIFICATION

This phased approach minimises disruption and cost, allowing the business to continue trading while upgrading. Starting with planning ensures all requirements are aligned with customer needs and budget. Testing before launch prevents technical issues that would damage reputation. The staggered rollout also allows adjustments based on early feedback, while ongoing review ensures the solution evolves with market changes.

## 6. KPIS & SMART OBJECTIVES

### 6A. METRICS

Key Performance Indicator: Total Revenue (in-store + online) and Recurring Revenue Share

Table

SMART Objective

Achieve a 20% increase in overall sales within 12 months, with 30% of revenue coming from online orders and subscriptions

Attract 50+ active monthly subscribers and 10+ corporate subscription accounts within 6 months

Reduce customer complaints about website usability to zero within 2 months of launch

### 6B. USAGE OF METRICS

These metrics will be tracked monthly using sales data, website analytics and customer feedback forms. Revenue figures will show if the solution is improving profitability, while subscription numbers will confirm if recurring income targets are being met. Usability feedback will highlight areas for improvement. Progress will be reviewed quarterly to adjust marketing, pricing or website features as needed, ensuring the solution remains effective and aligned with business goals.

## 7. KEY FINDINGS SUMMARY

- Green Haven’s decline stems from shifting customer behaviour, outdated digital systems and rising competition, not poor product quality.

- The preferred solution of digital upgrades and subscription services addresses all core challenges, creating stable income and expanding reach.

- Risks are manageable with careful planning and phased implementation.

- Success will be measured through sales growth, subscription uptake and customer satisfaction.

- This approach preserves the shop’s unique identity while adapting to modern retail demands.

## REFERENCES

- CBI (2025) The Future of UK High Street Retail. London: Confederation of British Industry.

- Flowers & Plants Association (2026) Sustainability and Consumer Trends in the UK Floristry Sector. London: FPA.

- Gov.uk (2026) Digital Transformation Grants for Small Businesses. Available at: https://www.gov.uk/access-to-digital-funding(Accessed 18 July 2026).

- Mintel (2025) Online Flower Delivery Market Report – UK. London: Mintel Group Ltd.

Open Dola