## Front
NRM1 Cost Plan Template
F+G
27/01/2023

## Status
NRM1 Elemental Cost Plan Template
2022-11-02
Document Status
Revision | Date | Status | Prepared by | Checked by | Authorised by
DISCLAIMER
This document and its contents have been prepared and are intended solely for [name of client] information and use in relation to [name of project]
Faithful+Gould assumes no responsibility to any other party in respect of or arising out of or in connection with this document and/or its contents.
COPYRIGHT
The copyright of this document is vested in Faithful+Gould. This document may not be reproduced in whole or in part without their express written permission.

## Information Used
Information Used & Assumptions
1 | Information Used
Design Drawings;
Innovation Matrix - Ground Floor Shell and Core
Innovation Matrix - Proposed Landscape Plan
Innovation Matrix - First Floor Shell and Core
Innovation Matrix - Existing Site Plan
Innovation Matrix - Roof Plan, Full Building
Innovation Matrix - Elevations
Innovation Matrix - Elevations Detail 1
Innovation Matrix - Elevations Detail 2
Innovation Matrix - Section
Innovation Matrix - Ground Floor Layout, Full Building
Innovation Matrix - First Floor Layout, Full Building
2 | General Assumptions;
External Works is excluded unless specifically identified within the cost plan.
Cavity Wall with no insulation is assumed.
Costs are based upon the information as provided by drawings or query sheets.
We have assumed a project bank account will not be required for this scheme.
We have assumed that the area of works will be decanted for the project. No allowance is made for throughways or dealing with building occupants.
The exact nature of specification for internal doors, screens, folding partitions and finishes is assumed.
All costs are provisional awaiting design development.
All base costs are based on Q42022
Assumed that WC Suite from spons included WC and hand wash station
Assumed internal walls are timber stud partitions
3 | General Notes and Exclusions;
All included costs are subject to variation following design development.
Land Costs
A risk allowance of 10% is included for this estimate.
VAT is excluded from the estimate.
Works will be undertaken in a single phase.
Local Authority Fees
Building Regulation fees
Party Wall Awards
Acquisition & associated legals
Provisional demolition cost of £35,000
No foundation drawings, provisional sum of £350/m2
Provisional sum for furnishings and fittings as usage and number of occupants are not known
Provisional sum for services of £350/m2 as no drawings/information given

## Summary Original
Project details: Innovation Matrix
Description: Innovation Matrix
Building Works Estimate
Based on GIA of: 3704.88m2 |  |  |  |  | 3704.88
| Group Element | Element Type | Total | £/m2
| Group element 0 | FACILITATING WORKS - excluded from scope | 35000 | 9.447
| Group element 1 | SUBSTRUCTURE | 716625 | 193.4273
| Group element 2 | SUPERSTRUCTURE | 3275057.2521 | 883.9847 | 3562.6623
| Group element 3 | INTERNAL FINISHES | 423343.3686 | 114.2664
| Group element 4 | FITTINGS AND FURNISHINGS | 222292.8 | 60
| Group element 5 | SERVICES | 6518814.048 | 1759.521
| Group element 8 | EXTERNAL WORKS - excluded from scope | 0 | 0
| Group element 9 | MAIN CONTRACTOR'S PRELIMINARIES | 2008103.8444 | 542.0159
Works cost estimate (sub total A) |  |  | 13199236.3131 | 3562.6623
Project design team fees and other development costs (sub total B)
Base cost estimate A + B (sub total C) |  |  | 13199236.3131 | 3562.6623
Group element 13
| Design Contingency | Risk allowance @ 5% | 659961.8157 | 178.1331
| Construction Risk | Risk allowance @ 2.50% | 329980.9078 | 89.0666
| Employers Change Risk | Risk allowance @ 2.50% | 329980.9078 | 89.0666
| Other Mis. Risk | Risk allowance @ 0% | 0 | 0
Total Risk allowances (sub total D) |  |  | 1319923.6313 | 356.2662
Total Construction Cost (C + D) |  |  | 14519159.9444 | 3918.9285

## NRM1 CP template
Cost Plan for XXXXXXX
NRM 1 phaseologies
Elemental Cost Plan
Elements in red are NRM1 Phraseologies
Ref. | Element | Timesing | Quantity |  | Unit | Rate | Sub-Total | Group-Total | Notes
[6 empty] | £ | £ | £
GIFA
| GF |  | 25.8
|  |  | 71.8 | 1852.44
| FF |  | 25.8
|  |  | 71.8 | 1852.44
|  |  |  | 3704.88 | m2
0 | FACILITATING WORKS - excluded from scope | [6 empty] | 35000
0.1 | Demolition |  |  |  |  | 35000 | 35000 |  | Sum stated in query sheet 1
1 | SUBSTRUCTURE | [6 empty] | 716625
1.1 | Foundations | GF | 27.5
|  |  | 73 | 2007.5
|  |  |  | 2007.5 | m2
1.1.1 | [5 empty] | 350 | 702625 |  | Sum stated in query sheet 1
1.2 | Extra Overs
1.2.1 | Lift Bases |  | 2 | 2 | Nr | 2000 | 4000
1.2.2 | Two Ends of cladding founds |  | 2 | 2 | Nr | 5000 | 10000
2 | SUPERSTRUCTURE | [6 empty] | 3275057.2521
2.1 | Frame
Steel frame, composite beam and slab floors,
| Suspended slab, permanent steel shuttering with 130 mm thick concrete including steel frame. |  |  | 3704.88 | GIFA | 225 | 833598 |  | Sum stated in query sheet 2
2.2 | Upper Floors |  | 26.5
|  |  | 75 | 1987.5
1987.5
|  | Void A | 9
|  |  | 8.4 | 75.6
|  | Void B | 7.5
|  |  | 7.5 | 56.25
|  | Void C | 25.4
|  |  | 6 | 152.4
|  | Void D | 18
|  |  | 6 | 108
|  | Void E | 16.5
|  |  | 5.8 | 95.7
|  | Void F | 8.8
|  |  | 8 | 70.4
|  | Lifts 2 | 1.5
|  |  | 2 | 6
|  | Void G | 9
|  |  | 1.5 | 13.5
|  |  |  | 1409.65 | m2
[6 empty] | 120 | 169158 |  | Sum stated in Query sheet 3
2.3 | Roof
27.2
| Metal cladding panel |  | 76 | 2067.2 | m2 | 280 | 578816 |  | Sum stated in query sheet 1, including over hang of building
2.4 | Stairs & Ramps |  | 5 | [5 empty] | Number of flights
2.4.1 | Reinforced concrete construction Staircase; terrazzofinish; mild steel balustrades and handrails; plastered soffit;balustrades and staircase soffit decorated3.00m rise; dogleg |  |  | 5 | Nr | 12005.4 | 60027 |  | Updated TPI and Location Factor
2.4.2 | Lifts
2
| Passenger lift, (standard brushed stainless steel finish; 2 panel centre opening doors) 8-person; 4 stops; 1.0 m/s speed including a lift car LCD TV |  |  | 2 | Nr | 103683 | 207366 |  | Updated TPI and Location Factor
2.5 | External Walls
| Metal profiled cladding panel - Flat panel composite insulated roofing system; micro-rib panel; 60mm overall panel, thickness (U-value = 0.35W/m2K) |  | 152 | [5 empty] | Definition from Spons Pg. 197
|  |  | 3.4 | 516.8
516.8
1.9
|  | 48 | 3 | 273.6
273.6
| GF |  |  | 243.2
152
|  |  | 3.4 | 516.8
516.8
1.9
|  | 48 | 3 | 273.6
273.6
| FF |  |  | 243.2
| SF |  | 152
|  |  | 0.8 | 121.6
243.2
243.2
121.6
|  |  |  | 608 | m2 |  |  |  | Total of all external walls
[6 empty] | 280 | 170240 |  | Sum stated in query sheet 1
Perimeter Calculation
76
76
152
2.6 | Windows and external doors
2.6.1 | Windows
| Composite aluminium/timber windows; U value = 1.5W/m2K | 96 | 3
| Purpose-made windows; stainless steel ironmongery; Velfac System 200 or similar, Fixed windows up to 1.50m2 |  | 1.4
|  |  |  | 403.2 | m2 | 316.506 | 127615.2192 |  | Updated TPI and Location Factor
| Composite aluminium/timber windows; U value = 1.5W/m2K Purpose-made windows; stainless steel ironmongery; Velfac System 200 or similar, Fixed windows up to 1.50m2 | 64 | 0.5
1.4
|  |  |  | 44.8 | m2
[6 empty] | 316.506 | 14179.4688 |  | Updated TPI and Location Factor
| Unitized curtain walling system with double glazed units, aluminium structural framing and sandal rails. Standard colour powered coated |  | 21.7
|  | 2 | 3.8 | 164.92
25.7
|  | 2 | 3.8 | 195.32
Triangels
|  | 2 | 21.76
43.52
|  |  |  | 403.76 | m2 | 1309.68 | 528796.3968 |  | Updated TPI and Location Factor
2.6.2 | External Doors
| Revolving door |  | 2
|  |  |  | 2 | Nr | 45000 | 90000 |  | Sum stated in query sheet 2
| Wheel chair entrance door - Stainless steel entrance screens and doors, Purpose-made screen; double glazed, with automatic doors |  | 2
|  |  |  | 2 | Nr | 3274.2 | 6548.4 |  | Updated TPI and Location Factor
2.7 | Internal walls
2.7.1 | Walls |  | 63
| GF |  | 3.4 | [5 empty] | 3.4 single height 7 double height
|  |  |  | 214.2 | m2
| Timber stud partitions softwood stud comprising 100 mm × 38 mm softwood studs at 600 mm centres; head and sole plates; 12.5 mm thick plasterboard each side; tape and fill joints; emulsion finish | [7 empty] | Definition from spons Pg. 203
27
3.4
|  |  |  | 91.8 | m2
8.4
|  | 21 | 3.4
|  |  |  | 599.76 | m2
9
|  | 1 | 3.4
|  |  |  | 30.6 | m2
8.4
|  | 3 | 7
|  |  |  | 176.4 | m2
8.8
| FF |  | 3.2
|  |  |  | 28.16 | m2
27
3.2
|  |  |  | 86.4 | m2
9
|  | 4 | 3.2
|  |  |  | 115.2 | m2
8.8
|  | 13 | 3.2
|  |  |  | 366.08 | m2
18
|  | 2 | 3.2
|  |  |  | 115.2 | m2
|  |  |  | 1823.8 | m2 | 76.398 | 139334.6724 |  | Updated TPI and Location Factor
| toilet and plant room |  | 9
| GF | 2 | 3.4
|  |  |  | 61.2 | m2
8.4
|  | 4 | 3.4
|  |  |  | 114.24 | m2
| FF |  | 9
|  | 2 | 3.6
|  |  |  | 64.8 | m2
8.4
|  | 4 | 3.6
|  |  |  | 120.96 | m2
|  |  |  | 361.2 | m2 | 76.398 | 27594.9576 |  | Updated TPI and Location Factor
| Allowance for fire pInternal partitions 60/120 min fire-rating rotection through penetrations |  |  | 2185 | m2 | 98.226 | 214623.81 |  | Updated TPI and Location Factor
2.8 | Internal doors & screens & Windows
| Toilet doors - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets, standard bathroom door (unisex) |  | 48
|  |  |  | 48 | Nr | 354.705 | 17025.84 |  | Updated TPI and Location Factor
| GF doors - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets classroom door; lockable; fire-rated |  | 22
|  |  |  | 22 | Nr | 600.27 | 13205.94 |  | Updated TPI and Location Factor
| FF doors - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets classroom door; lockable; fire-rated |  | 12
|  |  |  | 12 | Nr | 600.27 | 7203.24 |  | Updated TPI and Location Factor
| Plant rooms - Ironmongery sets Stainless steel ironmongery; euro locks; push plates; kick plates; signage; closures; standard sets, maintenance/plant room door; lockable; fire-rated |  | 20
|  |  |  | 20 | Nr | 436.56 | 8731.2 |  | Updated TPI and Location Factor
| Screen Panel - Demountable/Folding partitions Demountable partitioning; aluminium framing; veneer finish doors medium quality; 46mm thick panels factory finish vinyl faced |  | 8.1
0.2
|  |  |  | 1.62 | m2 | 458.388 | 742.5886 |  | Updated TPI and Location Factor
| Internal Windows - Composite aluminium/timber windows; U value = 1.5W/m2K Purpose-made windows; stainless steel ironmongery; Velfac System 200 or similar, Fixed windows over to 1.50m2 |  | 2.8
|  | 26 | 1.2
|  |  |  | 87.36 | m2 | 338.334 | 29556.8582 |  | Updated TPI and Location Factor
2.8
|  | 2 | 0.2
|  |  |  | 1.12 | m2 | 338.334 | 378.9341 |  | Updated TPI and Location Factor
2.8
|  | 16 | 1
|  |  |  | 44.8 | m2 | 338.334 | 15157.3632 |  | Updated TPI and Location Factor
2.8
|  | 16 | 1
|  |  |  | 44.8 | m2 | 338.334 | 15157.3632 |  | Updated TPI and Location Factor
3 | INTERNAL FINISHES | [6 empty] | 423343.3686
3.1 | Wall finishes
3.1.1 | In situ wallfinishes one mist and two coats emulsion paint ( to General areas) | 2 | 146
|  | 2 | 292
|  |  | 584 | [5 empty] | Perimeter Calculation
73
|  |  | 403.2 | [5 empty] | 73
|  |  |  | 180.8 | m2 |  |  |  | 146
1823.8
2
|  |  |  | 3647.6 | m2
8.4
|  | 4 | 3.4
|  |  |  | 114.24 | m2
8.4
|  | 4 | 3.4
|  |  |  | 114.24 | m2
3.4
|  | 2 | 2.7
|  |  |  | 18.36 | m2
3.2
|  | 2 | 2.7
|  |  |  | 17.28 | m2
|  |  |  | 3864.04 | m2 | 5.5661 | 21507.7876 |  | Updated TPI and Location Factor
3.1.2 | Ceramic wall tiles; including backing (In Wet Areas)
| Disabled toilets |  | 1.6
2.3
3.9
2
7.8
|  | 4 | 3.4
|  |  |  | 106.08 | m2
7.8
|  | 4 | 3.6
|  |  |  | 112.32 | m2
| Toilet entrance hall |  | 1
|  | 2 | 1.8
3.6
|  | 4 | 3.4
|  |  |  | 48.96 | m2
3.6
|  | 4 | 3.6
|  |  |  | 51.84 | m2
| Shower Rooms |  | 2.7
|  | 2 | 1
5.4
|  | 4 | 3.4
|  |  |  | 73.44 | m2
5.4
|  | 4 | 3.6
|  |  |  | 77.76 | m2
| Toilet cubicles |  | 1
|  | 2 | 1.6
3.2
|  | 4 | 3.4
43.52
4
|  |  |  | 174.08 | m2
1
|  | 2 | 1.6
3.2
|  | 4 | 3.6
46.08
4
|  |  |  | 184.32 | m2
| Main toilet area |  | 4.8
|  | 2 | 1
9.6
|  | 4 | 3.4
|  |  |  | 130.56 | m2
9.6
|  | 4 | 3.6
|  |  |  | 138.24 | m2
|  |  |  | 1097.6 | m2 | 54.57 | 59896.032 |  | Updated TPI and Location Factor
3.2 | Floor finishes
3.2.1 | Cement and sand (1:3) screeds; steel trowelled
50 mm thick ( to Ground Floor)
| GF |  | 1756.16
| FF |  | 1208.14
2964.3
|  |  |  | 2964.3 | m2 | 21.828 | 64704.7404 |  | Updated TPI and Location Factor
3.2.2 | vinyl flooring (To Wet Areas) |  | 5.7
|  | 4 | 7.8 | 44.46
|  |  |  | 177.84 | m2 | 19.6452 | 3493.7024 |  | Updated TPI and Location Factor
3.2.3 | Carpet tiles; including underlay, edge grippersheavy domestic duty; tofloors
8.2
|  | 11 | 2.8 | 252.56
252.56
8.2
|  | 7 | 5.8 | 332.92
332.92
8.2
|  | 3 | 8.8 | 216.48
216.48
8.8
|  | 1 | 5.2 | 45.76
45.76
|  | Area 1 | 54
|  |  | 9 | 486
|  | Area 2 | 17.5
|  |  | 8.8 | 154
|  | Area 3 | 20.4
|  |  | 8.8 | 179.52
| GF |  |  | 1667.24
2.8
|  | 2 | 8.1 | 45.36
45.36
5.8
|  | 3 | 8.1 | 140.94
140.94
8.8
|  | 6 | 8.1 | 427.68
427.68
8.8
|  | 4 | 9.7 | 341.44
341.44
6
|  | 3 | 1.5 | 27
27
8.9
|  | 3 | 1.5 | 40.05
40.05
17.9
|  |  | 1.5 | 26.85
26.85
18.1
|  |  | 1.5 | 27.15
27.15
28.5
|  |  | 1.5 | 42.75
42.75
| FF |  |  | 1119.22
|  |  |  | 2786.46 | m2 | 76.398 | 212879.9711 |  | Updated TPI and Location Factor
3.3 | Ceiling finishes
| Armstrong suspended ceiling; mineral fibre; basic range; Cortega, Tatra, Academy; exposed grid |  | 5.7
|  | 4 | 7.8 | 44.46
177.84
8.2
|  | 11 | 2.8 | 252.56
252.56
8.2
|  | 7 | 5.8 | 332.92
332.92
8.2
|  | 3 | 8.8 | 216.48
216.48
8.8
|  | 1 | 5.2 | 45.76
45.76
847.72
2.8
|  | 2 | 8.1 | 45.36
45.36
5.8
|  | 3 | 8.1 | 140.94
140.94
8.8
|  | 6 | 8.1 | 427.68
427.68
8.8
|  | 4 | 9.7 | 341.44
341.44
6
|  | 3 | 1.5 | 27
27
8.9
|  | 3 | 1.5 | 40.05
40.05
17.9
|  |  | 1.5 | 26.85
26.85
18.1
|  |  | 1.5 | 27.15
27.15
28.5
|  |  | 1.5 | 42.75
42.75
|  |  |  | 2144.78 | m2 | 28.3764 | 60861.1352 |  | Updated TPI and Location Factor
| FITTINGS AND FURNISHINGS | [6 empty] | 222292.8
4 | General fittings, furnishings and equipment
|  |  |  | 3704.88 | GIFA | 60 | 222292.8 |  | Sum stated in Query sheet 3
5 | SERVICES | [6 empty] | 6518814.048
5.1 | Sanitary installations
| Disabled toilet, including WC, wash hand basin, grabrails and otherfittings |  | 8 |  | Nr | 1637.1 | 13096.8 |  | Updated TPI and Location Factor
| shower tray; glazedfireclay; chromium plated waste; riser pipe; rose andmixing valve |  | 8 |  | Nr | 763.98 | 6111.84 |  | Updated TPI and Location Factor
| WC suite |  | 32 |  | Nr | 502.044 | 16065.408 |  | Updated TPI and Location Factor
5.3 | Disposal Installations
5.3.1 | Generally |  |  | 3704.88 | GIFA | 350 | 1296708 |  | Sum stated in Query sheet 3
5.4 | Water installations
5.4.1 | Generally |  |  | 3704.88 | GIFA | 350 | 1296708 |  | Sum stated in Query sheet 3
5.5 | Heat source
5.5.1 | Generally |  |  | 3704.88 | GIFA | 350 | 1296708 |  | Sum stated in query sheet 2
5.8 | Electrical installations
5.8.1 | Generally |  |  | 3704.88 | GIFA | 350 | 1296708 |  | Sum stated in query sheet 2
5.12 | Power
5.12.1 | Power & Data distribution |  |  | 3704.88 | GIFA | 350 | 1296708 |  | Sum stated in Query sheet 3
9 | MAIN CONTRACTOR'S PRELIMINARIES
| Main contractors preliminaries |  |  | 12 | % | 1338735.8962
| OHP |  |  | 6 | % | 669367.9481
2008103.8444
| SECTION SUB-TOTAL | [5 empty] | 2008103.8444
13199236.3131
Note on F26: tc={067C826A-8B72-483A-9C36-E5C3607C1458}: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is measured using the GIFA Rule but only for lowest ground floor construction.
Note on D144: ,0: Number of windows, ground floor and first floor
Note on D165: ,0: 0.5*base*height
Note on D196: ,0: Number of the same length walls
Note on F252: ,0: Total of all internal Walls
Note on E273: ,0: Window height
Note on D293: ,0: Each side external walls
Note on D295: ,0: 2 floors
Note on F299: ,0: External wall inside - windows
Note on E302: ,0: Total of internal walls 30 minutes fire protection
Note on E303: ,0: Each side of the wall
Note on F309: ,0: One side of the toilet walls
Note on F313: ,0: Deduction of internal wall in the toilet
Note on F318: ,0: GF plant rooms
Note on F322: ,0: FF plant rooms
Note on E339: ,0: Disabled toilet width
Note on E340: ,0: Disabled toilet length
Note on E344: ,0: Each disabled toilet wall lengths added together
Note on D345: ,0: Number of disabled toilets on GF
Note on E345: ,0: GF Height
Note on D350: ,0: Number of disabled toilets on FF
Note on E350: ,0: FF height
Note on E357: ,0: Toilet hall
Note on D382: ,0: Toilet cubicles per toilet room
Note on E382: ,0: GF height
Note on E385: ,0: Number of Toilet rooms
Note on D395: ,0: Toilet cubicles per toilet room
Note on E395: ,0: FF height
Note on E398: ,0: Number of Toilet rooms
Note on D437: ,0: For both toilets on each floor
Note on D442: ,0: Number of rooms with this measurement
Note on D518: ,0: For both toilets on each floor
Note on D522: ,0: Number of rooms with this measurement

## TPI and Location Factor
TPI and Location Factor
| Cost | TPI | Location Factor | Reference
Spons |  | 4Q2022 128.4 | Wales 0.85
Stairs | 11000 | 14124 | 12005.4 | Spons Pg. 194
Lift | 95000 | 121980 | 103683 | Spons Pg. 215
Windows - 3.4 x 1.4 | 290 | 372.36 | 316.506 | Spons Pg. 201
Windows - 0.5 x 1.4 | 290 | 372.36 | 316.506 | Spons Pg. 201
Curtain Wall | 1200 | 1540.8 | 1309.68 | Spons Pg. 198
External Wheelchair Door | 3000 | 3852 | 3274.2 | Spons Pg. 202
Internal Walls | 70 | 89.88 | 76.398 | Spons Pg. 203
Toilet and plant internal Walls | 70 | 89.88 | 76.398 | Spons Pg. 203
Fire Protection 30/60mins | 90 | 115.56 | 98.226 | Spons Pg. 102
Toilet Doors | 325 | 417.3 | 354.705 | Spons Pg. 206
GF doors | 550 | 706.2 | 600.27 | Spons Pg. 206
FF doors | 550 | 706.2 | 600.27 | Spons Pg. 206
Plant room doors | 400 | 513.6 | 436.56 | Spons Pg. 206
Screen Panel | 420 | 539.28 | 458.388 | Spons Pg. 205
Internal Windows - All the same cost | 310 | 398.04 | 338.334 | Spons Pg. 201
Internal wall Paint | 5.1 | 6.5484 | 5.5661 | Spons Pg. 207
Internal wall Tiles | 50 | 64.2 | 54.57 | Spons Pg. 207
Floor finish, cement and sand | 20 | 25.68 | 21.828 | Spons Pg. 208
Floor finish, vinyl | 18 | 23.112 | 19.6452 | Spons Pg. 209
Floor finish, carpet tiles | 70 | 89.88 | 76.398 | Spons Pg. 209
Ceiling finish | 26 | 33.384 | 28.3764 | Spons Pg. 210
Sanitary - disabled toilet | 1500 | 1926 | 1637.1 | Spons Pg. 140
Sanitary - shower tray | 700 | 898.8 | 763.98 | Spons Pg. 213
Sanitary - WC Suite | 460 | 590.64 | 502.044 | Spons Pg. 143

## Finished Query Sheet 1
Student name: | Jenny Stroud
Return email: | 2008886@student.uwtsd.ac.uk
Innovation Matrix - Cost Plan
|  |  |  | Query Sheet Nr. | 1
Date : 18/11/22
QUERY |  |  | Answer
Are we starting on site in the fourth quarter of 2022? |  |  | Yes, anticipate start on site 4Q22
Are there any foundation drawings? |  |  | No, please allow £350/m2 of the floor area, allowance for the provision of all works upto ground level.
How thick would you like the floor slabs to be? |  |  | As above. (inc found rate)
What is the wall detail? |  |  | As drawings issued.
What material is going to be on the roof? |  |  | Metal Cladding Panel; please allow £280/m2
What are the ground conditions? |  |  | As above. (inc found rate)
Where is the site and is it clear or will it need demolition? |  |  | The site is in SA1 the demolition allowance as below.
Is there easy access for services? |  |  | Yes
Are there existing buildings in the area or works taking place? |  |  | Please allow £35,000 for demolition and clearing existing structures from the proposed site.
What is the cladding on the external walls? |  |  | Metal Cladding Panel; please allow £280/m2

## Finished Query Sheet 2
Student name: Jenny Stroud
Return email: 2008886@student.uwtsd.ac.uk
Innovation Matrix - Cost Plan
Query Sheet Nr. 2
Date : 29th November 2022
QUERY |  | Answer
What is the specification of the lifts? |  | Passenger lift; (standard brushed stainless steel finish; 2 panel centre opening doors) 8-person; 4 stops; 1.0 m/s speed including a lift car LCD TV
What’s the specification of the rotating doors? |  | Please include a Prov. Sum of £45,000 for the revolving door.
What is the mechanical and electrical plans? |  | Please use £350.00 / m2 of GIFA of the provision of M+E instatllation
What is the main structure material? |  | Steel frame; composite beam and slab floors Suspended slab; permanent steel shuttering with 130 mm thick concrete including steel frame. Please use £225 / m2 GIFA
What is the specification of the stairs and hand railings? |  | Pre cast concrete
What is the specification of the doors and windows? |  | Suitable for education provision
What is the finish to the internal walls? |  | one mist and two coats emulsion paint ( to General areas) Ceramic wall tiles; including backing (In Wet Areas) economical quality
What is the finish to the floors? |  | Cement and sand (1:3) screeds; steel trowelled 50 mm thick ( to Ground Floor) vinyl flooring (To Wet Areas); Carpets to all other areas
What is the finish to the ceilings? |  | Armstrong suspended ceiling; mineral fibre; basic range; Cortega, Tatra, Academy; exposed grid

## Finished Query Sheet 3
Student name: Jenny Stroud
Return email: 2008886@student.uwtsd.ac.uk
Innovation Matrix - Cost Plan
Query Sheet Nr. 3
Date : 8th December 2022
QUERY |  | Answer
Assuming £60 per m2 as a provisional sum for fittings and furnishings? |  | Yes please
Shall a provisional sum of £350 per m2 be used for Disposal Installations, Water installations, Heat source, Electrical installations and Power? |  | Yes please
Assuming a risk allowance of 10%? |  | Yes please
Assuming Main contractors preliminaries is 12% |  | Yes please
Assuming OHP is 6% |  | Yes please
What is the upper floor materials? |  | Please assume a precast concrete suspended floors at £120/m2