## Task List
Task No. | Aims | Task | Performed by | Days | Cost (£)
Task group: Field Investigation |  |  |  | 31.5 | 11340
1 |  | Set up site | PO | 1 | 360
2 |  | Mark out | PO | 1 | 360
3 |  | Topsoil | PO | 1 | 360
4 | 1, 2, 3, 4, 5, 6 | Trench 1 | PO | 5 | 1800
|  |  | FA | 11 | 3960
5 | 7, 8 | Outreach | PO | 1.5 | 540
|  |  | FA | 7 | 2520
6 | 1, 2, 3, 5, 7, 8 | Drone | FA | 2 | 720
7 |  | Backfill | PO | 1 | 360
8 |  | Close site | PO | 1 | 360
Task group: Preparation |  |  |  | 4.25 | 1620
9 |  | Return site archive to office | PO | 0.25 | 90
10 |  | Security copy site archive | CB | 1 | 450
11 | 1, 2, 3, 4, 5, 6 | Process Finds and Samples | SK | 3 | 1080
Task group: Specialist Analysis |  |  |  | 8.5 | 3825
12 | 1, 2, 3, 4, 5 | Documentary analysis | GG | 2 | 900
13 | 2, 4, 5 | Indentify/analyse and report on ceramics | PB/EMcS | 1.5 | 675
14 | 2, 4, 5 | Ceramic input into site phasing | PB/EMcS | 0.5 | 225
|  |  | GG | 0.5 | 225
15 | 2, 4, 5 | Produce updated phasing | GG | 0.5 | 225
16 | 4, 5 | Indentify/analyse and report on metalwork, as applicable | AB | 0.5 | 225
17 | 4, 5 | Indentify/analyse and report on lithics, as applicable | JS | 0.5 | 225
18 | 4, 5 | Indentify/analyse and report on animal bone, as applicable | AC/MH | 0.5 | 225
19 | 4, 5 | Indentify/analyse and report on human bone, as applicable | ShC | 0.5 | 225
20 | 2, 4, 5, 6 | Indentify/analyse and report on environemental remains | CS/SW | 1.5 | 675
Task group: Illustrations |  |  |  | 2 | 810
21 | 2, 4, 5, 8 | Produce pottery drawings | HMM | 0.5 | 180
22 | 2, 4, 5, 8 | Produce other finds drawings | HMM | 0.5 | 180
23 | 1, 2, 3, 4, 5, 8 | Produce site plans, sections, etc. | DL | 1 | 450
Task group: Preparation of Publication Text |  |  |  | 8.75 | 8268.75
24 |  | Review Meeting | PO + PX | 0.5 | 3082.5
25 |  | Write strategraphic text | GG | 2 | 900
26 |  | Edit and intergrate specialist reports | PB | 0.5 | 225
|  |  | GG | 0.5 | 225
27 |  | Write background/introduction | GG | 1.5 | 675
28 |  | Write discussions and conclusions | GG | 1.5 | 675
29 |  | Circulate text for internal comment/sign-off | PO + PX | 0.25 | 1541.25
30 |  | Collate report for referees and submit | LP | 1 | 495
|  |  | GG | 1 | 450
Task group: Update Project Design |  |  |  | 4 | 2025
31 |  | Receive and consider referee's comments | LP | 0.5 | 247.5
|  |  | SC | 0.5 | 270
|  |  | PB/EMcS | 0.5 | 180
32 |  | Meeting with Stakeholders | SC | 1 | 540
33 |  | Meeting with Editors | SC | 0.5 | 270
34 |  | Update Project Design for Editorial Execution Stage | LP | 0.5 | 247.5
|  |  | SC | 0.5 | 270
Task group: Signpost and Archive Deposition |  |  |  | 3.5 | 1327.5
35 |  | Update OASIS record | GG | 0.5 | 180
36 |  | Collate and deposit research archive | LP | 0.5 | 247.5
|  |  | CB | 2.5 | 900
Task group: Project Management |  |  |  | 4.5 | 5242.5
37 |  | General liaison / management; highlight report, issues log, risk log | SC | 4 | 2160
38 |  | End Stage Review Meeting | PO + PX | 0.5 | 3082.5
Task group: Post-project Outreach |  |  |  | 2.5 | 900
39 | 7,8 | Design and produce information boards; prepare for event | PO | 1 | 360
40 | 7,8 | Host outreach day event | PO | 1 | 360
41 | 7,8 | Host outreach evening seminar | PO | 0.5 | 180

## Costing
Project name: |  | Great Linford Manor Park: Project Design for Supplementary Archaeological Investigation with Community Involvement
Costing prepared by: |  | Laura Pearson, Project Manager
Staff | Post | Name (if known) | Day rate | Overhead % as decimal | Charge day rate | No. days | Total
| Project Officer | Unknown | 200 | 0.8 | 360 | 13 | 4680
| Archaeologist | Unknown | 200 | 0.8 | 360 | 6 | 2160
| Archaeologist (Drone Op) | Unknown | 200 | 0.8 | 360 | 7 | 2520
| Outreach Assistant | Unknown | 200 | 0.8 | 360 | 7 | 2520
| Post-Ex. Archaeologist | SK | 200 | 0.8 | 360 | 4.25 | 1530
| Ceramics Specialist | PB/EMcS | 250 | 0.8 | 450 | 4.25 | 1912.5
| Other Finds Specialists | AB, JS | 250 | 0.8 | 450 | 3.5 | 1575
| Other Enviro Specialists | AC, ShC | 250 | 0.8 | 450 | 3.5 | 1575
| Environmental Officer | CS/SW | 250 | 0.8 | 450 | 2.75 | 1237.5
| Assistant Illustrator | HMM | 200 | 0.8 | 360 | 2.25 | 810
| Geomatics Officer | DL | 250 | 0.8 | 450 | 2.25 | 1012.5
| Publications Officer | GG | 250 | 0.8 | 450 | 11.25 | 5062.5
| Archive Officer | CB | 250 | 0.8 | 450 | 4.75 | 2137.5
| Project Manager | LP | 275 | 0.8 | 495 | 3.75 | 1856.25
| Project Assurance | SC | 300 | 0.8 | 540 | 7.75 | 4185
TOTAL STAFF | [5 empty] | 83.25 | 34773.75
Non staff | Item |  | Rate (including VAT charged) |  |  | No. | Total
| Transport (per week) |  | 200 |  |  | 2 | 400
| Plant (per day) |  | 300 |  |  | 2 | 600
| Site Cabin (HQ; per day) |  | 100 |  |  | 10 | 1000
| Portaloo (per day) |  | 50 |  |  | 10 | 500
| HERAS Fencing (per day) |  | 60 |  |  | 10 | 600
| Sand bags (×50) |  | 25 |  |  | 1 | 25
| Outreach Supplies |  | 50 |  |  | 1 | 50
| Drone [CA equipment] |  | 0 |  |  | 1 | 0
| Gazebo [CA equipment] |  | 0 |  |  | 1 | 0
TOTAL NON STAFF | [6 empty] | 3175
[8 empty] | VAT | TOTAL inc. VAT
TOTAL COST | [6 empty] | 37948.75 | 7589.75 | 45538.5

## GANTT Chart
Task No. | Task | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Event/Public Talk |  | Total | Day rate (£) | Other (£) | Cost for task (£)
200
1 | Set up site | 1 | [10 empty] | Set up site | 1 | 200 |  | 200
2 | Mark out | 1 | [10 empty] | Mark out | 1 | 200 |  | 200
3 | Topsoil |  | 1 | [9 empty] | Topsoil | 1 | 200 | 300 | 500
4 | Trench 1 |  | 2 | 3 | 3 | 3 | 3 |  |  | 2 |  |  | Trench 1 | 16 | 3200 |  | 3200
5 | Outreach |  | 1 | 1 | 1 | 1 | 1 | 2 |  |  |  | 2.5 | Outreach | 9.5 | 1900 |  | 1900
6 | Drone | [6 empty] | 1 |  | 1 |  |  | Drone | 2 | 400 | 200 | 600
7 | Backfill | [9 empty] | 1 |  | Backfill | 1 | 200 | 300 | 500
8 | Close site | [9 empty] | 1 |  | Close site | 1 | 200 |  | 200
| Total person days | 2 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 3 | 2 | 2.5 |  | 32.5
Day rate
| 200 | 400 | 800 | 800 | 800 | 800 | 800 | 600 | 0 | 600 | 400 | 500 |  | 6500 | 6500 | 800 | 7300
| Machinery costs |  | 300 |  |  |  |  | 100 |  | 100 | 300 |  |  | 800
7300

## Risk Log
PROJECT RISK LOG |  | Great Linford Manor Park: Project Design for Supplementary Archaeological Investigation with Community Involvement
Risk no. | Description | Probability | Impact | Countermeasures | Est. time/cost | Owner | Date last updated
1 | Manual handling (HERAS fencing, gazebo, etc.) | Low | Medium | HERAS fencing to be transported and set-up by suitably trained staff, adhering to the requirements as set out in Parks Trust RA (DW026). Use of competent people to specify suitable temporary equipment. Use of competent people to supervise erection of gazebos. Regular checks during set up, during event and take down. Use of suitable loading ramps or trolleys where necessary. Training and briefing of site crews, stewards and volunteers. All gazebos/marquees and flags to be well tethered with adequate guys ropes and/or weights against strong wind conditions. In wind conditions more than 18 mph small gazebos/marquees are not to erected and are to be taken down if wind conditions exceed 18 mph. Gazebos/marquees to be made of fire retardant material. | 1 day, £600 | PL [Project Leader] | 2024-05-06
2 | Slips / trips / falls (uneven ground) | Low | Medium | Event manager will walk site prior to unloading fencing and materials, to identify any potential hazards. Only authorized personnel allowed in trenches; excludes the public. Sensible footwear and PPE to be worn. Routes in and out of trenches to be checked each morning. Trip hazards to be identified, highlighted and removed if possible. Participants to be briefed on expected behaviour within trench areas. Trenches to be closed at night with Heras fencing (locked at night). Sensible footwear and PPE to be worn at all times in trenches. Advisory signage to be in place. | 1 day, £0 | PL | 2024-05-06
3 | Vechicle movements | Low | High | All vehicle’s movements to be limited to a speed of <=5mph. Hazard lights to be on when moving vehicles and a banksman to be used to guide vehicle through the park. | 0 day, £0 | PL | 2024-05-06
4 | Mechanical excavation | Low | High | All mechanical excavation to take place in designated areas which will be contained via HERAS fencing. Specialised sub-contractor employed to undertake work (see separate RAMs and insurance). | 0 day, £0 | PL | 2024-05-06
5 | Working at Height | Low | Medium | Only authorized personnel allowed in trenches. Trenches to be closed at night with Heras fencing (locked at night). Sensible footwear and PPE to be worn at all times in trenches. Participants to be briefed on expected behaviour within trench areas. Advisory signage to be in place. | 0.5 days, £0 | PL | 2024-05-06
6 | Hand tools | Low | Low | All use of hand tools to be supervised by trained contractors, and to be included in the briefing for the public. | 0 day, £0 | PL | 2024-05-06
7 | Fire and Emergency | Low | Medium | First aid kits and extinguishers to be included at control point. Central control point to be advertised to all contractors, volunteers and as part of any briefing sessions. Trained first aider on site at all times. Radio and mobile phone communication to be used between Parks Trust and CA teams. Public open space so several emergency exists already in place. Parks Trust staff to ensure public are assisted in leaving park in case of emergency by stewarding. Emergency vehicle routes kept open if required. | 0.5 days, £100 | PL | 2024-05-06
8 | First Aid | Low | Low | Trained first aider on site at all times. First aid kit will be made available at central control point. | £0, £50 | PL | 2024-05-06
9 | Hygiene / welfare | Low | Medium | Toilets and washing facilities will be available on site for participants. Refreshments available at Central Control point. | 0.5 days, £1500 | FA [Field Arch.] | 2024-05-06
10 | Litter and waste | Low | High | Litter bags provided and emptied. Ensure regular checks to prevent build-up of waste, especially flammable and trade waste. Regular litter sweeps by volunteers wearing appropriate PPE. | 1 day, £0 | FA | 2024-05-06
11 | Extreme weather conditions | Medium | High | Weather forecast checked prior to event and throughout. Emergency access plan in place to clear site quickly and efficiently. Adequate first aid provision on site. Communication system in place. Use social media and website to issue advisory announcements e.g cover up and wear sunblock in sunny conditions. Drinking water available; hydrate and take shade breaks as required. Ensure storm plan liaison with suppliers and sub-contractors. Plan for removal of temporary structures in adverse conditions. Contingency plans for bad weather and water-logged ground. Sand bags (empty, ×50) stored on site in case of flooding; fill using spoil. Temporary structures to be well tethered and wind speeds checked. Windy conditions over 18mph temporary structures to be take down. | 1-5 days, £25 | PL | 2024-05-06
12 | Safeguarding young / venerable persons | Medium | High | Ensure competent suppliers and operating staff for all activities. Ensure separate operating procedures/method statements/H&S/ risk assessments for key activities and/or equipment as appropriate. Awareness of the legal and insurance restrictions on using young people as volunteers. First aid provision on site. Parents, guardians and other adult supervisors to remain with young people in their care. Lost children procedure in place. Family meeting point to be located at event control point. All key staff to be safeguarding trained and DBS checked. | 1 day, £72 | PL | 2024-05-06
13 | Crowd control (esp. during the Open day) | Medium | Medium | Site designed to allow good pedestrian flow. Likely audience profiles and behaviours considered in planning. Security and event team to patrol and monitor the site. Appropriate signage in place. Public Address system in place to make announcements as required. Weather forecast checked prior to event. Drinking water available. First aid provided by professional event medical company with at least 2 trained medical operatives supported by Parks Trust staff who are first aid trained. Effective communication amongst Events and Security Teams. Suitable fencing used where appropriate. Attendance numbers monitored entering and leaving critical areas. | 1.5 days, £50 | PL | 2024-05-06
14 | Presence of dogs | Low | Low | Site inspected before set-up and dog waste removed. Ensure dog owners keep their dogs on lead and under control. Provide adequate signage. Provision of First aid on site. | 0.5 days, £0 | FA | 2024-05-06
15 | Topographical features in the park | Low | Low | Refer to Site specific Risk Assessment in planning and event set-up. Grass cut before set-up and removed where possible. Site inspected before open to the public. Any features creating slip/trip/fall hazard to be marked or taped off. Emergency Access Plan in place. Contingency plan in place for waterlogged ground. | 0.5 days, £0 | PL | 2024-05-06

## Product Description
Product 1
Product No. | P1
Product Title | Social Media (MK1097)
Purpose of the Product | Engage with the public/local interest groups; to promote the Open Day
Composition | Provides details about the investigation: location, aims, interesting finds, Open Day dates
Derived from | Photos taken during the on-site investigation; short video clips of volunteers
Format and presentation | Posts on 'X' [formerly Twitter], CA's 'Community and Research' webpage and Facebook
Allocated to | Laura Pearson (Project Manager)
Quality criteria and method | Checked against standards and guidance; CIfA, 2107, p. 20-22
Person/group responsible for quality assurance | Rosanna Price (Digital Engagement Manager)
Person/group responsible for approval | The Parks Trust (Client)
Planned completion date | During Stage 1 (Field Investigation). LP to Draft immediately. Final agreed with 1 working day.
Product 2
Product No. | P2
Product Title | Local News Coverage (MK1097)
Purpose of the Product | Engage with the public; to promote the Open Day
Composition | Provides details about the investigation: location, aims, interesting finds, Open Day dates
Derived from | Interview with PL/volunteers; soundbites/brief from Digital Engagement Manger
Format and presentation | PDF article to feature digitally or in-print with a local news outlet; possibly an appearance on local TV
Allocated to | Laura Pearson (Project Manager)
Quality criteria and method | Undertaken according to CA Standards
Person/group responsible for quality assurance | Rosanna Price (Digital Engagement Manager)
Person/group responsible for approval | The Parks Trust (Client)
Planned completion date | During Stage 1 (Field Investigation). LP to Draft immediately. Final agreed with 3 working days.
Product 3
Product No. | P3
Product Title | Interim Reports (MK1097)
Purpose of the Product | Provide an overview of the fieldwork performance
Composition | Account of actions, decisions; assessment of success based on paradata
Derived from | Day Record Sheets, Cashe
Format and presentation | Word Document
Allocated to | (Project Leader)
Quality criteria and method | Checked against standards and guidance; CIfA, 2014a; HE, 2015
Person/group responsible for quality assurance | Laura Pearson (Project Manager)
Person/group responsible for approval | Adrian Scruby (Principal Fieldwork Manager)
Planned completion date | During Stage 1 (Field Investigation). PL to Draft by mid-July. Final agreed by end of July.
Product 4
Product No. | P4
Product Title | Specialist Reports (MK1097)
Purpose of the Product | Provide analysis of artefactual/environmental material
Composition | Datasets; methods, assemblage condition, provenance, identification/typology, dating; interpretation of data
Derived from | Artefactual/Environmental material and associated datasets
Format and presentation | Word Document
Allocated to | (Specialists, as appropriate)
Quality criteria and method | Checked against standards and guidance; APABE, 2017; AAF, 2007; CIfA, 2017; HE, 2011
Person/group responsible for quality assurance | Line managers / Senior Finds Officers
Person/group responsible for approval | Finds Managers
Planned completion date | During Stage 2 (Analysis). Specialists to Draft by mid-November. Final agreed by end of November.
Product 5
Product No. | P5
Product Title | Milton Keynes HER Entries
Purpose of the Product | Add/enhance detailed information about the historic environment of Great Linford
Composition | HER entries; metadata
Derived from | Fieldwork records (e.g. context sheets, GIS data), artefacts/ecofacts
Format and presentation | Online entries to the MK HER website
Allocated to | Grace Griffith (Publications Officer)
Quality criteria and method | Checked against standards and guidance; MKCC, 2024
Person/group responsible for quality assurance | Laura Pearson (Project Manager)
Person/group responsible for approval | Sarah Cobain (Project Assurance)
Planned completion date | During Stage 2 (Analysis). GG to Draft by mid-December. Final agreed by end of December.
Product 6
Product No. | P6
Product Title | OASIS Summary (MK1097)
Purpose of the Product | Provide information about MK1097 to MK HER and relevant national heritage organisations
Composition | Project details, location, creators, monument types, significant finds, archives, bibliography
Derived from | Fieldwork records (e.g. context sheets, GIS data), artefacts/ecofacts
Format and presentation | Online reporting form
Allocated to | Grace Griffith (Publications Officer)
Quality criteria and method | Checked against standards and guidance; OASIS, 2024
Person/group responsible for quality assurance | Laura Pearson (Project Manager)
Person/group responsible for approval | Sarah Cobain (Project Assurance)
Planned completion date | During Stage 2 (Analysis). GG to Draft by mid-December. Final agreed by end of December.
Product 7
Product No. | P7
Product Title | Project Report (MK1097)
Purpose of the Product | Present the project's archaeological findings, analyses results, and discusses interpretation
Composition | Background, aims/objectives, methods, results, material, discussion, archives, references, contexts, specialist reports
Derived from | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations
Format and presentation | Word Document; eventual conversion to PDF
Allocated to | Grace Griffith (Publications Officer); Laura Pearson (Project Manager)
Quality criteria and method | Checked against CA standards and standards and guidance; HE, 2015
Person/group responsible for quality assurance | Jo Barker (Post-excavation Manager)
Person/group responsible for approval | Sarah Cobain (Project Assurance)
Planned completion date | During Stage 2 (Analysis). GG to Draft by early January. Final agreed by mid-January.
Product 8
Product No. | P8
Product Title | Paper archive (MK1097)
Purpose of the Product | Collate all paper-based records related to the project and identified for long-term preservation
Composition | Site cache, context sheets, registers [drawings, photography, bulk finds, registered artefacts], photography, bound report, TOT
Derived from | All records compiled during the project
Format and presentation | Paper records in archival-quality boxes
Allocated to | Clare Bond (Archive Officer)
Quality criteria and method | Checked against standards and guidance; CIfA, 2014b; MKM, 2022;
Person/group responsible for quality assurance | Hazel O'Neill (Senior Archives officer)
Person/group responsible for approval | Milton Keynes Museum (Stakeholder)
Planned completion date | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
Product 9
Product No. | P9
Product Title | Digital Archive (MK1097)
Purpose of the Product | Collate all digital records related to the project and identified for preservation/dissemination
Composition | CAD files, databases, digital photographs, geophysical/other survey data, GIS files, images, spreadsheets, text files, 3D data; hardcopy list
Derived from | All digital data compiled during the project
Format and presentation | Digital files; relevant files burned to CD for MK Museum deposition
Allocated to | Clare Bond (Archive Officer)
Quality criteria and method | Checked against standards and guidance; CIfA, 2014b; ADS, 2024
Person/group responsible for quality assurance | Hazel O'Neill (Senior Archives officer)
Person/group responsible for approval | Milton Keynes Museum (Stakeholder)
Planned completion date | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
Product 10
Product No. | P10
Product Title | Artefact/Ecofact Archive (MK1097)
Purpose of the Product | Collate all artefactual/environmental material related to the project and identified for long-term preservation
Composition | Artefacts, human remains, animal bone, environmental samples
Derived from | Artefactual/environmental material recovered, subject to retention policy
Format and presentation | Artefactual material in archival-quality boxes
Allocated to | Clare Bond (Archive Officer)
Quality criteria and method | Checked against standards and guidance; CIfA, 2014b; MKM, 2022;
Person/group responsible for quality assurance | Hazel O'Neill (Senior Archives officer)
Person/group responsible for approval | Milton Keynes Museum (Stakeholder)
Planned completion date | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
Product 11
Product No. | P11
Product Title | Project Report on ADS
Purpose of the Product | Preserve data, and make it available for research, learning and teaching
Composition | Site report, as above (P7)
Derived from | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations, as above (P7)
Format and presentation | PDF uploaded to ADS website
Allocated to | Grace Griffith (Publications Officer)
Quality criteria and method | Checked against standards and guidance; ADS, 2024
Person/group responsible for quality assurance | Jo Barker (Post-excavation Manager)
Person/group responsible for approval | Sarah Cobain (Project Assurance)
Planned completion date | During Stage 3 (Archive Deposition). GG to Draft by early February. Final agreed by mid-February.
Product 12
Product No. | P12
Product Title | CA Reports Online
Purpose of the Product | Preserve data, and make it available for research, learning and teaching
Composition | Site report, as above (P7)
Derived from | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations, as above (P7)
Format and presentation | PDF and accompanying summary uploaded to CA 'Reports' webpage
Allocated to | Grace Griffith (Publications Officer)
Quality criteria and method | Published according to CA Standards
Person/group responsible for quality assurance | Jo Barker (Post-excavation Manager)
Person/group responsible for approval | Sarah Cobain (Project Assurance)
Planned completion date | During Stage 3 (Archive Deposition). GG to Draft by early February. Final agreed by mid-February.
Product 13
Product No. | P13
Product Title | Outreach Information Board (MK1097)
Purpose of the Product | Appraise visitors to the Park of the project's results
Composition | Description of the site/investigation/results, photographs, QR code to CA 'Community and Research' webpage
Derived from | Synthesis of the Project Report, photographs of the volunteers/Open Day, artefacts
Format and presentation | Large Posterboards
Allocated to | (Project Leader)
Quality criteria and method | Published according to CA Standards, to satisfy the DCMP (AHL-AhaCL, 2013)
Person/group responsible for quality assurance | Caroline Adams (Outreach and Community Engagement Officer)
Person/group responsible for approval | The Parks Trust (Client)
Planned completion date | During Stage 4 (Post-project Outreach). PL to Draft by early February. Final agreed by mid-February.
Product 14
Product No. | P14
Product Title | Outreach Evening Seminar (MK1097)
Purpose of the Product | Appraise the public/local residents/volunteers/local interest groups of the project's results
Composition | Description of the site/investigation/results, photograpghs, link to CA 'Community and Research' webpage
Derived from | Synthesis of the Project Report, photographs of the volunteers/Open Day, artefacts
Format and presentation | In-person seminar with online webinar live-stream - recorded, to be uploaded to the CA YouTube account
Allocated to | (Project Leader)
Quality criteria and method | Published according to CA Standards, to satisfy the DCMP (AHL-AhaCL, 2013)
Person/group responsible for quality assurance | Caroline Adams (Outreach and Community Engagement Officer)
Person/group responsible for approval | The Parks Trust (Client)
Planned completion date | During Stage 4 (Post-project Outreach). PL to Draft by early February. Final agreed by mid-February.

## Product Description Alt.
Product No. | Product Title | Purpose of the Product | Composition | Derived from | Format and presentation | Allocated to | Quality criteria and method | Person/group responsible for quality assurance | Person/group responsible for approval | Planned completion date
P1 | Social Media (MK1097) | Engage with the public/local interest groups; to promote the Open Day | Provides details about the investigation: location, aims, interesting finds, Open Day dates | Photos taken during the on-site investigation; short video clips of volunteers | Posts on 'X' [formerly Twitter], CA's 'Community and Research' webpage and Facebook | Laura Pearson (Project Manager) | Checked against standards and guidance; CIfA, 2107, p. 20-22 | Rosanna Price (Digital Engagement Manager) | The Parks Trust (Client) | During Stage 1 (Field Investigation). LP to Draft immediately. Final agreed with 1 working day.
P2 | Local News Coverage (MK1097) | Engage with the public; to promote the Open Day | Provides details about the investigation: location, aims, interesting finds, Open Day dates | Interview with PL/volunteers; soundbites/brief from Digital Engagement Manger | PDF article to feature digitally or in-print with a local news outlet; possibly a live appearance on local TV | Laura Pearson (Project Manager) | Undertaken according to CA Standards | Rosanna Price (Digital Engagement Manager) | The Parks Trust (Client) | During Stage 1 (Field Investigation). LP to Draft immediately. Final agreed with 3 working days.
P3 | Interim Reports (MK1097) | Provide an overview of the fieldwork performance | Account of actions, decisions; assessment of success based on paradata | Day Record Sheets, Cashe | Word Document | (Project Leader) | Checked against standards and guidance; CIfA, 2014a; HE, 2015 | Laura Pearson (Project Manager) | Adrian Scruby (Principal Fieldwork Manager) | During Stage 1 (Field Investigation). PL to Draft by mid-July. Final agreed by end of July.
P4 | Specialist Reports (MK1097) | Provide analysis of artifactual/enviromental material | Datasets; methods, assemblage condition, provinence, identification/typology, dating; interpretation of data | Artefactual/Environmental material and associated datasets | Word Document | (Specialists, as appropriate) | Checked against standards and guidance; APABE, 2017; AAF, 2007; CIfA, 2017; HE, 2011 | Line managers / Senior Finds Officers | Finds Managers | During Stage 2 (Analysis). Specialists to Draft by mid-November. Final agreed by end of November.
P5 | Milton Keynes HER Entries | Add/enhance detailed information about the historic environment of Great Linford | HER entries; metadata | Fieldwork records (e.g. context sheets, GIS data), artefacts/ecofacts | Online entries to the MK HER website | Grace Griffith (Publications Officer) | Checked against standards and guidance; MKCC, 2024 | Laura Pearson (Project Manager) | Sarah Cobain (Project Assurance) | During Stage 2 (Analysis). GG to Draft by mid-December. Final agreed by end of December.
P6 | OASIS Summary (MK1097) | Provide information about MK1097 to MK HER and relevant national heritage organisations | Project details, location, creators, monument types, significant finds, archives, bibliography | Fieldwork records (e.g. context sheets, GIS data), artefacts/ecofacts | Online reporting form | Grace Griffith (Publications Officer) | Checked against standards and guidance; OASIS, 2024 | Laura Pearson (Project Manager) | Sarah Cobain (Project Assurance) | During Stage 2 (Analysis). GG to Draft by mid-December. Final agreed by end of December.
P7 | Project Report (MK1097) | Present the project's archaeological findings, analyses results, and discusses interpretation | Background, aims/objectives, methods, results, material, discussion, archives, references, contexts, specialist reports | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations | Word Document; eventual conversion to PDF | Grace Griffith (Publications Officer); Laura Pearson (Project Manager) | Checked against CA standards and standards and guidance; HE, 2015 | Jo Barker (Post-excavation Manager) | Sarah Cobain (Project Assurance) | During Stage 2 (Analysis). GG to Draft by early January. Final agreed by mid-January.
P8 | Paper archive (MK1097) | Collate all paper-based records related to the project and identified for long-term preservation | Site cashe, context sheets, registers [drawings, photography, bulk finds, registered artefacts], photography, bound report, TOT | All records compiled during the project | Paper records in archival-quality boxes | Clare Bond (Archive Officer) | Checked against standards and guidance; CIfA, 2014b; MKM, 2022; | Hazel O'Neill (Senior Archives officer) | Milton Keynes Museum (Stakeholder) | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
P9 | Digital Archive (MK1097) | Collate all digital records related to the project and identified for preservation/dissemination | CAD files, databases, digital photographs, geophysical/other survey data, GIS files, images, spreadsheets, text files, 3D data; hardcopy list | All digital data compiled during the project | Ditigal files; relevant files burned to CD for MK Museum deposition | Clare Bond (Archive Officer) | Checked against standards and guidance; CIfA, 2014b; ADS, 2024 | Hazel O'Neill (Senior Archives officer) | Milton Keynes Museum (Stakeholder) | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
P10 | Artefact/Ecofact Archive (MK1097) | Collate all artefactal/envirmomental material relatied to the project and identified for long-term preservation | Artefacts, human remains, animal bone, environmental samples | Artefactual/environmental material recovered, subject to retention policy | Artefactual material in archival-quality boxes | Clare Bond (Archive Officer) | Checked against standards and guidance; CIfA, 2014b; MKM, 2022; | Hazel O'Neill (Senior Archives officer) | Milton Keynes Museum (Stakeholder) | During Stage 3 (Archive Deposition). CB to compile by late January. Final agreed by early February.
P11 | Project Report on ADS | Preserve data, and make it available for research, learning and teaching | Site report, as above (P7) | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations, as above (P7) | PDF uploaded to ADS website | Grace Griffith (Publications Officer) | Checked against standards and guidance; ADS, 2024 | Jo Barker (Post-excavation Manager) | Sarah Cobain (Project Assurance) | During Stage 3 (Archive Deposition). GG to Draft by early February. Final agreed by mid-Febraury.
P12 | CA Reports Online | Preserve data, and make it available for research, learning and teaching | Site report, as above (P7) | Fieldwork records, Specialist reports, Geomatics graphics, Illustrations, as above (P7) | PDF and accompanying summary uploaded to CA 'Reports' webpage | Grace Griffith (Publications Officer) | Published according to CA Standards | Jo Barker (Post-excavation Manager) | Sarah Cobain (Project Assurance) | During Stage 3 (Archive Deposition). GG to Draft by early February. Final agreed by mid-Febraury.
P13 | Outreach Information Board (MK1097) | Appraise visitors to the Park of the project's results | Description of the site/investigation/results, photograpghs, QR code to CA 'Community and Research' webpage | Synthesis of the Project Report, photographs of the volunteers/Open Day, artefacts | Large Posterboards | (Project Leader) | Published according to CA Standards, to satisfy the DCMP (AHL-AhaCL, 2013) | Caroline Adams (Outreach and Community Engagement Officer) | The Parks Trust (Client) | During Stage 4 (Post-project Outreach). PL to Draft by early February. Final agreed by mid-February.
P14 | Outreach Evening Seminar (MK1097) | Appraise the public/local residents/volunteers/local interest groups of the project's results | Description of the site/investigation/results, photograpghs, link to CA 'Community and Research' webpage | Synthesis of the Project Report, photographs of the volunteers/Open Day, artefacts | In-person seminar with online webinar live-stream - recorded, to be uploaded to the CA YouTube account | (Project Leader) | Published according to CA Standards, to satisfy the DCMP (AHL-AhaCL, 2013) | Caroline Adams (Outreach and Community Engagement Officer) | The Parks Trust (Client) | During Stage 4 (Post-project Outreach). PL to Draft by early February. Final agreed by mid-February.