University of Wales

Trinity Saint David

London

Project Management

Sustainable Community Café Development in Manchester

Student name: Silviya Stancheva

Student number: 2310452

Modul code: LCBB6006

Modul name: Project management

Lecturer name: Dr Zainab Atta

Table of Contents

Introduction	3

Aim, Objectives, and Scope of the Project	3

Aim	3

Objectives	3

Scope	4

Project Outputs (deliverables and other direct results)	4

Primary Deliverables	4

Secondary Outputs	5

Activities Required to Deliver the Outputs	6

Stage 1: Project Initiation	6

Stage 2: Project Planning	7

Stage 3: Project Execution	7

Stage 4: Monitoring and Control	7

Stage 5: Project Closure	7

Work Breakdown Structure (WBS)	8

WBS Outline for Sustainable Community Café Project	8

Deliverables and Milestones (Timeline)	9

Resource Usage (Personnel and Material)	10

Personnel Resources	10

Material Resources	11

Estimated Budget Allocation	12

Conclusion	12

References	13

Introduction

The proposed project is aimed at the development of Sustainable Community Cafe in Manchester which is designed to foster environmental awareness, social inclusion and economic sustainability. The cafe sector in the UK has been undergoing a stable development over the last few years, and sustainability is the main competitive edge (Pierre, 2025). Customers are getting more and more interested in environmentally friendly businesses that focus on the sourcing of products in their local areas, minimising waste products, and considering socially responsible supply chains (Bussel et al., 2022). The cafe will become a center of sustainable living that provides plant-based food and environmental practices workshops. The initiative is consistent with the Net Zero 2050 goal of the UK, which includes renewable energy infrastructure, recyclable products, and the minimum amount of waste (Burnett and Stewart, 2024). My role as project manager will include the implementation of project management techniques or methodologies, namely PRINCE2 and PMBOK principles, to plan, coordinate, and finalize the project within the time, scope, and budget constraints (PMI, 2021). The project plan will give a framework, deliverables, activities, resources and milestones that are required in executing the Sustainable Community Cafe in an effective manner as it shows how professional project management tools and techniques were applied.

# Aim, Objectives, and Scope of the Project

## Aim

To design and execute a sustainable community cafe in Manchester that is sustainable in view of environmental responsibility, local job creation and promotion of social interaction by means of sustainable activities.

## Objectives

- To build an environmentally-neutral cafe with renewable materials and energy-saving technologies within 12 months.

- To provide at least 10 residents with local employment opportunities by encouraging inclusivity and sustainable hospitality training.

- To form collaborations with local suppliers that will make sure that 80 percent of ingredients will be locally and ethically sourced.

- To engage local communities in sustainability-motivated community programmes that will bring not less than 1,000 participants every year.

- To attain BREEAM Good or better sustainability certification at the project completion.

## Scope

The project will involve site selection, cafe design and construction, staff recruitment and training, supplier engagement, marketing and community outreach, and project evaluation. It omits the post-launch financial performance monitoring, which will be under the operational management. The scope is geographically small to the Manchester city centre, which makes it accessible and visible. The project is a 12 months project with a budget of £250,000 that will be financed by the local grants and the private investors.

# Project Outputs (deliverables and other direct results)

The project outputs are the tangible outputs and the deliverables that are realized within the project lifecycle. Project Management Institute (PMI, 2021) defines these outputs as the visible manifestation of the project completion, but they are divided into primary and secondary deliverables.

## Primary Deliverables

Figure 1 Primary Deliverables

- Completed Sustainable Café Building: A fully functional eco-certified cafe with energy efficient lighting, renewable sources of power and sustainable furniture. The quality and environmental integrity is maintained by adhering to the BREEAM and UK environmental standards.

- Renewable Energy System: Solar panels and LED lighting will be installed to make the company partially or fully carbon neutral. Such a system will lower operation expenses and be in line with the Net Zero strategy of the UK (Burnett and Stewart, 2024).

- Staff Recruitment and Training Programme: It is proposed to recruit 10 local people and to provide them with the eco-friendly management of the hospitality business, waste minimisation and ethical sourcing.

- Local Supply Chain Network: Building relationships with farmers, coffee producers, and sustainable packaging suppliers in the region.

- Marketing and Launch Campaign: A strong promotional push on digital and traditional media to promote the sustainability ethos of the cafe and its grand opening.

## Secondary Outputs

Figure 2 Secondary Outputs

- Community Engagement Workshops: Monthly community workshops that acknowledge environmental awareness, no waste lifestyles, and healthy eating. Such events improve the social contribution and image of the cafe.

- Operational Policy Manuals: Preparation of Standard Operating Procedures (SOPs) explaining day-to-day workings, health and safety consideration and sustainability procedures.

- Evaluation and Impact Report: A detailed report of the performance of the cafe compared to the goals in terms of carbon footprint reduction, customer satisfaction, and community engagement in KPIs.

All these outputs contribute to the Triple Constraint Model (PMI, 2021) to provide a balance between scope, time, and cost and achieve high quality and stakeholder satisfaction. They also help achieve broader sustainability goals that are in line with the United Nations Sustainable Development Goals (SDGs), specifically, SDG 11 (Sustainable Cities and Communities) and SDG 12 (Responsible Consumption and Production).

# Activities Required to Deliver the Outputs

The activities are also planned based on the project life cycle stages, including initiation, planning, execution, monitoring, and closure (Lock, 2020). Each stage has mandatory tasks to be performed in order to deliver.

Figure 3 Project Life Cycle stages

## Stage 1: Project Initiation

It is the stage, which lays the basis of project success. It starts with feasibility study that evaluates the suitability of the site, cost analysis and environmental impact. The needs of the stakeholders will be gathered by conducting interviews and consulting the community groups, local authorities, and investors. The charter of the project will formalise the objectives, scope, and governance frameworks whereas a pre-project risk register will be used to identify possible risks like cost constraints, unavailability of suppliers, and delay in approvals.

## Stage 2: Project Planning

Planning phase transforms goals of the project into a roadmap. It entails the formulation of a comprehensive project plan, Work Breakdown Structure (WBS) and allocation of resources matrix. Engineers and consultants will contribute on design architectural plans and sustainability. At this level, the project team will also gain planning rights and regulatory approvals, develop procurement plans and quality management and communication plans.

## Stage 3: Project Execution

The execution step entails putting into practice all the activities planned. The physical development of the cafe, the use of renewable systems, and the finalisation of the interior design will be a part of the construction stage. Simultaneously, the HR manager will hire and train employees and the marketing team will initiate first-time brand awareness programs. Contracts with the suppliers will be formalised, and sustainable materials will be obtained. There will be close liaisons between contractors and the management of the project in order to prevent delays or quality failures.

## Stage 4: Monitoring and Control

At this phase, the project manager will be involved in managing performance using Gantt charts, progress meetings, as well as quality control inspection. Budgets compliant and schedule efficiency will be monitored with the help of such tools as Earned Value Management (EVM) (Fleming and Koppelman, 2016). Risk management will proceed by monitoring supply, cost, and labour risks. The change control procedures will rectify any deviations of the plan hence ensuring that the project plan stays consistent with the baseline plan.

## Stage 5: Project Closure

The last phase is concerned with the formal project completion and evaluation. An ultimate examination will be done to make sure that all deliverables are within the preset quality parameters. Upon receiving regulatory approvals as well as environmental certifications, the cafe will be transferred to operational management. This will be followed by a lessons-learned workshop to review project strengths, weaknesses and best practices in future initiatives. Finally, a project closure report will be used to summarise results over the objectives and suggest on future sustainable projects.

# Work Breakdown Structure (WBS)

A Work Breakdown Structure (WBS) breaks down the project into manageable parts that facilitate the allocation of resources, the progression of the project, and the cost control (Larson and Gray, 2021).

## WBS Outline for Sustainable Community Café Project

| Level 1 | Level 2 | Level 3 (Tasks) |
| --- | --- | --- |
| 1. Project Initiation | 1.1 Feasibility Study | Conduct environmental and market analysis |
|  | 1.2 Stakeholder Identification | Identify local partners, council, investors |
|  | 1.3 Project Charter | Draft and approve project charter |
| 2. Planning | 2.1 Site Design | Architectural design and layout |
|  | 2.2 Permissions | Apply for council permits |
|  | 2.3 Procurement Plan | Identify suppliers and contractors |
|  | 2.4 Financial Plan | Budget allocation and approval |
| 3. Execution | 3.1 Construction | Foundation, structure, utilities |
|  | 3.2 Interior Setup | Furniture, solar panels, kitchen equipment |
|  | 3.3 Recruitment | Hire and train staff |
|  | 3.4 Marketing Campaign | Social media, community events |
| 4. Monitoring & Control | 4.1 Performance Tracking | Weekly site reports, budget checks |
|  | 4.2 Risk Management | Update risk register, mitigate delays |
| 5. Closure | 5.1 Evaluation | Compare actual vs planned outcomes |
|  | 5.2 Handover | Transfer ownership and operational control |
|  | 5.3 Final Report | Document lessons learned |

Table 1 WBS Outline for Sustainable Community Café Project

This form allows the project manager to manage every work package and allocate duties efficiently.

# Deliverables and Milestones (Timeline)

The project will be run over a 12-month duration, and the milestones will be determined in accordance with a Gantt Chart approach (Burke, 2013).

| Phase | Key Activities | Deliverables | Milestone | Timeline |
| --- | --- | --- | --- | --- |
| Initiation | Feasibility study, stakeholder meeting | Feasibility report, stakeholder list | Approval of project charter | Month 1 |
| Planning | Design, budgeting, permissions | Approved design & budget | Planning consent granted | Months 2–3 |
| Execution – Construction | Building works, installation | Completed structure | Building completion certificate | Months 4–8 |
| Execution – Staffing | Recruitment & training | Team operational | Staff training completed | Months 7–8 |
| Execution – Marketing | Marketing campaign launch | Promotional content | Public awareness campaign live | Month 9 |
| Monitoring & Control | Quality assurance & performance reports | Progress reports | Risk mitigation report approved | Months 5–11 |
| Closure | Handover & final evaluation | Project report & lessons learned | Café opening ceremony | Month 12 |

Table 2 Deliverables and Milestones

Milestones are set strategically to track progress against time and cost baselines, based on the Earned Value Management (EVM) structure of performance control (Fleming and Koppelman, 2016).

# Resource Usage (Personnel and Material)

## Personnel Resources

The project manager, architect, site engineer, HR manager, marketing officer, sustainability consultant and the finance officer are the key personnel. The communication within the team will be done on weekly review meetings and online collaborative tools like Microsoft Project and Asana (Heldman, 2018). RACI chart will provide role responsibility and transparency.

| Role | Responsibility | Duration |
| --- | --- | --- |
| Project Manager | Overall project control, schedule management | 12 months |
| Architect & Engineer | Design, building compliance | 3 months |
| Construction Manager | Oversee building works | 6 months |
| HR Manager | Recruitment and staff training | 2 months |
| Marketing Officer | Campaign design and execution | 3 months |
| Sustainability Consultant | Ensure environmental compliance | 6 months |
| Finance Officer | Budgeting and reporting | Throughout |

Table 3 Personnel Resources

The personnel resources will be addressed with the help of a RACI matrix (Responsible, Accountable, Consulted, Informed) in order to understand roles and communication (Heldman, 2018).

## Material Resources

The procurement of material will focus on environmentally friendly materials like recycled timber, natural paints and biodegradable wrapping. The solar panels, energy-saving appliances, and other equipment will be obtained in the UK because the UK-based suppliers will minimise transport emissions. The entire amount is estimated to be £250,000, including 10% contingency allowability. A procurement will adhere to the UK Public Contracts Regulations (2015) as the ethical buyer.

| Category | Materials Required | Purpose |
| --- | --- | --- |
| Construction | Eco-bricks, recycled wood, insulation | Café structure |
| Equipment | Solar panels, kitchen appliances | Energy and service delivery |
| Furniture | Recycled tables, chairs | Café interiors |
| IT & POS Systems | Computers, point-of-sale software | Operations and transactions |
| Marketing Materials | Posters, banners, digital media | Promotion |

Table 4 Material Resources

Local suppliers will be given more importance by the procurement in an effort to lower carbon footprint and foster community activities. The sustainability criteria will be in accordance with ISO 14001 Environmental Management Standards (BSI, 2022).

## Estimated Budget Allocation

| Category | Estimated Cost (£) |
| --- | --- |
| Construction and Equipment | 150,000 |
| Staffing and Training | 40,000 |
| Marketing and Launch | 20,000 |
| Consultancy and Compliance | 25,000 |
| Contingency (10%) | 15,000 |
| Total | £250,000 |

Table 5 Estimated Budget Allocation

Variance analysis will be used to support budget monitoring and frequent financial reporting, which will ensure accountability.

# Conclusion

The Sustainable Community Cafe Project in Manchester offers a real-life case of how sustainability principles can be put to use to realize project management goals in terms of the environment and social impacts. The project plan also shows a well-organised process starting with initiation and finishing with closure with the help of established methodologies like PRINCE2, WBS, and EVM. The major deliverables will be carbon neutral cafe, trained employees, local supply chain, and programmes in community engagement. The 12-month proposal and resources will mean that the planning can be done realistically with a fixed budget of PS250,000. The aspect of sustainability that is integrated during the project is not only consistent with the priorities established by the UK society, but it also guarantees a social and environmental value in the long term. This plan will provide a powerful base towards implementation and operational sustainability by following effective project management models.

# References

BSI (2022). ISO 14001 - Environmental Management System (EMS). [online] BSI. Available at: https://www.bsigroup.com/en-GB/products-and-services/standards/ems-iso-14001-environmental-management-system/ [Accessed 7 Nov. 2025].

Burke, R. (2013). Project Management : Planning and Control Techniques. 5th ed. Hoboken, N.J.: Wiley ; Chichester.

Burnett, N. and Stewart, I. (2024). The UK’s Plans and Progress to Reach Net Zero by 2050. [online] House of Commons Library. Available at: https://commonslibrary.parliament.uk/research-briefings/cbp-9888/ [Accessed 7 Nov. 2025].

Bussel, L. van, Kuijsten, A., Mars, M. and Veer, P. van ’t (2022). Consumers’ perceptions on food-related sustainability: A systematic review. [online] ResearchGate. Available at: https://www.researchgate.net/publication/358546809_Consumers [Accessed 7 Nov. 2025].

Fleming, Q.W. and Koppelman, J.M. (2016). Earned Value Project Management - Fourth Edition. 4th ed. Project Management Institute.

Heldman, K. (2018). PMP : Project Management Professional Exam Study Guide. Indianapolis, Indiana: Sybex.

Kerzner, H. (2017). Project management: a Systems Approach to planning, scheduling, and Controlling. 12th ed. John Wiley & Sons, Inc.

Larson, E.W. and Gray, C.F. (2021). Project management: the Managerial Process. 8th ed. New York, Ny: Mcgraw-Hill Education.

Lock, D. (2020). Project Management. [online] Routledge. doi:https://doi.org/10.4324/9781315245911.

Pierre, D. (2025). Coffee Shop Industry: Market Statistics and Growth. [online] BusinessDojo. Available at: https://dojobusiness.com/blogs/news/coffee-shop-industry-statistics [Accessed 6 Nov. 2025].

PMI (2021). A guide to the project management body of knowledge: (PMBOK guide). 7th ed. Newtown Square, Pa: Project Management Institute.