Caitlain Davies

2203224

Strategic Sports Event Management (BMSM6006)

Assignment 1

Content

Part 1: Event Scoping and Feasibility                            Page 3 - 6

Part 2: Strategic Marketing Overview                            Page 7 - 9

Part 1:

A feasible event that Wales could host is an International Girls' Football Tournament, which is a viable sporting event. The competition is intended to increase participation in women's football by developing young players' talent and give them exposure to other countries and ensuring sustainability for the tournament to be replicated annually. The Football Association of Wales' (FAW) For Her strategy, which aims to double the number of women playing football to 20,000 by 2026 (FAW, 2024). This is in alignment with this event. Organising an international tournament encourages young girls to participate in the sport by providing inspiration and visibility. Harries, O. (2023) states Wales has demonstrated its capacity to oversee major events by hosting the men's UEFA Champions League Final at Cardiff's Principality Stadium in 2017. Wales has hosted qualifying matches for the 2024 tournaments leading up to the 2025 tournaments and has participated in the UEFA Women's Under-19 and Under-17 Championships. These events are essential for fostering female football potential and attracting international teams to Wales. An occasion like this would significantly raise the region's awareness of women's and girls' football. In line with initiatives by the Football Association of Wales (FAW) and Sport Wales, the idea supports Wales' goals to increase women's football participation and advance equality in sports. Sports Wales (2024) A 50% increase in female football involvement over the previous five years lends support to holding such an event. Wales would benefit strategically and significantly from hosting an international girls' football tournament, utilising its facilities, football culture, and governmental goals to promote women in sports. Making use of the top-notch facilities at establishments like Cardiff Metropolitan University and the University of South Wales (USW) guarantees access to the highest quality fields, training facilities, and accommodation (University of South Wales, 2022). These universities are perfect hosts since they already have connections with both elite and grassroots football programs so there is already ready an established connection.

The seven-day international girls' football competition in Cardiff is intended to be an exciting and captivating experience for both players and spectators. The 16 international teams will arrive at their accommodations, register, receive welcome packets, and go through orientation before the event starts. On the first day, the teams are introduced to the local environment and culture through a welcome meal and venue familiarization. On Day 2, the official opening ceremony and the start of the group stage matches mark the start of the first competitive activity. Community involvement will be emphasized throughout the competition, including educational seminars and local youth football clinics designed to motivate the upcoming generation of female athletes. On Day 5, teams will compete in their group matches before moving on to the semi-finals, where they will also attend skill-building and strategy training seminars. The finals, which include the third-place playoff and the championship match, will take place on Day 6 of the event. An awards ceremony will mark the event's conclusion, honoring the tournament's social and educational contributions in addition to its athletic accomplishments. In keeping with the Welsh Government's goal of fostering sports at the local level, post-event evaluations will evaluate the tournament's effectiveness and its long-term impact on boosting girls' football involvement.

Cardiff would attract athletes, families, and spectators if it hosted an international football event. Rimmer, Simon (2019), events such as the 2017 UEFA Champions League final brought in over 200,000 tourists, demonstrating the city's ability to successfully handle high-volume sports tourism. Comparable competitions might bring in a sizable sum of money from lodging, food, and local attractions. Supporters of these events typically promote local economies by spending money on accommodation, shopping, and transportation. According to Davies, Larissa (2016) Wales' main sporting events can generate millions of dollars in consumer expenditure, boosting regional companies and service providers. The setting up of temporary positions in logistics, catering, security, and event management would increase employment temporarily. Longer-term effects include better job opportunities and skill development for communities. Jones, Calvin (2019) states Cardiff's reputation as a city that hosts high-profile events would be strengthened. Successful competitions raise the city's brand abroad, attracting more bids for major sporting events and strengthening ties with regulatory organizations like FIFA and UEFA. Under the direction of policies meant to maximize economic effect, promote diversity, and advance sustainability, Wales has established a solid reputation for hosting important athletic events. To make sure these objectives are fulfilled, the Welsh Government works with Sport Wales, local authorities, and event planners. Prioritizing safety, guaranteeing accessibility for all participants, and putting ecologically friendly principles into practice are important policy requirements (GOV.WALES, 2023). Cardiff University provides top-notch facilities that can accommodate global gatherings. To manage access, obtain required permissions, and stick to compliance rules, event planners must work with campus authorities. Following Cardiff Council's rules for public areas and efficiently attending to community needs are part of this (Cardiff Council, 2023). Also states, public events require specific approvals, such as licensing for commercial operations like food stands and merchandise. To get these clearances and adhere to local laws, coordination with Cardiff Council is required. Maximum participation will be ensured by avoiding scheduling conflicts with national and international events, such as the Women's FA Cup or school holidays. A summer schedule maximizes attendance and player availability by fitting in with both the football off-season and academic breaks.

Partnerships with Cardiff Council, Sport Wales, and private sponsors can be used to secure financial support. Securing such support requires proving the event's compatibility with community objectives and long-term benefits. Events that increase participation and provide a lasting impact are frequently given priority when it comes to public funding (Sport Wales, 2022).

The Cardiff international girls' football tournament can make money in a number of ways, such as through ticket sales, sponsorships, and collaborations with nearby companies. Cardiff University can offer significant assistance as a host and partner thanks to its vast facilities and branding opportunities. The institution could support event features, including youth football workshops, player development initiatives, or matchday operations, to raise awareness of its academic and athletic offers. Local food businesses, such as Elliott's Produce, which specializes in providing fresh produce, can also collaborate with the event to provide catering, food for attendees and participants, and sponsorship of activities or prizes. These collaborations would improve ties among the local community while also supporting the tournament's objective of encouraging healthy living. Vendor fees, goods sales, and broadcasting rights might generate additional income. Considering the significance of encouraging physical activity and community involvement, collaborating with nearby companies and academic institutions will improve the whole experience and generate long-term benefits for the city and its partners.

Venue and Facility Costs: £20,000–£30,000

Accommodation and Travel: £128,000

Accommodation for 16 Teams: Assuming each team comprises 20 individuals (players, coaches, and staff), the total number of participants will be around 320 people. Accommodation will be needed for 6 nights and cost £96,000. Costs for budget hotels or university halls could range from £100 per person per week, to £32,000.

Staffing and Volunteers: £0

Volunteers (university students)

Insurance and Risk Management: £5,000–£10,000

Equipment and Supplies: £0

Provided by the Universities

Catering and Hospitality: £0

Working with a local food company, their business will be promoted on TV.

Technology and AV Equipment: £10,000–£20,000

Live Broadcasting and Streaming: Media coverage, match analysis, and live broadcasting will all require AV equipment. It may cost between £10,000 and £20,000 to rent broadcasting equipment, match-day scoreboards, and other technologies (Sport Wales, 2022).

Miscellaneous/Contingency: £10,000–£15,000

Total cost from: £165,000 – £200,000

It is both practical and strategically advantageous for Cardiff's Universities to host an international ladies' football competition. This tournament can have long-lasting social, economic, and athletic effects by adhering to national and international regulations, utilising Cardiff's demonstrated ability to host sizable events, and capitalising on the growing interest in women's football.

References list

FAW (2024) For Her Strategy. FAW [online] Available at https://faw.cymru/strategies/

Harries, O. (2023). Nineteen FAW Girls’ Academy players selected for UEFA Tournament - FAW. FAW. [online] doi:https://doi.org/101123719/2023-09 08_Girls_North_Wales_Academy_Headshots_NCM-0178-1024x538.

Sports Wales (2024). Transforming Women’s Football in Wales… and beyond. [online] Sport Wales. Available at: https://www.sport.wales/media-centre/latest-news/transforming-womens-football-in-wales-and-beyond/.

University of South Wales (2022). “Grassroots Football: Growing the Game in Wales.” Southwales.ac.uk, University of South Wales, 2020, exercise.research.southwales.ac.uk/blog/grassroots-football-growing-game-wales/.

Rimmer, Simon (2019). “20 Years of Economic Output to Celebrate.” Principality Stadium, 26 June 2019, www.principalitystadium.wales/2019/06/26/20-years-of-economic-output-to-celebrate/.

Davies, Larissa, and Themis Kokolakakis. Measuring the Social and Economic Value of Sport in Wales. 2016.

Jones, Calvin. “The Stadium and Economic Development: Cardiff and the Millennium Stadium.” European Planning Studies, vol. 10, no. 7, Oct. 2002, pp. 819–829, https://doi.org/10.1080/0965431022000013239. Accessed 6 Sept. 2019.

GOV.WALES (2023). First Minister Welcomes UEFA EURO 2028 Decision. GOV.WALES.

Cardiff Council (2023). Event Planning Guidelines for Cardiff. Cardiff Council.

Sport Wales (2022). Vision for Sport in Wales. Sport Wales

Part 2:

Attracting and keeping fans at an international girls' football tournament in Cardiff requires a thorough strategy that incorporates strategic market segmentation, a customized marketing mix, and measurable objectives. By including these components, the event is guaranteed to be in line with the more general objectives of community involvement, inclusivity, and participation.

Strategic marketing goals and techniques are essential to the international girls' football tournament's success because they draw crowds, involve local communities, and generate excitement for the occasion. Aiming to attracting 30,000 spectators over the course of the week is one of the event's main marketing goals, which can be accomplished through focused advertisements and collaborations with nearby football teams, schools, and sports organizations like Sport Wales. Increasing the number of girls playing football in Wales by 20% in a year is another important goal. This supports the objective of encouraging sustained participation in grassroots sports and using the event to have a good social impact. (Sport Wales, 2024). Another objective is utilizing channels like Instagram and TikTok will assist attract a younger, football-enthusiast audience, and gaining 3,000 new followers for associated social accounts and 7,000 social media mentions are essential for increasing the event's online visibility (Olly Social, 2024). Social media may be an effective marketing technique by generating a viral buzz, which will increase engagement with a wider fan base and expand the event's reach beyond Cardiff. The event's positioning as a celebration of women's sports is in line with the goals of gender equity as well as the larger mission of inclusion-promoting organisations like Sport Wales and FIFA (GOV.WALES, 2023).

Considering the marketing mix and how it relates to my event. Over the course of seven days, 16 international teams compete in the football competition, which is the main offering. Live entertainment like halftime concerts or cultural performances, workshops, and player meet-and-greets are examples of supplemental items. The event also intends to offer an educational component, including lectures on football diversity and women's sports development. Its credibility is increased by holding the event at Cardiff University's state-of-the-art facilities. The university's facilities and strategic position make it the perfect setting for a top-tier competition, guaranteeing convenience for both domestic and foreign participants and advancing Wales as a center for the growth of inclusive sports (Cardiff University, 2023).

For the international girls' football tournament, striking a balance between accessibility and revenue generating requires a competitive price plan. Tickets for this event might range from inexpensive daily passes aimed at broader community engagement to free admission for kids under 12 to draw families. In addition to promoting involvement, group discounts for local clubs and schools support grassroots football projects. More privileged spectators looking for a premium experience may be drawn to premium VIP packages that offer unique seating and player interactions in order to accommodate a variety of audience segments. Furthermore, ticket-merchandise bundles and early-bird pricing can boost anticipation before the event and encourage advance sales. Masterman, G. (2014) states these tactics are in line with industry best practices for managing sporting events, where adaptable price structures increase attendance and revenue.

Cardiff University is the perfect place for an international girls' football competition because of its convenient location and strong infrastructure. Professional-level conditions are guaranteed for the event thanks to the university's top-notch sports facilities, which include a 33-acre sports field, indoor training facilities, and a cutting-edge fitness center. Cardiff's reputation for hosting successful sporting events adds to the tournament's legitimacy and appeal, and the campus's close proximity to the city's public transport system improves accessibility for both local attendees and foreign visitors (ISC Cardiff, 2023). Beyond the event itself, participants can enjoy Cardiff's vibrant culture and community-focused atmosphere, with sites like Cardiff Bay and Bute Park. Additionally, the university's ability to offer summer lodging and on-site food guarantees smooth logistical support for attendees and competitors (Cardiff University, 2024).

Young football fans and their families are the target of digital marketing on social media sites like Facebook, Instagram, and TikTok, which takes advantage of these platforms' capacity to reach demographics. Collaborations with nearby school systems and athletic associations such as Sport Wales or the Football Association of Wales (FAW) can broaden the event's marketing scope, encouraging community involvement and supporting more general policy objectives to boost young sports participation. (Sport Wales, 2024). Partnerships with Cardiff University and nearby companies increase exposure and provide sponsorship opportunities. Targeted initiatives, such as influencer partnerships and the usage of hashtags unique to an event to increase online awareness, might be supported by sponsors. For instance, partnering with BBC will maximise reach, this can be achieved by livestreaming matches and interacting with viewers on social media, particularly for those who are unable to attend in person. Including cultural elements in halftime performances or other entertainment broadens the attractiveness of the event and gives guests a more complete experience. The customer experience is improved by procedures like online ticketing, quick check-ins, and an unambiguous communication system. Schedules, real-time updates, and participatory elements like "Player of the Match" voting can all be found on an app. By incorporating efficient procedures, logistical obstacles are reduced, and attendees and participants may concentrate on the main excitement of the event. FIFA, (2024) highlights how crucial user-friendly ticketing systems are to increasing accessibility and happiness at the same time.

Personalized items like t-shirts, scarves, and water bottles generate enduring memories and marketing chances. Banners, photo booths, and branded backdrops are used to create interactive areas where fans can take pictures and post their experiences on social media during competitions like the FIFA World Cup. This kind of branding increases the event's internet presence and reaches a far wider audience than just those who are present. (Cardiff Metropolitan University, 2023; FIFA, 2023)

An international girls' football tournament in Cardiff needs to strategically combine market segmentation, focused positioning, and a well-designed marketing mix to draw and keep fans. Through the integration of digital promotion with community-focused partnerships and activities, the event may accomplish its dual goals of increasing girls' football participation and promoting community engagement. Frequent feedback systems, such post-event questionnaires, guarantee ongoing enhancement and event sustainability for subsequent iterations.

Reference list

Sport Wales (2024). Women and Girls in Sport. Retrieved from https://www.sportwales.org.uk

Olly Social (2024). The Impact of Social Media on the Sports Industry. Retrieved from https://www.olly.social/blog/post/the-impact-of-social-media-on-the-sports-industry

GOV.WALES (2023) Vision for Sport in Wales: Policy Framework. Available at: https://gov.wales.

Cardiff University (2023) Sports Facilities Overview. Available at: https://www.cardiff.ac.uk.

Masterman, G. (2014). Strategic Sports Event Management: An International Approach. Routledge.

Cardiff University (2024). Conferences and Summer Facilities. Retrieved from https://www.cardiff.ac.uk

International Study Centre (ISC) Cardiff (2023). Cardiff: A Great Place to Live and Study. Retrieved from https://isc.cardiff.ac.uk

FIFA (2024). Apply for Tickets. Retrieved from fifa.com

Cardiff Metropolitan University. (2023). Event Planning and Branding Strategies. Retrieved from cardiffmet.ac.uk

FIFA. (2023). FIFA World Cup 2026 Official Brand Unveiling. Retrieved from fifa.com