## Concrete Slab
Method Statement
Job Title; | SA1 Caretakers home
Date- | 01.05.05.2020
Description of Works | Suspended Concrete Beam And Block floor
Task- | Lay Concrete Slab
Duration- | Day
Location- | GF
Supervision- | Head Ganger and Site Agent
Plant/ Equipment | Roller and excavator
Materials | Concrete- Jabfill- Timber
Assessment of Risk | High
Access | Available
Noise/ Manual Handling | Both Present

## Door and windows
Method Statement
Job Title; | SA1 Caretakers home
Date- | 01.05.05.2020
Description of Works | Fitting of windows and doors
Task- | As Above
Duration- | 1 day
Location- | Exterior
Supervision- | N/A
Plant/ Equipment | Glue Guns. Hand tools
Materials | PVC
Assessment of Risk | Low
Access | Available
Noise/ Manual Handling | Manual Handling

## Roof
Method Statement
Job Title; | SA1 Caretakers home
Date- | 01.05.05.2020
Description of Works | Roof Consturction
Task- | Lay roof tiles
Duration- | 2 days
Location- | Roof of construction
Supervision- | Site agent
Plant/ Equipment | Hand Tools
Materials | Slate covering, timber
Assessment of Risk | Low
Access | Available
Noise/ Manual Handling | Manual Handling