## Sheet1
Start
0 | 0 | 35 | 35 | 0 | 49 |  | 49 | 20 | 67 |  | 67 | 20 | 76
Documentation and prep |  |  | Inspection |  |  |  | Climatic testing |  |  |  | Handling drop desting
35 | 35 | 35 | 35 | 14 | 49 |  | 69 | 18 | 87 |  | 87 | 9 | 96
35 | 0 | 49 | 47 | 0 | 96 | [5 empty] | 96 | 0 | 105 | 105
Vibration paperwork, prep & setup |  |  | Vibration testing | [7 empty] | Post trial inspection |  |  | Dispatch
35 | 14 | 49 | 49 | 47 | 96 | [5 empty] | 96 | 9 | 105
Key: | [7 empty] | Float
|  |  | Critical Path Analysis (CPD) |  |  | Early start |  |  |  | Early finish
Activity
[6 empty] | Late start |  |  |  | Late finish
Duration