Project Plan

Waste Removal and Storage Optimisation Project

Churchill Group (One Cabot Square, Canary Wharf)

Student Name: Hristina Veskova

Student Number: 2328970

Module: Project Management (LCBB6006)

Lecturer: Dr Zainab Atta

Table of Contents

Executive Summary	3

1. Introduction	3

1.1 Project Management Approach	3

2. Aim, Objectives and Scope	3

2.1 Aim	3

2.2 Objectives	4

2.3 Scope	4

3. Project Outputs and Deliverables	4

4. Activities Required to Deliver the Outputs	5

5. Work Breakdown Structure (WBS)	5

6. Deliverables, Milestones and Timeline	7

7. Resource Requirements	7

8. Stakeholders	8

9. Risk Assessment	8

10. Budget Estimation	8

11. Sustainability Considerations	9

12. Conclusion	9

References	9

# Executive Summary

This report sets out a project plan for the Waste Removal and Storage Optimisation Project carried out by my employer, Churchill Group, at One Cabot Square, Canary Wharf. The aim of the project is to improve storage efficiency, tidy up the workplace and support the organisation’s sustainability goals by removing, recycling and redistributing redundant equipment and materials. Working as the Operations Supervisor, I act as the project manager for the work: I coordinate the inventory assessment, identify what can be reused or must be disposed of, and raise the Purchase Orders (POs) that get the work approved and paid for.

The project is scheduled to run over one month with an approved budget of £15,000, including a contingency. It tackles three everyday problems - overcrowded storage areas, unused equipment and poor use of space - that have built up over time and now create health and safety risks. The plan that follows breaks the work down into clear deliverables, a work breakdown structure, a timeline of milestones and a resource list, so the team knows exactly what to do, by when and with what.

# 1. Introduction

Good project management is what keeps a piece of work on time, on budget and at the right quality. It gives a team a structured way to plan the work, share out resources, manage risk and check that the end result actually meets the objectives that were set (PMI, 2021). Even a fairly small, one-month project benefits from being planned properly rather than tackled on the fly.

Churchill Group provides integrated facilities management services to clients across several sectors, including financial institutions in Canary Wharf. At One Cabot Square, the back-of-house storage areas had gradually filled up with redundant materials: obsolete equipment, unused cleaning chemicals, broken trolleys and outdated machinery. These items took up valuable space, blocked walkways, created health and safety concerns and made day-to-day operations slower than they needed to be.

To deal with this, Churchill Group set up the Waste Removal and Storage Optimisation Project. The work focuses on identifying what is no longer needed, arranging recycling or safe disposal, and reorganising the remaining storage so it is easier and safer to use. As Operations Supervisor I lead the project on the ground - carrying out inventory checks, coordinating with the waste contractor and raising the Purchase Orders that authorise the spend. This document is the plan for that project.

## 1.1 Project Management Approach

Because the project is short and the deliverables are well defined, it is managed using a straightforward predictive (waterfall) approach: the phases run broadly in sequence, with each one signed off before the next begins (Larson and Gray, 2021). The plan draws on standard project management tools - a work breakdown structure to organise the work, a Gantt chart to schedule it, a risk register to control uncertainty and a simple cost breakdown to track spend. The supervisor acts as project manager throughout, giving a single point of accountability for time, cost and quality, which is one of the principles emphasised in the PMBOK Guide (PMI, 2021).

# 2. Aim, Objectives and Scope

## 2.1 Aim

The aim of the project is to improve storage efficiency and waste management at One Cabot Square by removing, recycling and redistributing redundant equipment and materials, creating a safer and better organised working environment.

## 2.2 Objectives

The project objectives are SMART - specific, measurable and time-bound - so that success can be judged clearly at the end:

- Identify and classify all redundant equipment and materials within the first week.

- Remove and dispose of waste safely and in line with regulations.

- Increase usable storage capacity and improve how the space is organised.

- Reduce health and safety risks in the storage areas.

- Support sustainable waste management by recycling wherever possible.

- Complete the project within the one-month schedule.

- Deliver the project within the approved budget of £15,000.

## 2.3 Scope

Setting a clear scope prevents “scope creep”, where extra work quietly gets added and pushes the project over time and budget (Larson and Gray, 2021). The table below shows what is in and what is out.

| In scope | Out of scope |
| --- | --- |
| Inspection of storage areas | Major building refurbishment |
| Inventory assessment and classification | Structural modifications |
| Removal of obsolete equipment | Buying new storage facilities |
| Recycling of reusable materials | Long-term facilities redesign |
| Safe disposal of hazardous/unusable items | Refurbishing other floors of the building |
| Coordination with the waste contractor |  |
| Raising and approving Purchase Orders |  |
| Final cleaning and storage reorganisation |  |

# 3. Project Outputs and Deliverables

The outputs are the tangible things the project produces - the results the client can see and check at the end. Listing them up front makes it clear what “done” looks like (PMI, 2021). The main deliverables and direct results of this project are:

- A completed inventory and classification report listing every item and whether it is to be kept, reused, recycled or disposed of.

- Cleared storage areas with all redundant equipment and materials removed.

- Approved Purchase Orders and waste transfer notes covering removal and disposal.

- Recycling and disposal certificates from the waste contractor, confirming compliant handling.

- A reorganised, labelled and fully usable storage layout.

- A project closure report summarising outcomes, final spend against budget and lessons learned.

Alongside these direct deliverables, the project produces wider results that are harder to put on a checklist but matter just as much: more usable floor space, reduced health and safety risk, and measurable progress against Churchill Group’s sustainability targets through landfill diversion. Defining the deliverables clearly at the start also makes it far easier to confirm at closure that the project has actually achieved what it set out to do, rather than relying on a vague sense that the areas “look tidier”. Each deliverable becomes a checkpoint the client can verify.

# 4. Activities Required to Deliver the Outputs

To produce those deliverables, the work is grouped into five main activities (or phases). Thinking in terms of activities first, before drilling down into individual tasks, keeps the plan organised and makes sure nothing is missed (Burke, 2013):

- Initiation and planning - confirming scope, budget and roles, and booking the contractor.

- Inventory and assessment - inspecting the storage areas and classifying every item.

- Procurement and approvals - raising and approving the Purchase Orders for removal and disposal.

- Removal, recycling and disposal - the physical clearance work with the contractor.

- Reorganisation and closure - cleaning, relabelling the space and closing the project.

# 5. Work Breakdown Structure (WBS)

A Work Breakdown Structure is a deliverable-oriented breakdown of the total scope of a project into smaller, more manageable pieces (PMI, 2021). It takes each main activity and splits it into sub-activities and then into individual tasks, so that work can be assigned, estimated and tracked. The WBS below uses a numbered “code of accounts” so every task has a unique reference.

| WBS | Sub-activity | Tasks |
| --- | --- | --- |
| 1.0 | Initiation & Planning | Confirm scope, budget and roles; appoint team; brief stakeholders |
| 1.1 | Project set-up | Hold kick-off meeting; agree responsibilities and reporting |
| 1.2 | Contractor selection | Request quotes; check accreditation; book the waste contractor |
| 2.0 | Inventory & Assessment | Survey all storage areas and classify items |
| 2.1 | Site inspection | Walk each storage area; photograph and log conditions |
| 2.2 | Classification | Tag items as keep, reuse, recycle or dispose; flag hazardous items |
| 2.3 | Inventory report | Compile classification report and removal list |
| 3.0 | Procurement & Approvals | Raise and approve Purchase Orders |
| 3.1 | Raise POs | Prepare POs for removal, recycling and disposal |
| 3.2 | Approval | Obtain manager sign-off; confirm contractor dates |
| 4.0 | Removal, Recycling & Disposal | Carry out the physical clearance |
| 4.1 | Removal | Remove obsolete equipment and redundant materials |
| 4.2 | Recycling | Separate and send reusable materials for recycling |
| 4.3 | Disposal | Dispose of hazardous/unusable items; collect transfer notes |
| 5.0 | Reorganisation & Closure | Reset the space and close the project |
| 5.1 | Cleaning & layout | Deep clean; relabel and reorganise storage |
| 5.2 | Closure | Final inspection; closure report; lessons learned |

# 6. Deliverables, Milestones and Timeline

Each phase has a clear deliverable and a milestone - a checkpoint that marks the completion of a key stage (Lock, 2017). Spreading these milestones across the four weeks makes progress easy to monitor and gives early warning if anything slips. The Gantt-style overview below shows when each phase runs.

| WBS | Phase / task | Deliverable | Milestone | Timeline |
| --- | --- | --- | --- | --- |
| 1.0 | Initiation & planning | Approved project brief | Project kicked off | Days 1–2 |
| 2.0 | Inventory & assessment | Inventory & classification report | Items classified | Days 3–7 |
| 3.0 | Procurement & approvals | Approved Purchase Orders | POs approved | Days 8–10 |
| 4.0 | Removal, recycling & disposal | Cleared areas; transfer notes | Waste removed | Days 11–22 |
| 5.0 | Reorganisation & closure | Reorganised storage; closure report | Project closed | Days 23–30 |

Gantt overview (each block = one week):

| Phase | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- |
| Initiation & planning | ██ |  |  |  |
| Inventory & assessment | ██ |  |  |  |
| Procurement & approvals |  | ██ |  |  |
| Removal, recycling & disposal |  | ██ | ██ |  |
| Reorganisation & closure |  |  |  | ██ |

# 7. Resource Requirements

Resources are the people, equipment and money needed to complete the work. Matching resources to each task makes sure the right people and kit are available at the right time and avoids bottlenecks (Kerzner, 2022). The table maps the main resources to each phase.

| Phase | Personnel | Material / other resources |
| --- | --- | --- |
| Initiation & planning | Operations Supervisor | PO system, project templates, meeting room |
| Inventory & assessment | Supervisor + 3 site employees | Inventory records, camera/tablet, PPE, labels |
| Procurement & approvals | Supervisor; approving manager | PO management tools, contractor quotes |
| Removal, recycling & disposal | 3 site employees; waste contractor | Waste containers, transport vehicles, PPE |
| Reorganisation & closure | Supervisor + 3 site employees | Cleaning equipment, shelving, labels |

In summary, the human resources are the Operations Supervisor (project manager), three site employees and an external waste contractor. The main physical resources are waste containers, cleaning equipment, transport vehicles and the storage areas themselves. The financial resource is the approved £15,000 budget, and the technological resources are the inventory records, communication systems and Purchase Order management tools.

# 8. Stakeholders

Stakeholders are the people and groups who affect, or are affected by, the project. Keeping them informed and on side is one of the biggest factors in whether a project succeeds (Maylor and Turner, 2022). The key stakeholders here are the client (the building occupier), Churchill Group management, the site team, the waste contractor and the building’s health and safety officer. Each gets the level of communication that suits their interest - management receives short progress updates against the milestones, the site team is briefed daily before work starts, and the client is notified before any activity that could affect their floors. Engaging the health and safety officer early is particularly important, because their sign-off is needed before hazardous items are moved.

# 9. Risk Assessment

Risk management means spotting what could go wrong, judging how likely and how serious it is, and planning how to deal with it before it happens (PMI, 2021). The register below lists the main risks, their rating and how each will be managed.

| Risk | Rating | Mitigation |
| --- | --- | --- |
| Hazardous materials handled unsafely | High | Use accredited contractor; PPE; follow disposal regulations |
| Removal disrupts daily operations | Medium | Schedule work in quieter periods; brief building users |
| Costs exceed budget | Medium | Fixed-price quotes; track spend; hold contingency |
| Delays in PO approval | Medium | Agree sign-off route early; flag approvals in advance |
| Recyclable items sent to landfill | Low | Segregate at source; require recycling certificates |

# 10. Budget Estimation

The approved budget is £15,000, including a contingency to cover unforeseen costs. Breaking the budget down by cost area keeps spending visible and controllable throughout the project.

| Cost area | Estimate (£) | Notes |
| --- | --- | --- |
| Waste contractor (removal & disposal) | 7,000 | Includes hazardous disposal |
| Recycling and transport | 2,500 | Segregation and haulage |
| Labour (site team time) | 2,500 | Allocated employee hours |
| Cleaning, shelving and labelling | 1,500 | Reorganisation materials |
| Contingency (~10%) | 1,500 | Unforeseen costs |
| Total | 15,000 |  |

# 11. Sustainability Considerations

Sustainability is now a core part of facilities management, not an optional extra. This project supports Churchill Group’s environmental goals by recycling reusable materials, diverting waste from landfill, reusing equipment where possible and disposing of hazardous items responsibly. Wherever an item can be redistributed to another site rather than scrapped, that option is taken first, which saves both money and resources. Recording how much waste is recycled versus sent to landfill also gives the client clear evidence of progress against corporate sustainability targets, which is increasingly expected by tenants in buildings like One Cabot Square. These figures feed into the closure report so the benefits are documented rather than assumed.

# 12. Conclusion

This plan sets out a clear, practical route to deliver the Waste Removal and Storage Optimisation Project at One Cabot Square. By defining the deliverables up front, breaking the work into a structured WBS, scheduling milestones across four weeks and matching resources to each task, the project gives the team a shared understanding of what needs to happen and when. With risks identified and a contingency built into the £15,000 budget, the project is well positioned to be delivered on time and on budget.

If it runs as planned, the result will be a safer, tidier and more efficient set of storage areas, less waste going to landfill, and a useful demonstration of how solid project management turns an everyday operational problem into a controlled, measurable piece of work.

# References

Burke, R. (2013) Project Management: Planning and Control Techniques. 5th edn. Chichester: Wiley.

Kerzner, H. (2022) Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 13th edn. Hoboken, NJ: Wiley.

Larson, E.W. and Gray, C.F. (2021) Project Management: The Managerial Process. 8th ed. New York: McGraw-Hill.

Lock, D. (2017) Project Management. 10th edn. Abingdon: Routledge.

Maylor, H. and Turner, N. (2022) Project Management. 5th edn. Harlow: Pearson.

Project Management Institute (PMI) (2021) A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th edn. Newtown Square, PA: Project Management Institute.