## Substructure and Superstructure
Schdeule of Works for Substructure
Check existing services
Set out site
Total excavation of site for foundations and drainage
Set out for piling
Pile excavation
Piling works to phase 1
Raft - Underslab and driange works
Install DPM
Placement of Slab
Schdeule of Works for Superstructure
Crane into positon
Install base plates
Steel frame arrives to site
Errect steel frame
Precast elevator shafts craned in and installed
Precast stairs craned in and installed
Precast concrete floors craned in and installed to FF
Scaffold Lift
Replicate works for First floor to Second Floor
Replicate works for Second floor to Third Floor.
Replicate works for Third Floor and Fourth Floor
Installation of CLT Panels
Roof
Windows and Doors
Drop scaffolding
Take away Crane

## Ground Floor
Schedule of Works - Ground Floor
Room 1 & 2 - Entrance / Lobby / Gift Shop
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 3 - Plant Room and Bin Store
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 4 - Toilets
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Tiling
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 5 - Childrens Creche
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 6 - Under Stairs Storage / Cleaning Room
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 7 - Coffee Shop
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 8 - Kitchen
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Tiling
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings

## First Floor
Schedule of Works - First Floor Plan
Room 1 - Information Desk
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 2 - Storage and Admin
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 3 - Meeting Room
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 4 - Toilets
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Tiling
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 5 - Teaching Space
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 6 Poetry Performance Stage
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 7 - Study zone
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 8 - Flexible Meeting Space
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 9 - Interview Rooms/Workshops
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings

## Second Floor
Schedule of Works - Second Floor Plan
Room 1 - Library Archive
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 2 - Stock Room
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 3 - Chuldrens Library
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 4 - Toilets
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Tiling
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 5 - Quiet Room
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 6 - Study Zone
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 7 - Courtyard
External Lighting and Electrics
Floor finishes
Installation of External Furnishings and Fittings

## Third Floor
Schedule of Works - Third Floor Plan
Room 1 - Admin
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings
Room 2 - Quiet reading zone
First Fix M&E
First Fix Carpentry
Plasterbaording and Plastering
Second Fix M&E
Second Fix Carpentry
Full Decoration
Floor Finishes
Full Clean
Installation of Furnishings and Fittings