EVENT PLAN EXAMPLE

Event: Small Conference on Digital Marketing

Date: March 15, 2024

Venue: City Convention Center

Objective:

To bring together digital marketing professionals to discuss the latest trends and strategies in the industry.

Event Plan:

Pre-Event Planning Phase (3-6 months prior):

- Define event objectives and target audience.

- Establish budget and secure funding/sponsorship.

- Select and book venue.

- Hire event staff (if needed).

- Develop event marketing plan.

- Create event website and registration platform.

- Identify and invite speakers.

- Arrange travel and accommodation for speakers.

Marketing and Promotion Phase (3 months prior - up to the event):

- Launch promotional campaigns through social media, email newsletters, and industry websites.

- Create promotional materials (flyers, posters, digital ads).

- Implement early bird registration discounts to encourage early sign-ups.

- Reach out to media outlets for event coverage.

- Monitor registration numbers and adjust marketing strategies as needed.

- Logistics and Operations Phase (1 month prior - up to the event):

Finalize event schedule and program.

- Arrange catering services.

- Order necessary equipment and supplies (audio-visual equipment, signage, name tags, etc.).

- Coordinate with vendors and suppliers.

- Conduct site visits to ensure venue readiness.

- Develop contingency plans for unforeseen circumstances.

- Event Execution Phase (Day of the event):

- Set up registration/check-in area.

- Arrange seating and signage.

- Coordinate with venue staff and vendors.

- Ensure technical equipment is functioning properly.

- Welcome attendees and speakers.

- Facilitate networking opportunities.

- Manage any issues or emergencies that arise.

- Collect feedback from attendees.

Post-Event Evaluation and Follow-Up (After the event):

- Gather feedback from attendees, speakers, and sponsors.

- Analyse event data and metrics (attendance, engagement, revenue).

- Evaluate the success of the event against objectives.

- Send thank you notes to speakers, sponsors, and attendees.

- Follow up with leads generated during the event.

- Begin planning for future events based on lessons learned.

Budget:

- Venue Rental: $X

- Catering: $Y

- Speaker Fees: $Z

- Marketing and Promotion: $A

- Equipment Rental: $B

- Staffing: $C

- Miscellaneous: $D

- Total Budget: $Total