APPLYING PROJECT MANAGEMENT TECHNIQUES

USING

THE CONSTRUCTION OF OFFICE BUILDING

AS

A PRACTICAL CASE STUDY

BY

ASOWATA EFEHI DAVIDSON

STUDENT ID: 2304469

TABLE OF CONTENT

Title -----------------------------------------------------------------------------------------------------------------i

Table of Content ------------------------------------------------------------------------------------------------ii

- Introduction ------------------------------------------------------------------------------------------------1

1.1 Background to the project------------------------------------------------------------------------------ 2

2.0 Construction to the Network Diagram/Gantt chart and critical Path ------------------------3

3.0 Role of Communication ---------------------------------------------------------------------------------10

4.0 Application of PERT Analysis and Risk Management Techniques -----------------------------11

5.0 Costs of the Individual Activities and Total Costs of the project ------------------------------14

6.0 Application of Crash Costing Techniques -----------------------------------------------------------15

7.0 Consideration of project Handover Issues ----------------------------------------------------------17

Conclusion -------------------------------------------------------------------------------------------------------19

References -------------------------------------------------------------------------------------------------------20

Appendices ------------------------------------------------------------------------------------------------------21

1.0 INTRODUCTION

  - Background to the Project

The construction of office buildings is a complex and multifaceted project, often serving as a significant investment in urban development and corporate infrastructure. Such projects typically encompass several stages, including planning, design, procurement, construction, and post-construction activities (Smith and Jones, 2023, p. 45). The process requires careful coordination between architects, engineers, contractors, and clients to ensure that the final product meets both functional and aesthetic needs while adhering to budget and timeline constraints (Davis, 2022, p. 78).

Over the years, advancements in construction technology, sustainability standards, and project management practices have greatly influenced the design and execution of office buildings. The integration of green building practices and energy-efficient systems has become more prevalent, driven by increasing environmental awareness and regulatory requirements (Taylor, 2023, p. 102). Additionally, the evolution of work culture and the rise of flexible office spaces have reshaped the functional layout of office buildings, prompting designers to incorporate open-plan layouts, collaborative workspaces, and advanced technological infrastructure (Johnson, 2021, p. 67).

Moreover, the construction of office buildings often faces challenges such as zoning laws, site limitations, and fluctuating market conditions. Effective project management, therefore, becomes crucial in navigating these obstacles and ensuring the successful completion of the project (White and Green, 2022, p. 59). As the demand for modern office spaces continues to rise, the construction of office buildings remains a dynamic and critical area of the real estate and construction industries.

  - Basis and Purpose of the Project

1.2.1 Basis of the Project.
The project of constructing an office building is based on addressing the growing demand for modern, efficient, and flexible workspace solutions. It aims to provide a physical structure that meets the evolving needs of businesses, accommodating various office functions such as private offices, collaborative areas, and spaces for technological integration. As organizations increasingly prioritize adaptability and sustainability in their workplace environments, the construction of office buildings is not merely a physical endeavor but also a response to these broader economic and societal shifts (Taylor, 2023, p. 89).

1.2.2 Purpose of the Project.
The purpose of undertaking this project stems from a combination of factors: the need to accommodate corporate growth, the desire to provide employees with conducive work environments, and the growing emphasis on environmental sustainability (Davis, 2022, p. 102). As businesses seek to attract and retain top talent, they recognize that the design of their office spaces plays a pivotal role in fostering productivity, innovation, and employee well-being (Johnson, 2021, p. 55). Furthermore, the construction process allows for the integration of energy-efficient technologies and green building practices, which align with global efforts to reduce carbon footprints and promote sustainable development (Smith & Jones, 2023, p. 67).

In essence, the project serves both an economic and environmental purpose, contributing to the revitalization of urban spaces while fulfilling the demand for contemporary, sustainable office buildings. It represents a forward-thinking approach to meeting the needs of businesses and the broader community (White and Green, 2022, p. 72).

2.0 CONSTRUCTION OF THE NETWORK DIAGRAM/GANT CHART AND CRITICAL PATH

Table 1: Schedule of Activity

| Activity | Description | Duration |  |  | Laborer | Skilled |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Optimistic (Day) | Most likely (Day) | Pessimistic (Day) |  |  |
| 0-1 | Buy Land | 2 | 5 | 8 | 3 | 3 |
| 1-2 | Initial Survey | 3 | 7 | 10 | 5 | 3 |
| 2-3 | Design and planning | 2 | 6 | 8 | 2 | 3 |
| 3-5 | Site Preparation | 3 | 6 | 8 | 3 | 2 |
| 5-8 | Foundation work | 2 | 5 | 7 | 3 | 1 |
| 8-9 | Structural Framing | 2 | 5 | 8 | 5 | 1 |
| 9-16 | Roofing | 3 | 6 | 10 | 4 | 2 |
| 16-29 | External Finishing | 2 | 6 | 10 | 2 | 1 |
| 3-4 | Soil Testing | 2 | 6 | 9 | 3 | 3 |
| 9-13 | Plumbing Rough-in | 2 | 4 | 6 | 2 | 3 |
| 9-14 | Electrical Rough-in | 2 | 5 | 9 | 5 | 1 |
| 14-16 | Conduit Installation | 4 | 8 | 10 | 6 | 1 |
| 3-6 | Environmental Review | 4 | 8 | 12 | 4 | 3 |
| 6-7 | Permit Approval | 4 | 7 | 11 | 4 | 3 |
| 7-10 | Lift Shaft Excavation | 3 | 6 | 9 | 2 | 1 |
| 10-11 | Lift Installation | 3 | 7 | 10 | 4 | 1 |
| 11-12 | Lift Testing | 4 | 8 | 11 | 6 | 2 |
| 12-15 | HVAC Installation | 4 | 7 | 9 | 2 | 3 |
| 15-17 | System Testing | 4 | 7 | 9 | 2 | 2 |
| 17-18 | Final Mechanical Approval | 4 | 8 | 10 | 2 | 3 |
| 18-19 | Utility Connections | 2 | 5 | 9 | 6 | 1 |
| 19-20 | Final External Review | 4 | 8 | 12 | 6 | 2 |
| 20-21 | Flooring | 3 | 6 | 8 | 2 | 2 |
| 21-22 | Ceiling Work | 2 | 6 | 8 | 6 | 1 |
| 22-23 | Interior Painting | 2 | 5 | 9 | 2 | 2 |
| 23-24 | Joinery Work | 4 | 8 | 10 | 6 | 3 |
| 24-25 | Lighting Installation | 4 | 7 | 11 | 2 | 3 |
| 25-26 | Security System | 3 | 5 | 7 | 5 | 1 |
| 26-27 | Cleaning | 2 | 4 | 6 | 2 | 1 |
| 27-28 | Furniture Installation | 2 | 4 | 8 | 2 | 1 |
| 28-29 | Landscaping | 3 | 5 | 9 | 5 | 1 |
| 29-30 | Commissioning | 4 | 7 | 10 | 5 | 2 |
| 30-31 | Documentation | 4 | 7 | 11 | 3 | 3 |
| 31-32 | Project Handover | 4 | 7 | 10 | 3 | 1 |

0

0

0

0

Start

5

7

6

6

6

5

8

0

6

26

26

18

18

3

110

24

86

0

110

86

24

5

8

115

86

29

0

12

12

2

1

5

5

0

0

0

0

0

6

5

5

4

8

7

6

7

8

0

54

54

11

46

46

0

0

39

39

10

7

33

33

0

4

34

115

9

86

86

86

125

14

13

38

16

133

47

125

38

87

12

6

8

6

6

5

23

106

106

0

0

0

0

101

101

22

21

95

95

20

89

89

8

5

0

81

81

18

76

76

0

68

68

17

19

7

7

0

15

61

61

0

0

130

130

27

8

7

5

4

26

0

126

126

121

121

25

0

0

114

114

24

4

5

7

7

7

32

160

160

0

0

0

0

0

31

153

153

146

146

30

139

139

29

134

134

28

Finish

Network Diagram

Table 2: For Gantt Chart Construction

| Activity | Start Day | Duration (Day) | End Day | Predecessor |
| --- | --- | --- | --- | --- |
| Buy Land | 1 | 5 | 5 | _ |
| Initial Survey | 5 | 7 | 12 | Buy Land |
| Design and planning | 12 | 6 | 18 | Initial Survey |
| Site Preparation | 18 | 6 | 24 | Design and planning |
| Foundation work | 24 | 5 | 29 | Site Preparation |
| Structural Framing | 29 | 5 | 34 | Foundation work |
| Roofing | 34 | 6 | 47 | Structural Framing |
| External Finishing | 47 | 6 | 139 | Roofing |
| Soil Testing | 18 | 6 | 24 | Initial Survey |
| Plumbing Rough-in | 34 | 4 | 38 | Foundation work |
| Electrical Rough-in | 34 | 5 | 39 | Foundation work |
| Conduit Installation | 39 | 8 | 47 | Electrical Rough-in |
| Environmental Review | 18 | 8 | 26 | Design and planning |
| Permit Approval | 26 | 7 | 33 | Environmental Review |
| Lift Shaft Excavation | 33 | 6 | 39 | Permit Aproval |
| Lift Installation | 39 | 7 | 46 | Lift Excavation |
| Lift Testing | 46 | 8 | 54 | Lift Intallation |
| HVAC Installation | 54 | 7 | 61 | Lift Testing |
| System Testing | 61 | 7 | 68 | HVAC Installation |
| Final Mechanical Approval | 68 | 8 | 76 | System Testing |
| Utility Connections | 76 | 5 | 81 | Final Mechanical Approval |
| Final External Review | 81 | 8 | 89 | Utility Connection |
| Flooring | 89 | 6 | 95 | Final External Review |
| Ceiling Work | 95 | 6 | 101 | Flooring |
| Interior Painting | 101 | 5 | 106 | Ceinling |
| Joinery Work | 106 | 8 | 114 | Interior Painting |
| Lighting Installation | 114 | 7 | 121 | Joinery Work |
| Security System | 121 | 5 | 126 | Lighting Installation |
| Cleaning | 126 | 4 | 130 | Security System |
| Furniture Installation | 130 | 4 | 134 | Cleaning |
| Landscaping | 134 | 5 | 139 | Furniture intallation |
| Commissioning | 139 | 7 | 146 | Landscaping |
| Documentation | 146 | 7 | 153 | Commissioning |
| Project Handover | 153 | 7 | 160 | Documentation |

3.0 ROLE OF COMMUNICATION

Effective communication plays a pivotal role in managing the construction of office buildings, ensuring that all project stakeholders such as architects, contractors, clients, and engineers are aligned in their objectives, timelines, and expectations. Clear and consistent communication is essential to the coordination of tasks, resolution of conflicts, and prevention of misunderstandings that can lead to delays, cost overruns, or subpar outcomes (White and Green, 2022, p. 93). In the context of construction projects, communication serves as the foundation for decision-making, problem-solving, and maintaining project momentum (Davis, 2022, p. 117).

Improved communication channels can directly enhance project performance by facilitating timely updates, ensuring the accurate flow of information, and creating an environment where feedback is regularly shared. In many construction projects, inefficiencies arise due to poor communication, leading to missed deadlines, inadequate resource allocation, or errors in design and execution (Smith and Jones, 2023, p. 74). Establishing streamlined communication practices such as regular meetings, project management tools, and clear reporting systems can help mitigate these issues by ensuring that all team members are informed and can respond proactively to challenges (Taylor, 2023, p. 106).

In the current situation, where the construction of office buildings is often subject to market fluctuations, regulatory changes, and environmental considerations, improved communication can lead to significant benefits. For instance, if there is a shift in regulations or unforeseen delays due to supply chain issues, effective communication between stakeholders allows for swift adaptations to the plan, reducing the impact on the overall timeline (Johnson, 2021, p. 62). Moreover, with the increasing reliance on technology in construction management, utilizing digital communication tools can provide real-time updates and improve collaboration among geographically dispersed teams (White and Green, 2022, p. 97).

By fostering a culture of open and transparent communication, project managers can ensure that everyone involved is on the same page, improving decision-making and overall project success. For example, when a contractor faces a delay or difficulty, a timely update through clear communication allows for early intervention, resource reallocation, or a revised schedule that minimizes the impact on the project's final delivery (Davis, 2022, p. 121). Additionally, communication helps establish trust between stakeholders, leading to smoother negotiations, faster resolution of disputes, and a more cohesive team dynamic, all of which contribute to the project's success (Johnson, 2021, p. 68).

4.0 APPLICATION OF PERT ANALYSIS AND RISK MANAGEMENT TECHNIQUES

4.1 The table below shows the PERT Analysis of the Expected Time.

Table 3

| Activity | Duration (Days) |  |  | PERT Results : Expected Time (Days) |
| --- | --- | --- | --- | --- |
|  | Optimistic | Most Likely | Pessimistic |  |
| 0-1 | 2 | 5 | 8 | 5.00 |
| 1-2 | 3 | 7 | 10 | 6.83 |
| 2-3 | 2 | 6 | 8 | 5.67 |
| 3-5 | 3 | 6 | 8 | 5.83 |
| 5-8 | 2 | 5 | 7 | 4.83 |
| 8-9 | 2 | 5 | 8 | 5.00 |
| 9-16 | 3 | 6 | 10 | 6.17 |
| 16-29 | 2 | 6 | 10 | 6.00 |
| 3-4 | 2 | 6 | 9 | 5.83 |
| 9-13 | 2 | 4 | 6 | 4.00 |
| 9-14 | 2 | 5 | 9 | 5.17 |
| 14-16 | 4 | 8 | 10 | 7.67 |
| 3-6 | 4 | 8 | 12 | 8.00 |
| 6-7 | 4 | 7 | 11 | 7.33 |
| 7-10 | 3 | 6 | 9 | 6.00 |
| 10-11 | 3 | 7 | 10 | 6.83 |
| 11-12 | 4 | 8 | 11 | 7.83 |
| 12-15 | 4 | 7 | 9 | 6.83 |
| 15-17 | 4 | 7 | 9 | 6.83 |
| 17-18 | 4 | 8 | 10 | 7.67 |
| 18-19 | 2 | 5 | 9 | 5.17 |
| 19-20 | 4 | 8 | 12 | 8.00 |
| 20-21 | 3 | 6 | 8 | 5.83 |
| 21-22 | 2 | 6 | 8 | 5.67 |
| 22-23 | 2 | 5 | 9 | 5.17 |
| 23-24 | 4 | 8 | 10 | 7.67 |
| 24-25 | 4 | 7 | 11 | 7.17 |
| 25-26 | 3 | 5 | 7 | 5.00 |
| 26-27 | 2 | 4 | 6 | 4.00 |
| 27-28 | 2 | 4 | 8 | 4.33 |
| 28-29 | 3 | 5 | 9 | 5.33 |
| 29-30 | 4 | 7 | 10 | 7.00 |
| 30-31 | 4 | 7 | 11 | 7.17 |
| 31-32 | 4 | 7 | 10 | 7.17 |
| Total Expected Time |  |  |  | 209.67 |

TE (Expected Time) = Do + 4Dm + Dp   where, Do = optimistic duration, Dm = most likely duration, and Dp = pessimistic duration
Total Expected Time = Summation of all Individual Activity Expected Time

4.2 Risk Management Techniques
In the context of constructing an office building, the application of risk management techniques is essential to anticipate, assess, and mitigate potential threats that could compromise the project’s objectives. Risks in such projects typically span across financial, legal, environmental, and operational dimensions. If unaddressed, these risks can lead to cost overruns, schedule delays, reputational damage, and legal liabilities, all of which can significantly impact the business's profitability and stakeholder confidence. These risks and their impacts are discussed below.

4.2.1 Financial Risks
Cost escalation due to material price volatility or poor budgeting may erode profit margins. For example, unexpected increases in steel or concrete prices can lead to substantial financial strain (Zou et al., 2017, p. 11).

4.2.2 Legal and Regulatory Risks.
Non-compliance with local zoning laws or environmental regulations can lead to fines or project halts, disrupting timelines and increasing legal costs (Hillson and Murray-Webster, 2017, p. 89).

4.2.3 Environmental Risks.
Risks, such as soil contamination or extreme weather events can delay construction and inflate costs for remediation or adaptive measures (Aven, 2016, p. 45).

4.2.4 Health and Safety Risks.
Accidents on-site can result in injury, legal action, and reputational damage, potentially stopping work and attracting penalties (Choudhry and Fang, 2008, p. 687).

4.3 Risk Management Models and Techniques.
To manage these risks effectively, structured frameworks and tools can be applied.

4.3.1 PMBOK Risk Management Process.
This includes risk identification, qualitative and quantitative analysis, risk response planning, and monitoring (PMI, 2021, p. 401). Through this process, project managers can develop a comprehensive risk register and response strategies.

4.3.2 SWOT Analysis
Used in the planning phase to identify internal strengths and weaknesses, and external opportunities and threats (Gido and Clements, 2018, p. 63).

4.3.3 Monte Carlo Simulation
Enables quantitative risk analysis by simulating different outcomes and assessing the probability of cost or schedule overruns (Chapman and Ward, 2011, p. 215).

4.3.4 Risk Breakdown Structure (RBS)
Categorizes risks systematically, making it easier to analyze and address different risk types (Hillson, 2003, p. 47).

4.3.5 PESTLE Analysis.
Analyzes external macro-environmental risks: Political, Economic, Social, Technological, Legal, and Environmental.

4.4 Measures to be taken to mitigate these risks

- Financial Contingency Planning: Allocate reserves to address cost overruns and lock in prices with suppliers via contracts.

- Legal Compliance Checks: Engage legal experts early in the project for regulatory due diligence.

- Environmental Assessments: Conduct thorough site assessments and integrate sustainability plans.

- Safety Training and Protocols: Implement robust health and safety programs, and conduct regular audits.

5.0 COSTS OF THE INDIVIDUAL ACTIVITIES AND TOTAL COSTS OF THE PROJECT

Table 4: The table below shows the costs of the individual activities and total cost of the project based on the resource requirements and estimation of costs for activities.

| Activity | Duration | Resource |  | Cost (£) |
| --- | --- | --- | --- | --- |
|  |  | Laborer | Skilled |  |
| 0-1 | 5 | 3 | 3 | 13,500 |
| 1-2 | 7 | 5 | 3 | 23,100 |
| 2-3 | 6 | 2 | 3 | 14,400 |
| 3-5 | 6 | 3 | 2 | 12,600 |
| 5-8 | 5 | 3 | 1 | 7,500 |
| 8-9 | 5 | 5 | 1 | 10,500 |
| 9-16 | 6 | 4 | 2 | 14,400 |
| 16-29 | 6 | 2 | 1 | 7,200 |
| 3-4 | 6 | 3 | 3 | 16,200 |
| 9-13 | 4 | 2 | 3 | 9,600 |
| 9-14 | 5 | 5 | 1 | 10,500 |
| 14-16 | 8 | 6 | 1 | 19,600 |
| 3-6 | 8 | 4 | 3 | 24,000 |
| 6-7 | 7 | 4 | 3 | 21,000 |
| 7-10 | 6 | 2 | 1 | 7,200 |
| 10-11 | 7 | 4 | 1 | 12,600 |
| 11-12 | 8 | 6 | 2 | 24,000 |
| 12-15 | 7 | 2 | 3 | 16,800 |
| 15-17 | 7 | 2 | 2 | 12,600 |
| 17-18 | 8 | 2 | 3 | 19,200 |
| 18-19 | 5 | 6 | 1 | 12,000 |
| 19-20 | 8 | 6 | 2 | 24000 |
| 20-21 | 6 | 2 | 2 | 10,800 |
| 21-22 | 6 | 6 | 1 | 14,400 |
| 22-23 | 5 | 2 | 2 | 9000 |
| 23-24 | 8 | 6 | 3 | 28,800 |
| 24-25 | 7 | 2 | 3 | 16,800 |
| 25-26 | 5 | 5 | 1 | 10,500 |
| 26-27 | 4 | 2 | 1 | 4,800 |
| 27-28 | 4 | 2 | 1 | 4,800 |
| 28-29 | 5 | 5 | 1 | 10,500 |
| 29-30 | 7 | 5 | 2 | 18,900 |
| 30-31 | 7 | 3 | 3 | 18,900 |
| 31-32 | 7 | 3 | 1 | 10,500 |
| Total Project cost |  |  |  | 490,800 |

Estimated costs:
Laborer = £300 per Day
Skilled = £600 per Day

The Project Costs are £900 per day

6.0 APPLICATION OF CRASH COSTING TECHNIQUES

To reduce the scheduled duration of the project which is 160 days as verified by the activities on the critical path as illustrated in the network diagram (chapter two) by seven (7) days, the following activities, along the critical path are considered for some clear reasons.

- Initial Survey (Activity 1-2): Employing drones and 3D scanning can speed up site assessments, reduce labour and enhance accuracy.

- Joinery Work (Activity 23-24): Lean construction principles can be applied to streamline workflows and minimize time waste.

- Lighting Installation (Activity 24-25): Small controls could be implemented in order to reduce energy consumption and operational costs.

- Landscaping (Activity 28-29): Spreading landscaping over phases allows budget allocation over time.

- Commissioning (Activity 29-30): Early commissioning involvement by integrating commission agents early in the design phase can identify system inefficiencies before construction.

6.1 Step by step Application of crashing costing techniques

Table 5

| Activity | Normal Duration, ND (Days) | Crash Duration, CD (Days) | Normal Costs, NC (£) | Crash Cost, CC (£) |
| --- | --- | --- | --- | --- |
| 1-2 | 7 | 5 | 23,100 | 30,900 |
| 23-24 | 8 | 6 | 28,800 | 38,300 |
| 24-25 | 7 | 6 | 16,800 | 21,600 |
| 28-29 | 5 | 4 | 10,500 | 14,500 |
| 29-30 | 7 | 6 | 18,900 | 40,700 |

Note: Crash Costs, CC are estimated

Table 6

| Activity | Normal Duration, ND (Days) | Crash Duration, CD (Days) | Normal Costs, NC (£) | Crash Costs, CC (£) | Crash Costs Increase (£) | Crash Cost Per Day (£) |
| --- | --- | --- | --- | --- | --- | --- |
| 1-2 | 7 | 5 | 23,100 | 30,900 | 7,800 | 3,900 |
| 23-24 | 8 | 6 | 28,800 | 38,300 | 9,500 | 4,750 |
| 24-25 | 7 | 6 | 16,800 | 21,600 | 4,800 | 4,800 |
| 28-29 | 6 | 5 | 10,500 | 25,000 | 14,500 | 14,500 |
| 28-30 | 7 | 6 | 18,900 | 40,700 | 21,800 | 21,800 |

Crash Cost Increase = CC – NC
Crash Cost per Day = CC – NC divided by ND - CD

Table 7: Crash Cost Sequence

| Activity | Crash Costs | Normal Duration, ND (Days) | Crash Duration, CD (Days) | Time Saved (ND – CD) (Days) | Cumulative Project Cost Increase (£) |
| --- | --- | --- | --- | --- | --- |
| 1-2 | 3,900 | 7 | 5 | 2 | +7,800 |
| 23-24 | 4,750 | 8 | 6 | 2 | +17,300 |
| 24-25 | 4,800 | 7 | 6 | 1 | +25,100 |
| 28-29 | 14,500 | 5 | 4 | 1 | +39,600 |
| 29-30 | 21,800 | 7 | 6 | 1 | +61,400 |

Crash Sequence is 1-2, 23-24, 24-24, 28-29, and 29-30
Cumulative Project Costs = ∑ (product of CC and (ND – CD))
                                             = £ 61, 400

Recall that, the total project cost before the reduction of duration by 7 is £490,800

Therefore, the total project costs after crashing = £ 490,800 + £ 61, 400
                                                                                       = £ 552, 200

Hence, the final cost of the project is £ 552,200

7.0 CONSIDERATION OF PROJECT HANDOVER ISSUES

The project handover phase of an office building construction is a critical stage that involves transferring responsibility from the construction team to the client or building management team. It marks the completion of construction and the transition to operations, making it essential to address several key issues to ensure a smooth handover. These issues include:

7.1 Compliance agreement and Documentation.
One of the primary concerns during handover is ensuring that all regulatory requirements have been met and that the building complies with local zoning laws, safety standards, and environmental regulations. Documentation such as occupancy certificates, permits, warranties, and inspection reports should be thoroughly checked and handed over to the client (Smith and Jones, 2023, p. 125). Any discrepancies or missing documentation can delay the handover process and may cause legal issues later on.

7.2 Quality Assurance and Defects Management
Ensuring that the building is finished to the agreed-upon quality standards is another critical issue. Any defects or incomplete work must be addressed before the formal handover. A comprehensive defects list, often called a snagging list, should be created, with all necessary corrective actions taken by the contractor before the project is handed over (Davis, 2022, p. 132). The client should be provided with clear guidelines on how to report and manage any future defects or maintenance issues.

7.3 Training and Operational Information: A successful handover requires providing the client with essential operational knowledge. This includes training for building management on the operation of systems such as HVAC, lighting, fire safety, and security. The operational manuals for all equipment, as well as maintenance schedules, should be thoroughly reviewed with the client to ensure the building can be effectively maintained (White and Green, 2022, p. 103).

7.4 Final Inspection and Walkthrough: A final inspection or walkthrough with the client and key stakeholders is crucial. This allows the client to verify that all aspects of the project meet their expectations and are functioning as required. It also provides an opportunity for both parties to discuss the building’s final condition and any last-minute concerns (Johnson, 2021, p. 84).

7.5 Financial and Contractual Closeout: The financial aspects of the project must also be finalized before handover. This includes ensuring that all payments have been made, final invoices are processed, and the contractor has fulfilled all contractual obligations. Any unresolved financial issues, such as change orders or retention amounts, should be settled as part of the handover process (Taylor, 2023, p. 109).

7.6 Building Systems and Technology Transfer: In today’s office buildings, many systems are highly automated and technologically advanced. The integration of building management systems (BMS), smart technologies, and security infrastructure requires careful attention. Ensuring that these systems are fully operational, tested, and properly handed over to the building management team is crucial for the smooth running of the building post-handover (Smith and Jones, 2023, p. 128). While that is being done, relevant instructions should be given on how to operate the various technological infrastructures in the building. For example, the lighting, heater, Air conditioner and electronics gargets, etc.

7.7 Post-Handover Support and Warranty Period: Finally, establishing clear post-handover support arrangements, including warranty periods, is essential. The contractor should outline the scope of warranty coverage and the process for reporting issues during the warranty period. This ensures that the client has recourse should any issues arise soon after handover (Davis, 2022, p. 135).

CONCLUSION

The construction of an office building which comprises thirty-two defined activities, from land acquisition to final handover should be successfully completed within a span of one hundred and sixty working days. Through comprehensive planning and execution, the project team would effectively utilize several key project management tools and techniques to ensure timely delivery and quality assurance.

A detailed network diagram and Gantt chart constructed, offers visual clarity on the sequence, duration, and dependences of the activities. These tools are instrumental in identifying the critical path, which enables focus monitoring and ensure the delays are avoided in the task directly influencing the overall time.

The application of PERT analysis facilitates a better understanding of activity time estimates under uncertainty, improving scheduling accuracy and supporting informed decision-making. In addition, risk management strategies are implemented throughout the project life cycle to proactively identify, assess, and mitigate potential risks, which contribute to smoother operation operations and resource allocation.

In conclusion, the work demonstrated effective integration of scheduling, resource management, costs control, and risk mitigation strategies, resulting in the successful construction and delivery of an office building within the planned duration. This serves as a practical example of disciplined project management execution from initiation to closure.

REFERENCES

Aven, T. (2016). Risk Assessment and Risk Management: Review of Recent Advances on Their

Chapman, C. & Ward, S. (2011). How to Manage Project Opportunity and Risk: Why Uncertainty

Choudhry, R.M. &amp; Fang, D. (2008). Why Operatives Engage in Unsafe Work Behavior: Investigating

CRC Press, p. 47.

Davis, L. (2022). Construction Project Management in Practice. McGraw-Hill, pp. 78-135.

Factors on Construction Sites. Safety Science, 46(4), p. 687.

Foundation. European Journal of Operational Research, 253(1), p. 45.

Gido, J. & Clements, J.P. (2018). Successful Project Management. 7th ed. Boston: Cengage Learning,

Hillson, D. & Murray-Webster, R. (2017). Understanding and Managing Risk Attitude. 2nd ed. London:

Hillson, D. (2003). Effective Opportunity Management for Projects: Exploiting Positive Risk. New York:

Johnson, R. (2021). Modern Office Design and Functionality. Wiley, pp. 55-84

Management can be a Much Better Approach than Risk Management. 3rd ed. Chichester: Wiley, pp.215-218.

p. 63.

PMI (2021). A Guide to the Project Management Body of Knowledge (PMBOK Guide). 7th ed. Newtown

Routledge, p. 89.

Smith, A., & Jones, B. (2023). Principles of Building Construction. Pearson, pp. 45-128.

Square, PA: Project Management Institute, pp. 400-410.

Taylor, K. (2023). Sustainability in Modern Architecture. Routledge, pp. 89-128.

White, T., & Green, E. (2022). Project Management in Construction. Cambridge University Press, pp. 59-103.

Zou, P.X.W., Zhang, G. &amp; Wang, J. (2017). Understanding the Key Risks in Construction Projects in China. P. 11

APPENDICES

- Activity List and Descriptions

| Activity | Description |
| --- | --- |
| 0-1 | Buy Land |
| 1-2 | Initial Survey |
| 2-3 | Design and planning |
| 3-5 | Site Preparation |
| 5-8 | Foundation work |
| 8-9 | Structural Framing |
| 9-16 | Roofing |
| 16-29 | External Finishing |
| 3-4 | Soil Testing |
| 9-13 | Plumbing Rough-in |
| 9-14 | Electrical Rough-in |
| 14-16 | Conduit Installation |
| 3-6 | Environmental Review |
| 6-7 | Permit Approval |
| 7-10 | Lift Shaft Excavation |
| 10-11 | Lift Installation |
| 11-12 | Lift Testing |
| 12-15 | HVAC Installation |
| 15-17 | System Testing |
| 17-18 | Final Mechanical Approval |
| 18-19 | Utility Connections |
| 19-20 | Final External Review |
| 20-21 | Flooring |
| 21-22 | Ceiling Work |
| 22-23 | Interior Painting |
| 23-24 | Joinery Work |
| 24-25 | Lighting Installation |
| 25-26 | Security System |
| 26-27 | Cleaning |
| 27-28 | Furniture Installation |
| 28-29 | Landscaping |
| 29-30 | Commissioning |
| 30-31 | Documentation |
| 31-32 | Project Handover |

PERT Analysis calculations

- TE (Expected Time) = Do + 4Dm + Dp   where, Do = optimistic duration, Dm = most likely duration, and Dp = pessimistic duration

TE (0-1) = (2 + 4(5) + 8)/6 = 30/5 = 5.00
TE (1-2) = (3 + 4(7) + 10)/6 = 41/6 = 6.83
TE (2-3) = (2 + 4(6) + 8)/6 = 34/6= 5.67
TE (3-5) = (3 + 4(6) + 8)/6 =35/6 = 5.83
TE (5-8) = (2 + 4(5) + 7)/6 = 29/6 = 4.83
TE (8-9) = (2 + 4(5) + 8)/6 = 30/6 = 5.00
TE (9-16) = (3 + 4(6) + 10)/6 = 37/6 = 6.17
TE (16-29) = (2 + 4(6) + 10)/6 = 36/6 = 6.00
TE (3-4) = (2 + 4(6) + 9)/6 = 35/6 = 5.83
TE (9-13) = (2 + 4(4) + 6)/6 = 24/6 = 4.00, etc.

Costs of the Individual Activities

Estimated costs:
Laborer = £300 per Day
Skilled = £600 per Day

The Project Costs are £900 per day

Activity (0-1) = Duration x (Number of Laborer x cost per day + Number of skilled x cost per day)
                        = 5 x (3 x 300 + 3 x 600) = 5 x (900 + 1800) = 5 x 2700 = £13,500

Activity (1-2) = 7 x (5 x 300 + 3 x 600) = 7 x (1500 + 1800) = 7 x 3300 = £23,100

Activity (2-3) = 6 x (2 x 300 + 3 x 600) = 6 x (600 + 1800) = 6 x 2400 = £14,400

Activity (3-5) = 6 x (3 x 300 + 2 x 600) = 6 x (900 + 1200) = 6 x 2100 = £12,600

Activity (5-8) = 5 (3 x 300 + 1 x 600) = 5 x (900 + 600) = 5 x 1500 = £7,500, etc.