## Sheet1
|  |  |  | September |  | October |  |  |  | November |  |  |  | December |  |  |  | January |  |  |  | February |  |  |  | March |  |  |  | April |  |  |  | May
Task | Start Date | End Date | Duration | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4 | Week 1 | Week 2 | Week 3 | Week 4
Find primary sources | SeptemberWeek 3 | SeptemberWeek 4 | 13 days | bar: September Week 3 to September Week 4
Find scholarly sources | SeptemberWeek 3 | OctoberWeek 2 | 24 days | bar: September Week 3 to October Week 2
Analyse primary sources | OctoberWeek 3 | FebruaryWeek 4 | 14 days | bar: October Week 3 to February Week 4
Analyse scholarly sources | OctoberWeek 3 | FebruaryWeek 4 | 14 days | bar: October Week 3 to February Week 4
Write introduction | MarchWeek 3 | MayWeek 1 | 35 days | bar: March Week 3 to May Week 1
Write Section 1 | MarchWeek 1 | MayWeek 1 | 50 days | bar: March Week 1 to March Week 2; March Week 4 to May Week 1
Write Section 2 | MarchWeek 1 | MayWeek 1 | 50 days | bar: March Week 1 to March Week 2; March Week 4 to May Week 1
Write conclusion | MarchWeek 3 | MayWeek 1 | 35 days | bar: March Week 3 to May Week 1
Bibliography | SeptemberWeek 3 | MayWeek 1 | 88 days
Draft 1 deadline | MarchWeek 3 | MarchWeek 3 | N/A | bar: March Week 3
Draft 2 deadline | AprilWeek 2 | AprilWeek 2 | N/A | bar: April Week 2
Submission Deadline | MayWeek 1 | MayWeek 1 | N/A | bar: May Week 1