## Roadmap
Timeline | Activity | Expected Outcome
Months 1–2 | Complete a GDPR gap analysis and data mapping exercise. | Identify personal data, processing activities and compliance gaps.
Months 3–4 | Conduct a DORA operational resilience assessment and review ICT risks. | Establish resilience requirements for critical business services.
Months 5–6 | Update company policies and provide GDPR and DORA awareness training. | Improve staff understanding of regulatory responsibilities.
Months 7–9 | Test incident response, disaster recovery and business continuity plans. | Ensure the organisation can respond effectively to cyber incidents.
Months 10–12 | Complete an internal compliance audit and address any outstanding issues before EU expansion. | Demonstrate readiness for regulatory compliance and reduce business risk.

## Risk Register
Risk | Likelihood | Impact | Recommended Mitigation
Cloud Misconfiguration | High | High | Implement Cloud Security Posture Management (CSPM), regular security audits and least-privilege access controls.
Supply Chain Compromise | Medium | High | Conduct vendor security assessments, contract reviews and continuous third-party monitoring.
AI Data Poisoning | Medium | High | Validate training data, monitor model outputs and implement AI governance controls.

## Ransomware
Phase | Actions
Detect | Identify unusual activity using SIEM, XDR and endpoint monitoring tools. Confirm whether ransomware is present and assess the scope of the incident.
Contain | Immediately isolate affected devices and servers from the network to prevent the ransomware from spreading to other systems. Disable compromised user accounts if necessary.
Communicate | Notify the CISO, CEO and Cyber Security Steering Committee. Inform relevant stakeholders and, where required, report the incident to regulators in line with GDPR and DORA requirements.
Eradicate | Remove malicious software, identify the attack method and apply security updates to prevent reinfection. Reset compromised credentials and strengthen security controls where necessary.
Recover | Restore business systems and data from secure immutable backups. Monitor restored systems to ensure normal business operations have resumed without signs of further compromise.
Review | Do a post-incident review to identify lessons learned, update security policies and improve incident response procedures to reduce the odds of similar attacks occurring in the future.

## Cyber Security Committee
Role | Responsibility
Chief Executive Officer (CEO) | Provides strategic leadership and approves major security initiatives.
Chief Information Security Officer (CISO) | Chairs the committee, reports on cyber risks and oversees the security programme.
Chief Financial Officer (CFO) | Approves budgets and evaluates the financial impact of security investments.
Chief Technology Officer (CTO) | Ensures security is integrated into technology and software development.
Data Protection Officer (DPO) | Oversees GDPR compliance and data protection responsibilities.
Head of Legal & Compliance | Advises on regulatory requirements, contracts and legal obligations.
Security Operations Manager | Provides updates on incidents, vulnerabilities and operational security performance.

## 12 month Roadmap
Quarter | Key Activities | Expected Deliverables
Q1 (Months 1–3) | Recruit the Information Security Unit, complete risk assessments, begin GDPR and DORA gap analysis, implement Multi-Factor Authentication (MFA). | Security team established, governance structure approved, MFA implemented for all staff.
Q2 (Months 4–6) | Deploy Identity and Access Management (IAM), Zero Trust Network Access (ZTNA), introduce new security policies and begin staff awareness training. | Zero Trust implementation begins, policies approved, staff training completed.
Q3 (Months 7–9) | Implement SIEM, XDR and Cloud Security Posture Management (CSPM), perform vulnerability assessments and ransomware response exercises. | Continuous monitoring operational, incident response tested, cloud security strengthened.
Q4 (Months 10–12) | Complete internal compliance audit, review KPIs, update the risk register and prepare for EU expansion. | GDPR and DORA readiness demonstrated, final security review completed and roadmap updated for Year Two.
ID | Name | Start | Finish | Duration | % Complete | Color | Notes
1 | Recruit the Information Security Unit, complete risk assessments, begin GDPR and DORA gap analysis, implement Multi-Factor Authentication (MFA). | 2026-01-01 | 2026-03-31 | 64 day | 25 | 31 | Security team established, governance structure approved, MFA implemented for all staff.
2 | Deploy Identity and Access Management (IAM), Zero Trust Network Access (ZTNA), introduce new security policies and begin staff awareness training. | 2026-04-01 | 2026-06-30 | 65 day | 25 | 211 | Zero Trust implementation begins, policies approved, staff training completed.
3 | Implement SIEM, XDR and Cloud Security Posture Management (CSPM), perform vulnerability assessments and ransomware response exercises. | 2026-07-01 | 2026-09-30 | 66 day | 25 | 331 | Continuous monitoring operational, incident response tested, cloud security strengthened.
4 | Complete internal compliance audit, review KPIs, update the risk register and prepare for EU expansion. | 2026-10-01 | 2026-12-31 | 66 day | 25 | 121 | GDPR and DORA readiness demonstrated, final security review completed and roadmap updated for Year Two.

## KPIs
KPI | Target
Multi-Factor Authentication adoption | 100% of employees
Security awareness training completion | 100% annually
Critical security vulnerabilities | Remediated within 14 days
Mean Time to Detect (MTTD) security incidents | Less than 30 minutes
Mean Time to Respond (MTTR) | Less than 4 hours
GDPR and DORA compliance milestones | Completed within the planned timeline