BA (Hons) Leadership and Management Skills in the Workplace

Jahanur Rashid

Student No. 2419759

Lecturer:   Kareem Sani

Project Management

module code: LCLM5003

Contents

PART A – PROJECT PROPOSAL POSTER	0

Part B: Reflection on Poster Feedback and Project Development	0

PART C – PROJECT MANAGEMENT PLAN	2

1. Introduction	2

2. Project Description	2

Project Goals	3

Project Objectives	3

Expected Outcomes	3

Project Management Methodology	4

3. Project Scope	4

Scope Statement	4

Inclusions	4

Exclusions	5

Assumptions	5

Constraints	5

Scope Justification	5

Scope Control	6

4. Work Breakdown Structure (WBS)	6

Work Breakdown Structure	6

Benefits of the WBS	7

5. Quad Chart	7

Quad Chart – Digital Modernisation Project	7

Importance of the Quad Chart	8

6. Gantt Chart	9

Project Schedule (6 Months)	9

Key Milestones	10

7. Stakeholder Analysis	10

Key Stakeholders	11

Power–Interest Matrix	11

Stakeholder Engagement Strategy	12

8. Resource Allocation	12

Human Resources	13

Financial Resources	13

Technology Resources	13

Resource Justification	14

9. Risk Analysis	14

Risk Register	14

Risk Assessment Matrix	15

Project Triangle (Iron Triangle)	16

Leadership and Risk Management	16

Global Project Considerations	17

10. Conclusion	17

Refrences:	18

Figure 1:Poster designed and created using Canva.

PART A – PROJECT PROPOSAL POSTER

# Part B: Reflection on Poster Feedback and Project Development

The feedback received from my tutor was helpful because it identified both the strengths of my project proposal poster and areas that required further development. The feedback showed that the poster was visually appealing, well organised and clearly linked to the transport hub closure scenario. A key strength was the clear justification for choosing digital modernisation of passenger flow and logistics coordination. The poster explained how digital technology could improve passenger experience, transport efficiency and communication during the hub closure.

Another positive area was the use of measurable project objectives. For example, the project aims to reduce passenger congestion by 30%, improve real-time information accuracy to 95%, and improve logistics coordination efficiency by 20%. The feedback helped me understand that measurable objectives make it easier to monitor project performance and evaluate whether the project has achieved its intended outcomes. Clear objectives are important for effective project planning and control (PMI, 2021).

The tutor also recognised the risk and trade-off section as a strength. The poster identified important risks, including cybersecurity threats, system failure, budget overruns and staff resistance. However, the feedback suggested that the risks and trade-offs required greater critical analysis and stronger justification of mitigation strategies. In response, the final project management plan includes a detailed risk register and a probability and impact matrix. Cybersecurity is identified as a very high risk because the project depends on digital platforms, cloud-based databases and real-time data sharing. Mitigation strategies include security audits, encryption, access controls, backup systems and incident response procedures. Effective risk management supports project decision-making and reduces uncertainty (PMI, 2021).

Another area for improvement was the need for greater application of project management tools and techniques. Although the poster clearly identified key stakeholders, it did not show their levels of power, interest or influence. Therefore, the final project management plan includes a stakeholder analysis and power–interest matrix. The Local Authority, Transport Operators and Project Team are classified as stakeholders who should be managed closely, while passengers and logistics companies should be kept informed. A stakeholder engagement strategy has also been included to explain suitable communication methods for different stakeholder groups.

The tutor also suggested including implementation timelines and stronger project management structures. In response, a six-month Gantt Chart and key milestones have been included in the final plan. The Work Breakdown Structure divides the project into manageable activities, while the Gantt Chart shows the project schedule and task dependencies. These tools support planning, resource allocation and project monitoring (Kerzner, 2022).

Finally, the feedback highlighted the need for greater use of academic literature. Therefore, the final project plan uses a wider range of project management sources, including PMI (2021), Kerzner (2022), APM (2023), Lock (2020), and Maylor and Turner (2022). Overall, the feedback helped me develop the poster proposal into a more detailed, analytical and evidence-based project management plan.

# PART C – PROJECT MANAGEMENT PLAN

## 1. Introduction

Projects are temporary activities undertaken to achieve specific objectives within defined time, cost, and quality constraints (Pinto, 2019). They have a clear beginning and end, dedicated resources, and measurable outcomes.

The closure of the central transport hub has created significant challenges, including passenger congestion, service delays, communication difficulties, and inefficient logistics coordination. These issues affect passengers, transport operators, local businesses, and authorities. To address these challenges, this project proposes the digital modernisation of passenger flow and logistics coordination through an integrated digital management system.

This project management plan outlines how the project will be delivered using recognised project management tools and techniques, including scope management, scheduling, stakeholder analysis, resource allocation, and risk management. Effective project management provides a structured approach to planning, monitoring, and controlling project activities, helping to ensure objectives are achieved within agreed constraints while meeting stakeholder expectations (Kerzner, 2022).

Digital modernisation was selected because it offers a faster and more cost-effective solution than redeveloping the transport hub or constructing a temporary transport system. Although it does not solve long-term infrastructure issues, it can deliver immediate improvements in passenger flow, communication, and logistics coordination within the six-month project timeframe. Therefore, it represents the most practical option for reducing disruption caused by the hub closure.

## 2. Project Description

The Digital Modernisation of Passenger Flow and Logistics Coordination Project aims to improve transport operations during the closure of the central transport hub. The project involves the development and implementation of a digital platform that provides real-time passenger information, traffic monitoring, logistics coordination, and operational decision support.

The project follows the project life cycle discussed in the module, including project identification, planning, implementation, monitoring, and evaluation (Maylor and Turner, 2022).

### Project Goals

The overall goal is to improve the efficiency and reliability of transport services while reducing disruption caused by the transport hub closure.

### Project Objectives

- The project aims to:

- Reduce passenger congestion by 30% within six months of implementation.

- Improve logistics coordination efficiency by 20% within six months.

- Increase the accuracy of real-time transport information to 95% within six months.

- Increase customer satisfaction levels by 25% within six months.

- Reduce operational delays by 20% through the use of digital monitoring and data analytics tools within the project period.

### Expected Outcomes

The successful implementation of the project is expected to deliver:

- Faster passenger movement.

- Improved transport scheduling.

- Better communication between stakeholders.

- Reduced operational delays.

- Enhanced passenger satisfaction.

The project supports organisational digital transformation objectives and contributes to sustainable transport management strategies (Department for Transport, 2023; European Commission, 2020).

### Project Management Methodology

Two commonly used project management methodologies are Waterfall and Agile. The Waterfall approach follows a linear sequence of activities (PeopleCert, 2023) and is most suitable when project requirements are clearly defined from the beginning. In contrast, Agile uses an iterative approach that allows continuous feedback, testing, and improvement throughout the project lifecycle (Schwalbe, 2019).

For this project, Agile is considered more suitable because the development of digital systems may require ongoing stakeholder input, system updates, and user testing. Agile enables changes to be incorporated more easily than the Waterfall approach, reducing the risk of delivering a system that does not fully meet user requirements (Schwalbe, 2019). However, Agile requires regular stakeholder involvement and effective communication to ensure project objectives remain aligned with organisational needs. Therefore, an Agile approach is considered the most appropriate methodology for the successful delivery of this project.

## 3. Project Scope

Project scope refers to all work required to deliver the project outcomes and defines project boundaries (PMI, 2021). Clear scope management helps prevent misunderstandings, delays, and budget overruns (Lock, 2020).

### Scope Statement

The project will design, develop, test, and implement a digital passenger flow and logistics coordination system for temporary transport operations.

### Inclusions

The project includes:

- Requirements gathering.

- System design and development.

- Digital passenger information displays.

- Mobile application integration.

- Data analytics dashboard.

- Staff training.

- Pilot testing.

- Full implementation.

- Performance evaluation.

### Exclusions

The project excludes:

- Construction of physical transport infrastructure.

- Purchase of buses, trains, or vehicles.

- Permanent transport hub redevelopment.

- Long-term city planning initiatives.

### Assumptions

- Funding will be approved.

- Technology suppliers will deliver on time.

- Staff will participate in training.

- Internet connectivity will be reliable.

### Constraints

- Fixed project budget.

- Six-month implementation period.

- Compliance with transport regulations.

- Limited operational disruption during implementation.

### Scope Justification

Clearly defining project scope reduces uncertainty and helps ensure resources are allocated efficiently. According to PMI (2021), scope management provides a foundation for planning, scheduling, budgeting, and risk management.

### Scope Control

Effective scope management is important to prevent scope creep, which occurs when additional requirements are added without proper approval. Scope creep can lead to delays, increased costs, and resource shortages (PMI, 2021). Therefore, any additional requirements requested by stakeholders after scope approval would be reviewed through a formal change-control process. This ensures that changes are assessed for their impact on project time, cost, quality, and resources before implementation.

## 4. Work Breakdown Structure (WBS)

The module identifies the Work Breakdown Structure (WBS) as a key planning tool that divides a project into manageable work packages and tasks (PMI, 2021).

### Work Breakdown Structure

Table 1: Work Breakdown Structure (WBS) for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Level 1 | Level 2 | Level 3 |
| --- | --- | --- |
| Digital Modernisation Project | Project Initiation | Business Case Development |
|  |  | Stakeholder Identification |
|  | Project Planning | Scope Definition |
|  |  | Risk Assessment |
|  |  | Resource Planning |
|  | System Development | Software Design |
|  |  | System Programming |
|  |  | Data Integration |
|  | Testing | System Testing |
|  |  | User Acceptance Testing |
|  | Implementation | Staff Training |
|  |  | System Deployment |
|  | Monitoring and Evaluation | Performance Monitoring |
|  |  | Project Review |

### Benefits of the WBS

The WBS improves planning accuracy, facilitates resource allocation, supports cost estimation, and enhances project monitoring (Kerzner, 2022). The module highlights that WBS activities should be definable, measurable, and manageable.

The WBS also supports communication among stakeholders by clearly identifying project deliverables and responsibilities. This WBS structure is suitable because it breaks the project into clear and manageable work packages, making it easier to allocate resources, monitor progress, and assign responsibilities. However, a limitation of the WBS is that it does not show task dependencies or activity timelines. Therefore, it must be used alongside a Gantt Chart to provide a complete view of project scheduling and task relationships.

## 5. Quad Chart

The module identifies the Quad Chart as a simple but effective planning and communication tool used to summarise project objectives, stakeholders, outcomes, and measures of success.

### Quad Chart – Digital Modernisation Project

Table 2: Quad Chart for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Aims and Objectives | Stakeholders |
| --- | --- |
| Improve passenger flow management | Local Authority |
| Reduce congestion levels | Transport Operators |
| Enhance logistics coordination | Passengers |
| Improve real-time communication | Local Businesses |
| Increase customer satisfaction | Technology Suppliers |

Table 3: Quad Chart for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Desired Results | Measures of Success |
| --- | --- |
| Reduced passenger congestion | 30% reduction in congestion |
| Improved service efficiency | Reduced waiting times |
| Better logistics coordination | Increased operational efficiency |
| Improved customer experience | 25% increase in satisfaction scores |
| Effective digital transformation | Successful system implementation |

### Importance of the Quad Chart

The Quad Chart provides a concise overview of the project and supports communication among stakeholders (APM, 2023). It helps project managers define project purpose, identify beneficiaries, establish success criteria, and monitor project outcomes.

The Quad Chart also supports strategic decision-making by ensuring that project activities remain aligned with organisational objectives and stakeholder expectations (APM, 2023). The Quad Chart is particularly useful for stakeholder communication because it presents key project information in a simple and accessible format. This enables stakeholders to quickly understand project objectives, expected outcomes, and success measures. However, the Quad Chart provides limited detail on project schedules, task dependencies, and resource requirements. Therefore, it should be used alongside more detailed planning tools such as the WBS and Gantt Chart to support effective project management.

## 6. Gantt Chart

A Gantt Chart is a project scheduling tool that visually represents project activities, timelines, dependencies, and milestones (Lock, 2020). The Week 2 module identifies Gantt Charts as an important project planning tool because they help project managers monitor progress and compare actual performance against planned activities.

### Project Schedule (6 Months)

Table 4: Gantt Chart for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Activities | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 |
| --- | --- | --- | --- | --- | --- | --- |
| Project Initiation |  |  |  |  |  |  |
| Requirements Analysis |  |  |  |  |  |  |
| Stakeholder Consultation |  |  |  |  |  |  |
| System Design |  |  |  |  |  |  |
| Software Development |  |  |  |  |  |  |
| Data Integration |  |  |  |  |  |  |
| System Testing |  |  |  |  |  |  |
| User Acceptance Testing |  |  |  |  |  |  |
| Staff Training |  |  |  |  |  |  |
| System Deployment |  |  |  |  |  |  |
| Monitoring & Evaluation |  |  |  |  |  |  |

### Key Milestones

Table 5: Project Milestones and Completion Schedule

| Milestone | Completion Month |
| --- | --- |
| Project Approval | Month 1 |
| Scope Sign-off | Month 2 |
| System Design Approved | Month 3 |
| Development Completed | Month 4 |
| Testing Completed | Month 5 |
| System Go-Live | Month 5 |
| Final Evaluation | Month 6 |

The Gantt Chart supports effective time management by providing a structured schedule for project activities. It also enables project managers to identify delays and take corrective actions when necessary (Kerzner, 2022). The use of milestones aligns with the WBS approach discussed in the module. The Gantt Chart also highlights dependencies between project activities. For example, system testing cannot begin until software development and data integration have been completed, while system deployment depends on the successful completion of user acceptance testing. Identifying these dependencies helps reduce scheduling conflicts and ensures that project activities are completed in the correct sequence (Kerzner, 2022).

## 7. Stakeholder Analysis

Stakeholders are individuals or groups who can affect or are affected by project outcomes (PMI, 2021). Effective stakeholder management improves project success by increasing support, reducing resistance, and enhancing communication (APM, 2023). The Week 3 module emphasises that stakeholder analysis should be conducted throughout the project lifecycle.

### Key Stakeholders

Table 6: Stakeholder Analysis Matrix for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Stakeholder | Interest | Influence | Priority |
| --- | --- | --- | --- |
| Local Authority | High | High | High |
| Transport Operators | High | High | High |
| Passengers | High | Medium | High |
| Logistics Companies | High | Medium | High |
| Technology Vendors | Medium | High | Medium |
| Local Businesses | Medium | Medium | Medium |
| Project Team | High | High | High |
| Regulatory Bodies | Medium | High | Medium |

### Power–Interest Matrix

Manage Closely (High Power, High Interest)

- Local Authority

- Transport Operators

- Project Team

Keep Satisfied (High Power, Low Interest)

- Regulatory Bodies

- Technology Vendors

Keep Informed (Low Power, High Interest)

- Passengers

- Logistics Companies

Monitor (Low Power, Low Interest)

- General Public

- External Observers

This stakeholder classification follows the power-interest model presented in Week 3 (PMI, 2021).

### Stakeholder Engagement Strategy

Table 7: Stakeholder Engagement Strategy for the Digital Modernisation of Passenger Flow and Logistics Coordination Project

| Stakeholder | Engagement Method |
| --- | --- |
| Local Authority | Monthly progress meetings |
| Transport Operators | Weekly coordination meetings |
| Passengers | Digital updates and surveys |
| Technology Vendors | Contract review meetings |
| Local Businesses | Community consultations |
| Regulatory Bodies | Compliance reporting |

Stakeholder engagement helps reduce project resistance and supports collaborative decision-making. According to PMI (2021), stakeholder satisfaction is a critical factor in project success. However, stakeholder interests may sometimes conflict. For example, transport operators may prioritise rapid system implementation to minimise service disruption, whereas regulatory bodies may focus on compliance and risk reduction, which could extend project timelines. Effective stakeholder management is therefore essential to balance competing expectations and support successful project delivery.

## 8. Resource Allocation

Resource planning ensures that sufficient human, financial, technological, and operational resources are available throughout the project lifecycle (Kerzner, 2022). The Week 2 module identifies resource planning as an essential element of project management.

### Human Resources

Table 8: Human Resource Requirements for Project Implementation

| Role | Responsibility |
| --- | --- |
| Project Manager | Overall project coordination |
| Business Analyst | Requirements gathering |
| Software Developers | System development |
| Data Analysts | Data integration and reporting |
| Testing Team | Quality assurance |
| Training Officer | Staff training |
| IT Support Staff | Technical maintenance |

The project manager will be responsible for planning, organising, directing, and controlling project activities. Effective leadership is important because project managers must balance technical skills with behavioural and leadership competencies (Müller, Drouin and Sankaran, 2021).

### Financial Resources

Table 9: Budget Breakdown for Project Implementation

| Cost Category | Estimated Cost (£) |
| --- | --- |
| Software Development | 120,000 |
| Hardware & Infrastructure | 50,000 |
| Staff Training | 20,000 |
| Testing and Quality Assurance | 15,000 |
| Project Management | 30,000 |
| Contingency Reserve | 15,000 |
| Total Budget | 250,000 |

### Technology Resources

- Passenger flow monitoring software

- Data analytics platform

- Digital display systems

- Cloud-based databases

- Mobile application platform

### Resource Justification

Effective resource allocation ensures that the project has the people, funding, and technology required to achieve its objectives. Human resources provide the skills needed for project delivery, financial resources support implementation activities, and technology resources enable the operation of the digital system. Appropriate allocation and monitoring of resources help improve efficiency and reduce the risk of project delays or budget overruns (PMI, 2021).

The budget estimates were developed based on the expected costs of software development, technology infrastructure, staff training, testing activities, and project management requirements. According to Kerzner (2022), realistic cost estimation is essential for effective budget control and resource planning. A contingency reserve of £15,000 has also been included to address unforeseen costs and reduce the risk of budget overruns during project implementation.

## 9. Risk Analysis

Risk is a natural feature of projects because projects involve uncertainty and change (PMI, 2021). The Week 1 and Week 5 modules emphasise that effective risk management is necessary to improve project outcomes.

### Risk Register

Table 10: Risk Management Register for Project Implementation

| Risk | Probability | Impact | Risk Rating | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| System Failure | Medium | High | High | Backup systems and testing |
| Budget Overrun | Medium | High | High | Cost monitoring and contingency fund |
| Delayed Development | Medium | High | High | Agile monitoring and milestone reviews |
| Cybersecurity Threats | High | High | Very High | Security audits and encryption |
| Staff Resistance | Medium | Medium | Medium | Training and communication |
| Supplier Delays | Medium | Medium | Medium | Alternative suppliers |
| Data Integration Problems | Medium | High | High | Early testing and technical reviews |
| Regulatory Compliance Issues | Low | High | Medium | Compliance monitoring |

Cybersecurity threats have been rated as a very high risk because the project relies on digital platforms, cloud-based databases, and real-time information sharing. A successful cyberattack could result in data breaches, service disruption, financial losses, and reputational damage for stakeholders. To reduce this risk, security audits, data encryption, access controls, and regular system updates will be implemented. In addition, backup systems and incident response procedures will be established to ensure service continuity in the event of a cybersecurity incident.

### Risk Assessment Matrix

Table 11: Probability and Impact Matrix for Risk Analysis

| Impact / Probability | Low | Medium | High |
| --- | --- | --- | --- |
| High Impact | Medium | High | Very High |
| Medium Impact | Low | Medium | High |
| Low Impact | Low | Low | Medium |

### Project Triangle (Iron Triangle)

The Iron Triangle demonstrates the relationship between scope, time, cost, and quality. Changes in one area often affect the others. The project manager must balance these constraints to achieve project objectives.

Application to the Project

Scope

- Digital monitoring platform

- Real-time passenger information system

- Logistics coordination tools

Time

- Six-month implementation schedule

Cost

- Budget limited to £250,000

Quality

- Reliable, secure, user-friendly system

Failure to effectively balance these factors may result in project delays, budget overruns, or reduced service quality (Kerzner, 2022).

### Leadership and Risk Management

Week 8 highlights that project managers must act as both managers and leaders. Managing resources alone is insufficient; project managers must motivate teams, resolve conflicts, and communicate effectively with stakeholders. Situational leadership is particularly suitable because project requirements change throughout the lifecycle (Müller, Drouin and Sankaran, 2021).

### Global Project Considerations

Although this project is locally focused, global project management principles remain relevant. Week 9 highlights the importance of cultural awareness, communication, stakeholder diversity, and risk management in project environments. Digital technology suppliers may operate internationally, requiring effective communication and collaboration across organisational and cultural boundaries (Briscoe, Schuler and Tarique, 2022; Hofstede, Hofstede and Minkov, 2010).

## 10. Conclusion

This project management plan has outlined a structured approach for delivering the Digital Modernisation of Passenger Flow and Logistics Coordination Project. The project provides a practical and cost-effective solution to the challenges created by the transport hub closure by improving passenger flow, communication, and logistics coordination.

Project management tools, including scope management, the WBS, Gantt Chart, stakeholder analysis, resource allocation, and risk management, have been applied to support effective project delivery. Although risks such as cybersecurity threats, budget overruns, and project delays exist, appropriate mitigation strategies have been identified.

Overall, the project is expected to deliver significant benefits to stakeholders, improve operational efficiency, and support digital transformation objectives. Therefore, effective planning, stakeholder engagement, and resource management will be critical to achieving the project objectives within the agreed time, cost, and quality constraints.

# Refrences:

Association for Project Management (APM) (2023) APM Body of Knowledge. 8th edn. Buckinghamshire: Association for Project Management.

Briscoe, D.R., Schuler, R.S. and Tarique, I. (2022) International Human Resource Management: Policies and Practices for Multinational Enterprises. 6th edn. London: Routledge.

Hofstede, G., Hofstede, G.J. and Minkov, M. (2010) Cultures and Organizations: Software of the Mind: Intercultural Cooperation and Its Importance for Survival. 3rd edn. New York: McGraw-Hill.

Kerzner, H. (2022) Project Management: A Systems Approach to Planning, Scheduling, and Controlling. 13th edn. Hoboken, NJ: Wiley.

Lock, D. (2020) Project Management. 11th edn. London: Routledge.

Maylor, H. and Turner, N. (2022) Project Management. 5th edn. Harlow, England: Pearson.

Müller, R., Drouin, N. and Sankaran, S. (2021) Balanced Leadership: Making the Best Use of Personal and Team Leadership in Projects. New York: Oxford University Press.

PeopleCert (2023) Managing Successful Projects with PRINCE2®. 7th edn. Nicosia: PeopleCert.

Project Management Institute (PMI) (2021) A Guide to the Project Management Body of Knowledge (PMBOK® Guide). 7th edn. Newtown Square, PA: Project Management Institute.

Schwalbe, K. (2019) Information Technology Project Management. 9th edn. Boston, MA: Cengage Learning

Turner, J.R. (2014) Handbook of Project-Based Management: Leading Strategic Change in Organizations. 4th edn. New York: McGraw-Hill Education

European Commission (2020) Sustainable and Smart Mobility Strategy – Putting European Transport on Track for the Future. Brussels: European Commission. Available at: https://eur-lex.europa.eu/legal-content/EN/TXT/HTML/?uri=CELEX%3A52020DC0789 (Accessed: 4 June 2026).

Department for Transport (2023) Transport data strategy: innovation through data. Available at: https://www.gov.uk/government/publications/transport-data-strategy-innovation-through-data (Accessed: 4 June 2026).

United Nations (2023) The Sustainable Development Goals Report 2023. New York: United Nations. Available at: https://unstats.un.org/sdgs/report/2023/ (Accessed: 4 June 2026).

University of Wales Trinity Saint David (2026) LCLM5003 Assessment Brief May–June 2026. Swansea: UWTSD.

University of Wales Trinity Saint David (2026a) Week 1: Introduction to Project Management. Swansea: UWTSD.

University of Wales Trinity Saint David (2026b) Week 2: Project Scope and Planning. Swansea: UWTSD.

University of Wales Trinity Saint David (2026c) Week 3: Quad Chart and Stakeholder Analysis. Swansea: UWTSD.

University of Wales Trinity Saint David (2026d) Week 5: Project Life Cycle and Project Triangle. Swansea: UWTSD.

University of Wales Trinity Saint David (2026e) Week 7: A Spectrum of Project Management Roles. Swansea: UWTSD.

University of Wales Trinity Saint David (2026f) Week 8: Managing and Leading in Project Environments. Swansea: UWTSD.

University of Wales Trinity Saint David (2026g) Week 9: Project Management in a Global Context. Swansea: UWTSD.