David Deeth (2223671)

UWTSD | 10/01/2025

Project Planning

Assignment 1 – Task 3

“Task 3 - Allocate resources to all the activities in the work programme. Develop, evaluate and produce site specific reports for time, cost and resources of the work activities.”

For this project I created a Gantt chart based on references from the project template found at:

https://www.b4ubuild.com/resources/schedule/6kproj.shtml

Then I generated and assigned the materials to the tasks.

REPORTS:

COST OVERVIEW

PROJECT OVERVIEW

% Complete

Status for all top-level tasks. To see the status for subtasks, click on the chart and update the outline level in the Field List.

LATE TASKS

Tasks that are past due.

| Name | Start | Finish | Duration | % Complete | Resource Names |
| --- | --- | --- | --- | --- | --- |
| Set roof trusses | Mon 23/12/24 | Tue 24/12/24 | 2 days | 99% | Carpenter Supervisor,Carpenter 1,Plant Opperator,Telehandler 9m p/week[1] |
| install windows & doors | Wed 08/01/25 | Mon 13/01/25 | 4 days | 25% | Carpenter 1,Carpenter Supervisor |
| exterior finishes | Wed 08/01/25 | Tue 18/02/25 | 30 days | 0% | Bricklayer Supervisor,Bricklayer 1,Plasterer 1,Labourer 1,Cement Mixer Diesel p/week[1],Mortar p/m3[40] |

COST STATUS - TASKS

Cost status for top level tasks.

| Name | Actual Cost | Remaining Cost | Baseline Cost | Cost | Cost Variance |
| --- | --- | --- | --- | --- | --- |
| Oversee Project | £56,933.76 | £0.00 | £0.00 | £56,933.76 | £56,933.76 |
| SETOUT | £208.24 | £0.00 | £0.00 | £208.24 | £208.24 |
| Clear site area | £1,275.84 | £0.00 | £0.00 | £1,275.84 | £1,275.84 |
| Erect site perimiter & compound | £963.84 | £0.00 | £0.00 | £963.84 | £963.84 |
| Erect perimiter | £275.00 | £0.00 | £0.00 | £275.00 | £275.00 |
| Set-out for excavation | £481.92 | £0.00 | £0.00 | £481.92 | £481.92 |
| Clear & stockpile top soil | £690.72 | £0.00 | £0.00 | £690.72 | £690.72 |
| Excavate foundation | £1,472.16 | £0.00 | £0.00 | £1,472.16 | £1,472.16 |
| Layout footings | £208.24 | £0.00 | £0.00 | £208.24 | £208.24 |
| Pour footings | £10,390.72 | £0.00 | £0.00 | £10,390.72 | £10,390.72 |
| Stackout blocks & establish mortar mixing area | £3,783.76 | £0.00 | £0.00 | £3,783.76 | £3,783.76 |
| Build blockwork foundation | £10,737.64 | £0.00 | £0.00 | £10,737.64 | £10,737.64 |
| DPM & drainage services | £720.00 | £0.00 | £0.00 | £720.00 | £720.00 |
| Framing | £103,664.80 | £0.00 | £0.00 | £103,664.80 | £103,664.80 |
| Set roof trusses | £732.96 | £0.00 | £0.00 | £732.96 | £732.96 |
| Frame roof | £41,832.40 | £0.00 | £0.00 | £41,832.40 | £41,832.40 |
| Roofing | £81,832.40 | £0.00 | £0.00 | £81,832.40 | £81,832.40 |
| install windows & doors | £366.48 | £1,099.44 | £0.00 | £1,465.92 | £1,465.92 |
| install services | £0.00 | £10,417.60 | £0.00 | £10,417.60 | £10,417.60 |
| exterior finishes | £0.00 | £17,870.80 | £0.00 | £17,870.80 | £17,870.80 |
| floor finishes | £0.00 | £6,474.72 | £0.00 | £6,474.72 | £6,474.72 |
| paint & decorate | £0.00 | £2,915.36 | £0.00 | £2,915.36 | £2,915.36 |
| install fixtures & hardware | £0.00 | £6,882.40 | £0.00 | £6,882.40 | £6,882.40 |
| Landscaping | £0.00 | £3,035.04 | £0.00 | £3,035.04 | £3,035.04 |
| Final inspection | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| clean down | £0.00 | £963.84 | £0.00 | £963.84 | £963.84 |
| take down perimiter fencing & compound | £0.00 | £481.92 | £0.00 | £481.92 | £481.92 |
| handover | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |

COST STATUS - REASOURCES

| Name | Actual Cost | Remaining Cost | Baseline Cost | Cost | Cost Variance |
| --- | --- | --- | --- | --- | --- |
| MANAGEMENT | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Project Manager | £21,582.08 | £0.00 | £0.00 | £21,582.08 | £21,582.08 |
| Project Engineer | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Site Foreman | £14,227.20 | £0.00 | £0.00 | £14,227.20 | £14,227.20 |
| H&S Officer | £21,124.48 | £0.00 | £0.00 | £21,124.48 | £21,124.48 |
| Architect | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| WORKFORCE | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Groundworker 1 | £1,133.44 | £1,416.80 | £0.00 | £2,550.24 | £2,550.24 |
| Groundworker 2 | £1,056.00 | £1,320.00 | £0.00 | £2,376.00 | £2,376.00 |
|  | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Carpenter Supervisor | £4,651.52 | £5,460.48 | £0.00 | £10,112.00 | £10,112.00 |
| Carpenter 1 | £3,777.52 | £4,434.48 | £0.00 | £8,212.00 | £8,212.00 |
|  | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Bricklayer Supervisor | £2,640.00 | £5,280.00 | £0.00 | £7,920.00 | £7,920.00 |
| Bricklayer 1 | £2,242.80 | £4,485.60 | £0.00 | £6,728.40 | £6,728.40 |
| Electrician 1 | £0.00 | £3,272.00 | £0.00 | £3,272.00 | £3,272.00 |
| Electrician 2 | £0.00 | £3,163.20 | £0.00 | £3,163.20 | £3,163.20 |
| Plasterer 1 | £0.00 | £4,488.00 | £0.00 | £4,488.00 | £4,488.00 |
| Labourer 1 | £2,581.52 | £5,275.28 | £0.00 | £7,856.80 | £7,856.80 |
| Labourer 2 | £2,208.00 | £2,976.00 | £0.00 | £5,184.00 | £5,184.00 |
| Plumber 1 | £400.00 | £4,000.00 | £0.00 | £4,400.00 | £4,400.00 |
| Plumber 2 | £320.00 | £3,200.00 | £0.00 | £3,520.00 | £3,520.00 |
| Plant Opperator | £936.32 | £819.28 | £0.00 | £1,755.60 | £1,755.60 |
| PLANT | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Excavator 5T p/week | £900.00 | £300.00 | £0.00 | £1,200.00 | £1,200.00 |
| Telehandler 9m p/week | £0.00 | £300.00 | £0.00 | £300.00 | £300.00 |
| Cement Mixer Diesel p/week | £0.00 | £130.00 | £0.00 | £130.00 | £130.00 |
| MATERIALS | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Heras Fencing p/week | £275.00 | £0.00 | £0.00 | £275.00 | £275.00 |
| Steel p/m2 | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Concete p/m3 | £10,000.00 | £0.00 | £0.00 | £10,000.00 | £10,000.00 |
| Brick /Block Cavity Wall p/m2 | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Bricks p/m2 | £0.00 | £0.00 | £0.00 | £0.00 | £0.00 |
| Blocks p/2 | £6,500.00 | £0.00 | £0.00 | £6,500.00 | £6,500.00 |
| Mortar p/m3 | £15.00 | £120.00 | £0.00 | £135.00 | £135.00 |
| Timber p/m2 | £220,000.00 | £0.00 | £0.00 | £220,000.00 | £220,000.00 |

References:

https://uk.indeed.com/career/construction-project-manager/salaries/Wales

https://uk.indeed.com/career/construction-project-engineer/salaries/Wales

https://uk.indeed.com/career/construction-foreman/salaries/Wales

https://uk.indeed.com/career/construction-safety-manager/salaries/Wales

https://uk.indeed.com/career/architect/salaries/Wales?from=top_sb

https://uk.indeed.com/career/groundworker/salaries/Wales

https://uk.indeed.com/career/carpenter/salaries/Wales?from=top_sb

https://uk.indeed.com/career/carpenter-supervisor/salaries/Wales

https://uk.indeed.com/career/brick-mason/salaries/Wales

https://uk.indeed.com/career/builder/salaries/Wales

https://uk.indeed.com/career/electrical-supervisor/salaries/Wales

https://uk.indeed.com/career/electrician/salaries/Wales

https://uk.indeed.com/career/plasterer/salaries/Wales?from=top_sb

https://uk.indeed.com/career/laborer/salaries/Wales?from=top_sb

https://uk.indeed.com/career/plant-operator/salaries/Wales

https://www.checkatrade.com/blog/cost-guides/ready-mix-concrete-cost/

Brick & block cavity wall /m2

https://www.checkatrade.com/blog/cost-guides/cost-build-brick-wall/

https://www.mybuilder.com/bricklaying-repointing/price-guides/brick-wall-costs

https://www.checkatrade.com/blog/cost-guides/breeze-block-wall-cost/

https://www.b4ubuild.com/resources/schedule/6kproj.shtml

https://www.lakeside-hire.co.uk/security-fencing-for-hire/temporary-heras-fencing/

https://www.checkatrade.com/blog/cost-guides/concrete-pouring-cost/

https://www.chaseplanthire.com/prices/

https://www.toolhirecentre.co.uk/telehandlers

https://www.nationaltoolhireshops.co.uk/product/diesel-cement-mixer-hire/

https://www.toolhirecentre.co.uk/excavators