EXERCISE 2

We would like to know if we are able to tender for a project of a school construction. We have already calculated our estimated costs. The information that we have is as follows:

Estimated cost of works: £1.2 million

Duration: 12 months

Expected profit: 8%

Retention: 5%

Payments: 1 month after valuation

Interest for credit: 7% (locked-up capital completely supplied by the bank)

| Month | Cost |
| --- | --- |
| 1 | £20,000 |
| 2 | £50,000 |
| 3 | £100,000 |
| 4 | £130,000 |
| 5 | £150,000 |
| 6 | £180,000 |
| 7 | £140,000 |
| 8 | £130,000 |
| 9 | £120,000 |
| 10 | £100,000 |
| 11 | £50,000 |
| 12 | £30,000 |

We would like to know if this project will be profitable or not. Analyse it and explain your conclusions with a cashflow diagram.