## Sheet1
Measuring and estimating Assignment 2
Cost building based on Gross Internal Floor area for the existing and new building
GIFA Extension
| 4.62 x 1.515 = | 7.02m2 |  | Measurements taken with scale ruler from floor plans
| 3.01 x 2.87 = | 8.64m2
| 3.03 x x 1.5 = | 4.52m2
| 1.76 x 1.75 = | 3.08m2
| TOTAL | 23.26m2
GIFA Existing
| 7.56 - 0.6 = | 6.96LM | (length)
| 6.17 - 0.6 = | 5.57LM | (width)
| TOTAL | 38.77 x 2 = | 77.54m2 | Double quantity as 2 story building
Cost of extension
| 23.26 x 1350 = | 31401 |  | Based on 'local authority and housing association schemes' semi detatched bungalow as very similar
Cost of existing buidling
| 77.54 x 1350 = | 104679 |  | Based on 'local authority and housing association schemes' two storey detached house
Measure the external envelope of the extension to the house for (inner skin 200mm blockwork insulation 75mm thick 30mm cavity and 200mm Blockwork outer skin)
Centreline calculations
External blockwork
External wall perimeter - 30.06LM
2 x 4 x 0.5 x 200 = 800mm
| 30.06 - 0.8 = 29.26LM | Centreline
| 29.26 - 0.8 = 28.46LM | Internal face of external wall
Cavity
2 x 4 x 0.5 x 30 = 120mm
| 28.46 - 0.12 = 28.34LM | Centreline
| 28.34 - 0.12 = 28.22LM | External face of insulation
Insulation
2 x 4 x 0.5 x 75 = 300mm
| 28.22 - 0.3 = 27.92LM | Centreline
| 27.92 - 0.3 = 27.62LM | External face of internal wall
Internal blockwork
2 x 4 x 0.5 x 200 = 800mm
| 27.62 - 0.8 = 26.82LM | Centreline
Area Calculations
External wall area
29.26 x 2.35 = 68.76m2
Additionals
Gable end - 1.4m2
Lean to (side) - 0.7m2
Lean to (rear) - 0.9m2
TOTAL
71.76m2
-
Cavity area
28.34 x 2.35 = 66.60m2
Additionals
Gable end - 1.4m2
Lean to (side) - 0.7m2
Lean to (rear) - 0.9m2
TOTAL
69.6m2
-
Insulation
27.92 x 2.35 = 65.61m2
Additionals
Gable end - 1.4m2
Lean to (side) - 0.7m2
Lean to (rear) - 0.9m2
TOTAL
68.61m2
-
Internal wall
26.82 x 2.35 = 63.03m2
Additionals
Gable end - 1.4m2
Lean to (side) - 0.7m2
Lean to (rear) - 0.9m2
TOTAL
66.03m2
-
Measure the roof of the existing house for tiles
3.6LM x 7.8LM = 28.1m2
28.1 x 2 = 56.2m2
-
Produce a Bill of Quantities for the external envelope and tiles
Code | Description | Amount | Unit | Rate | Total
14.02 | High strength concrete blocks (7N); Thermalite High Strength 7 blocks or other equal and approved; in cement mortar (1:3) 200mm thick | 71.76 | m2 | 46.57 | 3341.8632 | External wall
14.02 | High strength concrete blocks (7N); Thermalite High Strength 7 blocks or other equal and approved; in cement mortar (1:3) 200mm thick | 66.03 | m2 | 46.57 | 3075.0171 | Internal wall
31.01 | Kingspan Thermawall TW50 (Thermal conductivity 0.022 W/mK) High performance rigid thermoset polyisocyanurate (PIR) insulant or other equal and approved; as partial cavity fill; including cutting and fitting around wall ties and retaining discs | 68.61 | m2 | 20.53 | 1408.5633 | Cavity insulation
14.07 | Forming cavities in hollow walls - width of cavity 100 mm; galvanized steel twisted wall ties; five wall ties per m2 | 69.6 | m2 | 4.29 | 298.584 | Rate pro rata from 75mm cavity and 3 ties per m2// Value x 1.66 (5 wall ties) x 1.33 (100mm)
18.03 | Concrete interlocking tiles; Marley Eternit Ludlow Major granule finish tiles or other equal; 75 mm lap; on 25 mm × 38 mm battens and type 1F reinforced underlay | 56.2 | m2 | 21.24 | 1193.688 | Roofing tiles