## Slide 1: BA (Hons) Leadership and Management Skills for the Workplace Module: Managing Projects in the Organisation. Module code: BMSW 5104 Student: Rupia Hussain-ID: 2010133 Lecturer: Charles Nwaogwugwu Assignment Title: Presentation- Proposal of Project Management Plan

## Slide 2
Table of Contents
What is Project Management
Introduction to project- Revamp
Project Statement
Quad Chart
Stakeholders and Communication plan
Work Breakdown Structure
Cost Breakdown Structure
Risks Identification and Risks Register
Risk Management- Matrix and Contingency Plan
Evaluation
Recommendations
References
Appendix

## Slide 3: What is a Project Management
A group of people assembled with necessary quality and skills to work together to achieve common goal or an objective, for or within an organisation.
Project life cycle - Start and End.
Project phases: planning, initiation, execution, monitoring and closing of the project.
Project has 3 major constrains:
Scope: refers to deliverables and tasks needs doing to achieve the goal.
Cost: total amount required to complete a project. Or can be fix budget to complete the project within the budget.
Time: to complete projects or given fix time to a project it’s also called the work schedule (Coursera, n.d.).

## Slide 4
The project is motivated by Covid-19 Pandemic.
Children gaining weight:- prone to illness, such as non-alcoholic fatty liver disease, diabetes type 2 and cardiovascular disease (Lubrecht et al., 2022).
Netflix sales went up by 16 millions (Thomas, 2020).
Gaming sales increased by 30% only in the first 3 months into lockdown (Morris, 2021).
Bromley Health Club - Project Revamp
Increase Health Club Subscriptions

## Slide 5
Project Statements
Key Objective- Targeted for children 11-16 years,
Introduce children to physical activity
12 weeks project
2 hours weekly
Team consist of project manager, fitness instructors, nutrition
Major deliverables:- Approval, Assembling of team, advertising, Activation, Monitoring.
Milestones:- 1. Reaching Activation. 2. Reaching Evaluation. 3. Ending
Encourage to join Health club

## Slide 6: The Quad Chart- Revamp
Objectives Create health-conscious mind Promote healthy lifestyle Tackle overweight/obesity Make Physical activity fun Encourage subscription to health club | Stakeholders Health club Instructors Parents/Guardians Children Other club users
Desired end results Demands for more similar project Joining health club Being more health conscious Continuing health programs Adapting to healthy living styling | Measures of success Children enjoying the physical activities Parents and children showing interest to similar projects Increased monthly/yearly contracts Positive feedbacks

## Slide 7: Stake holder Analysis and Communication Plan
Instructors- meetings every 2 weeks and each milestones
Health club- email update on reaching the milestones and Projective Activations- every 4 week
Parents- email updates with all relevant information at the start and when required, any change happens
Club users- advance notice display of any event / Class/ room change when required.
Children- Send emails once with activity details

## Slide 8: Work Breakdown Structure – Project Revamp
Task- Deliverables: Work Packs | Description | Date
1. Approval WP- 1.1. Senior approval | Contact line manager. Discus plans and get signed approval. Arranging funding from account department | Beginning March. 2 weeks
2. Assigned Team WP- 2.1. fix date and time, Hall | funding authorised, assign instructors/ assistants, decide date and times slots. Allocate hall, finalize, organize equipment. | 2 Weeks
3. Advertising WP- 3.1. Link online registration | Printing flyers, poster around the health club. Design online registration forms. | March 4 Weeks
Achievement of | First Milestone | April
4. Activation of the projects WP- 4.1. Meeting children | Introducing project, duration, activities, explain the objectives of the projects. | 6 Weeks. May
5. Monitoring WP- 5.1. Activities effectiveness | Observing interaction to the activities children are doing. | 6 Weeks. May
Achievement of | Second Milestone | June
6. Evaluations- 12 weeks WP- 6.1. Children/Parent feedbacks. | Collect feedbacks, encourage stay healthy and active. | 1 week
7. Ending- Revamp WP-7.1. measuring the success | Reporting overall achievements of the projects, improvements, closing of the projects. | 1 Week End of June

## Slide 9
Cost Breakdown Structure |  | Resources | Cost- Total £ 1,960
Team leader- £15.50 hour | Rupia | Access to all IT materials, admin systems | 290
Fitness Instructor -£14.70 hour | Elena | Physical activity Equipment-ball mats, rackets, rope, cones, timers, whistle. Sanitations materials | 550
Assistants coach- £13.50 hour | Andrew |  | 
Nutrition- £12.30 hour | Ana | Online resource, printing, water supply | 370
Advertising – £11. 25 hour | Maria | Printer, papers, online access | 750

## Slide 10: Risks Identification and Risks Register
Risks | Chance | Trigger | Impact | Mitigation
1. Spread of Covid | likely | Hygiene | Shut down | Use gels/wipes
2. Accidents | likely | In proper use of equipment | Cost to health club | Supervision. clear instructions
3. Staff of sick | low | Covid and general health | Reducing activity | book bank staff/instructor
4. Funding | low | Change in activity/ miss calculations | Reducing activity | Stay with the plan and budget
5. High many interest | Most likely | It free, too many interests | Costs rise, difficult to manage | Limit registrations, first come basis

## Slide 11: Risks Managements - Matrix and Contingency Plan
Email reminder to parents to check health day before.
Have Covid- testing kit available
Brief children the rules every session.
Book bank staff
Continuous monitoring of risks to eliminate existing or prevent of new risks

## Slide 12: Evaluation- project Revamp
Activities suitability- not all activities was not suitable for older children
Nutrition advise- some talk session was too long, less attractive to children
Sessions duration- 2 hours needs reviewing
Duration of project- 12 weeks was adequate to get understanding the need of staying active
achieve the objectives, encourage children stay active, like before the covid-19
Have more various skilled team members
Project did not have necessary time for marketing

## Slide 13: Recommendations
Keeping the nutrition talk short- making more interactive, fun, get kids involved
Variety of games- suitable for all ages
Project success- project has popularity should be run more often: holidays
Run similar project to encourage people to join the health club
Give away goodies reminder of the project
Increase work team and project size
Revamp
Revamp
Revamp

## Slide 14
Reference
1. Coursera. (n.d.). What Is the Project Management Triangle? [online] Available at: https://www.coursera.org/articles/project-management-triangle?isNewUser=true&showOnboardingModal=1 [Accessed 29 Nov. 2022].
2. Lubrecht, J., Arayess, L., Reijnders, D., Hesselink, M.L., Velde, G. ten, Janse, A., von Rosenstiel, I., van Mil, E.G.A.H., Verweij, M. and Vreugdenhil, A.C.E. (2022). Weight Gain in Children during the COVID-19 Pandemic and the Protective Effect of Lifestyle Intervention in Children with Obesity. Obesity Facts, 15(4), pp.600–608. doi:10.1159/000525298 [Accessed 14 Nov. 2022].
3. MORRIS, C. (2021). One year into the pandemic, video game sales aren’t slowing down. [online] Fortune. Available at: https://fortune.com/2021/04/16/video-game-march-sales-npd-monster-hunter-rise-ps5/ [Accessed 14 Nov. 2022].
3. Thomas, Z. (2020). Netflix Adds 16 Million sign-ups in Lockdown Boost. BBC News. [online] 22 Apr. Available at: https://www.bbc.co.uk/news/business-52376022 [Accessed 14 Nov. 2022].

## Slide 15: Thank you for listening, any questions??