## Sheet1
Exercise 2 Review. Control procedures
As Programmed | [11 empty] | As Built
Action | Budget | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 |  | Action | Budget | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Total
1 | 60000 | Week 1: 20000; Week 2: 20000; Week 3: 20000 | 60000 | 1 | 60000 | 20000 | 30000 | 10000 | [6 empty] | 60000
2 | 12000 | Week 4: 6000; Week 5: 6000 | 12000 | 2 | 12000 |  |  |  | 6000 | 5000 | 1000 |  |  |  | 12000
3 | 250000 | Week 4: 50000; Week 5: 50000; Week 6: 50000; Week 7: 50000; Week 8: 50000 | 250000 | 3 | 250000 |  |  |  | 20000 | 50000 | 50000 | 40000 | 40000 | 40000 | 240000
4 | 90000 | Week 6: 10000; Week 7: 10000; Week 8: 10000; Week 9: 10000 | 40000 | 4 | 90000 | [5 empty] | 5000 | 10000 | 10000 | 10000 | 35000
5 | 80000 | Week 4: 16000; Week 5: 16000; Week 6: 16000; Week 7: 16000; Week 8: 16000 | 80000 | 5 | 80000 |  |  | 5000 | 13000 | 16000 | 14000 | 16000 | 16000 |  | 80000
6 | 75000 | Week 9: 25000 | 25000 | 6 | 75000 | [8 empty] | 15000 | 15000
7 | 360000 | [9 empty] | 0 | 7 | 360000 | [9 empty] | 0
8 | 80000 | [9 empty] | 0 | 8 | 80000 | [9 empty] | 0
9 | 50000 | [9 empty] | 0 | 9 | 50000 | [9 empty] | 0
10 | 160000 | [9 empty] | 0 | 10 | 160000 | [9 empty] | 0
Total |  | 20000 | 20000 | 20000 | 72000 | 72000 | 76000 | 76000 | 76000 | 35000 |  | Total |  | 20000 | 30000 | 15000 | 39000 | 71000 | 70000 | 66000 | 66000 | 65000
Total cumulative |  | 20000 | 40000 | 60000 | 132000 | 204000 | 280000 | 356000 | 432000 | 467000 |  | Total cumulative |  | 20000 | 50000 | 65000 | 104000 | 175000 | 245000 | 311000 | 377000 | 442000
Variance |  | 0 | -10000 | -5000 | 28000 | 29000 | 35000 | 45000 | 55000 | 25000
Graph analysis:
Explain how resources (money) is spent and delay ocurring in this project
This delay peak is in week 8, week 9 is remediating this delay but not enough
Per activity, it can be identified that actions 3, 4 and 6 are delayed
Meetings with subcontractors for these activities should be held so that it can be corrected and the final end of works is not affected