## Question
A typical Bill of Quantities is provided below :
Ref. | Description | Quantity | Units | Rate | Value
S100 – PRELIMINARIES
Temporary accommodation: The contractor is to allow here for facilities to maintain an ongoing presence over a two year period even when no capital works are ongoing
1.1.1 | Erection of portable offices for the Project Manager until completion of the Works | 1 | item | 0 | 0
1.1.2 | Erection of portable offices for the Project Manager after completion of the Works | 1 | item | 0 | 0
1.1.3 | Erection of offices and messes for the Contractor | 1 | item | 0 | 0
1.1.4 | Erection of stores and workshops for the Contractor | 1 | item | 25000 | 25000
1.1.5 | Servicing of portable offices for the Project Manager until completion of the works | 1 | item | 6000 | 6000
1.1.6 | Servicing of portable offices for the Project Manager after completion of the works | 40 | wk. | 25 | 750
1.1.7 | Servicing of offices and messes for the Contractor | 1 | item | 75000 | 75000
1.1.8 | Servicing of stores and workshops for the Contractor | 1 | item | 100000 | 100000
1.1.9 | Dismantling of portable offices for the Project Manager until completion of the works | 1 | item | 0 | 0
1.1.10 | Dismantling of portable offices for the Project Manager after completion of the works | 1 | item | 0 | 0
1.1.11 | Dismantling of offices and messes for the Contractor | 1 | item | 0 | 0
1.1.12 | Dismantling of stores and workshops for the Contractor | 1 | item | 0 | 0
During the course of the contract and to allow for further development of the site, it may become necessary for the contractor to move the Project Manager’s
and his own site compound and accommodation to an alternative location within the development. Allow here for
1.1.13 | Dismantling of Project Manager’s offices and toilet facilities, transporting to an alternative location and re-erection of same. | 1 | item | 500 | 500
1.2.14 | Dismantling of contractors offices, messes, stores, workshops and compound complete with all stored plant and materials, transporting to an alternative location | 1 | item | 3000 | 3000
and re-erection of same.
Scaffolding
1.2.15 | Bringing to site of access scaffolding | 1 | item | 200 | 200
1.2.16 | Hiring of scaffolding | 15 | wk. | 550 | 8250
1.2.17 | Dismantling of scaffolding and removal from site | 1 | item | 200 | 200
S200 – SITE CLEARANCE
Site Clearance
2.1.3 | General site clearance | 0.17 | ha | 100 | 17
Take Up or Down and Set Aside for Reuse or Remove to Store off Site
2.1.4 | Take up or down and remove to tip off site lighting column including breaking out foundation and backfilling with imported type 1 material | 4 | nr | 140 | 560
2.1.5 | Take up or down and remove to tip off site street sign including breaking out foundation and backfilling with imported type 1 material | 1 | nr | 40 | 40
S500 – Drains and Service Ducts (Excluding Filter Drains, Narrow Filter Drains and Fin Drains
2.2.1 | Service duct; 100 diameter; two ducts, depth to invert not exceeding 2m, average depth 725mm ; construction in trench | 500 | m | 15 | 7500
2.2.2 | Service duct; 100 diameter; four ducts, depth to invert not exceeding 2m, average depth 625mm ; construction in trench | 250 | m | 25 | 6250
Chambers and Gullies
2.2.3 | PC Sum - Precast concrete chamber type JB4 (BT Reference) with recessed cover and frame depth to uppermost surface of base slab exceeding 1.0 metre for WDA Broadband | 4 | nr | 850 | 3400
2.2.4 | Precast concrete chamber type JB4 (BT Reference) with recessed cover and frame depth to uppermost surface of base slab not exceeding 1.0 metre for NTL | 4 | nr | 850 | 3400
2.2.5 | PC Sum - Precast concrete chamber with recessed cover and frame depth to uppermost surface of base slab not exceeding 1.0 metre for British Telecom | 5 | nr | 950 | 4250
S1300 - Road Lighting Columns and Brackets
2.3.1 | Lighting column; 450mm diameter sleeve 1400mm deep below underside of surfacing; Item coverage as series 1300, paragraph 4, items g-I and k-o | 8 | nr | 250 | 2000
S1400 - Locating Buried Road Lighting and Traffic Signs Cable
2.4.1 | Locating Buried Road Lighting and Traffic Signs Cable in carriageways, footways, bridge decks and paved areas | 10 | m | 5 | 50
Trench for Cable or Duct
2.4.2 | Trench for duct exceeding 300mm but not exceeding 450mm wide; depth not exceeding 1.5 metres in carriageways, footways, and paved areas | 250 | m | 8 | 2000
S1400 - Cable and Duct
Trench for Cable or Duct
2.4.3 | Trench for cable; 600 wide; trench depth not exceeding 1.5m; in carriageways, footways and paved areas | 300 | m | 12 | 6000
| Trench for gas main; 600 wide; trench depth not exceeding 1.5m; in carriageways, footways and paved areas | 125 | m | 12 | 1500
2.4.4 | Trench for water main; 600 wide; trench depth not exceeding 1.5m; in carriageways, footways and paved areas | 125 | m | 12 | 1500
|  |  |  | Contract Sum | 257367
Adjust BoQ for unagreed Variations as follows:
1 | Architects Instruction No. 101: Omit - the PC sum of £950.00 (2/2/5) for the supply of precast concrete chamber. Add – Enter into a supplier contract with A. Chamber in accordance with their quotation for the sum of £770.00 nett.
2 | Architects Instruction No. 102: the subcontractor to amend the service duct (2/2/2) to be installed in accordance with their quotation for the additional sum of £10.00 per meter inclusive of 3.5% discount to the main contractor.
3 | Architects Instruction No. 103: Due to new information on the ground conditions. The agreed rate has been increased from £200 to £250.00 for 1/2/15. Given the information provided recalculate the amount received by the contractor inclusive of 3.5%.
4 | Architects Instruction No. 104: The scope of the works of the cabling 2/4/3 has been remeasured and has altered from 300m to 850m.
Under the signed JCT SBC 2016 the contractor ahs negotiated a 7.5% discount for nominated suppliers and 3.5% discount on sub-contractors.

## Additional
Adjust BoQ for further unagreed Variations as follows:
5 | Architects Instruction No. 121: Omit - the PC sum of £850.00 (2/2/3) for the supply of precast concrete chamber. Add – Enter into a supplier contract with C. Chamber in accordance with their quotation for the sum of £950.00 nett.
6 | Architects Instruction No. 122: the subcontractor to amend the service duct (2/2/1) to be installed in accordance with their quotation for the additional sum of £15.50 per meter inclusive of 2.5% discount to the main contractor.
7 | Architects Instruction No. 123: Due to new information on the ground conditions. The agreed rate has been increased from £200 to £300.00 for 1/2/17. Given the information provided recalculate the amount received by the contractor inclusive of 2.5%.
8 | Architects Instruction No. 124: The scope of the works of the cabling 2/4/4 has been remeasured and has altered from 125m to 650m.
Under the signed JCT SBC 2016 the contractor ahs negotiated a 5% discount for nominated suppliers and 2.5% discount on sub-contractors.