Dominique Colette Zanotto (2533083)

Module Title: Problem Solving and Decision Making                                                     Module Code: LCLM 4004 Assessment: Component 2 Report    Basil’s Bakery                                                      Student Name: Dominique Zanotto                       Student Number: 2533083                                    Lecturer Name: Toyin Adisa

Table of contents

1.Executive summary

2.introduction

3.Scope and nature of bakery problems

4. Proposed solutions

4a. Solution 1;

4b. Solution 2;

5. Evaluation and analysis

5a. PMI Analysis for solution 1

5b. PMI Analysis for solution 2

5c. Results and best solution Recommendation

6. Risk analysis for the best solution

7. Implementation plan for the best solution

8. key performance indicators

9. Conclusion.

10. references

1. Executive summary

This report investigates the economic problems at basil’s bakery in Coventry.

The owner-managed shop facing stagnant sale figures and declining foot traffic due to tension between freshness and profitability. Demand varies while production and decision rely mainly on experience. This creates waste, stockout, rush labour and weak margin visibility.

Adopting secondary research and a case study methodology, the report compares two marketing solution to revitalize the brand presence and revenue streams.

The report outlines the scope of Basil’s bakery’s challenges, evaluates two strategic solutions, perform a PMI analysis, and recommends a risk-mitigated implementation plan and Key Performance Indicators (KPIs) provided to ensure measurable success.

2. Introduction

. Problem solving is the process of identify, analysing and resolving the problems of an organization’s ability to achieve its objectives. (Simon,1973)

Effective problem solving replaces intuition with a structured process of cause analysis and continuous improvement within organizations.

. Decision making, in the other hand, is the process of selecting course of action from among multiple alternatives, strategic choice, and find the best option. (Simon, 1960)

It also brings, recognition, diagnosis, evaluation, development and, selection phases in the commitment to action, (Mintzberg, 1973)

According to Kepner & Tregoe, 1965, it is a rational process of evaluating alternatives against established objectives, selecting the option that suits the best while minimising potential risks.

Good decision making is essential because it directly affect probability, competitiveness, and long-term survival of the organization (Harrison, 1999)

The integration of the module in academic literature covers the core concept of problem solving (Newell & Simon,1972 and decision making as selecting optimal solutions (Simon, 1947), providing essential skills for effective management

3. Scope and nature of Basil’s bakery problems

The bakery’s issues are managerial and operational. As the foot traffic is declined, the uncertainty of the demand makes daily batch size difficult. Overproductions create waste, underproduction creates lost sales and disappointed customers. This increase emergency purchases and expose the bakery to supplier delay. The limited brand visibility outside the local community, the inconsistent customer engagement across digital channels, and underutilized online presence with no website traffic or social media interaction is one of the major issue. Food safety, allergen control and customer experience remain non-negotiable. The report focuses on production, purchasing and availability, with marketing use only to shift demand toward planned capacity

4.Proposed solutions

a. social media first campaign;

. Launch a 3-month Instagram and Facebook campaign focusing on user generated content,            behind the scenes baking videos

. Use Instagram stories and reels to showcase the new products and promotions

. Implement a hashtag strategy to encourage community engagement

(#BasilBakery, #FreshFromBasil)

b. Google Ads plus hybrid marketing emails

. Invest in Google search and display Ads targeting local audiences searching for

“Artisan bakery” or “fresh bread near me”

. adopt a weekly email newsletter featuring promotions, recipes, and bakery updates.

. Use Google analytic to track website traffic and conversation rates

5. Evaluation and analysis

PMI analysis for solution 1, Social media first campaign

| Plus | Minus | Interesting |
| --- | --- | --- |
| . Brand awareness; Visibility via viral social media | . Time intensive; Requires consistent content creation | . Platform trends; Instagram reels short video aligns with baking content. |
| . Cost effective; Lower upfront to pay ads | . Staff training; Creative content needs dedicated staff |  |
| . creative flexibility; Showcases bakery’s values (behind the scenes stories) | . ROI uncertainty; Difficult to track direct sales impact without proper analytics | . Users content; Encourage customers to become brand ambassadors |
| . SEO benefits; Hashtags improve organic search visibility | . Algorithm dependence; Organic search decline without paid boosting | . Crisis management; Plan for negative review |
| . Community building; Strengthens customer relationships through engagement. |  |  |
| . Real time feedback; Interaction with customers | Viral backlash; Negative comments can escalate quickly |  |

PMI for solution 2, Google Ads plus hybrid marketing email

| . Targeted reach; Ads focus on local customers content (“fresh bread near me”) | . High costs; Google Ads may be expensive | . Seasonal trends; Campaign is adjusted for events |
| --- | --- | --- |
| . Measurable ROI; Google analytics tracks clicks, sales, and conversations. | . Click fraud; Bots and competitors may increase ad costs. | . Retargeting; Ads can follow website visitors |
| . Email engagement; Newsletters promote repeat visits. | . Email list growth; Require big efforts to expend subscribers | . Local SEO synergy; Google Ads boosts local search ranking over time |
| . Automation; Email sequences (promotion and welcomes) minimal daily effort | . Complexity; Google Ads need expertise (agency costs) |  |
| . Credibility; Google Ads brings you at the top results such (instant visibility) | . Ad fatigue; Over-reliance on paid ads may reduce organic traffic long term |  |
| . Scalability; Spens and adjust based on performance (increase when requested) |  |  |

The result for best solution shows social media firsts builds the brand loyalty through authentic engagement, while email marketing and Google Ads drive direct conversations with measurable ROI. The best solution is a hybrid approach;(70% budget) prioritize social media in the first 3 months to build customer relationship and brand authenticity. Then expand email and Google Ads based on performance data. This balances short time revenue with long term loyalty using Google’s precision targeting with social media storytelling to produce a digital ecosystem that drive to both direct sales and organic growth.

6.Risk analysis for the best solution

| What could cause the risk | Like hood (1-5) | Impact (1-5) | What can you do to reduce the risk | What can you do to minimise the risk |
| --- | --- | --- | --- | --- |
| Budget inefficiency as ads need time | 3 | 4 | Set a budget cap | 30 days test budget |
| System not working together | 3 | 4 | Plan before how all systems connect | Test before launch |
| Team getting too busy | 4 | 3 | Clear plan who do what | Hire expert or agency |
| Google Ads getting expensive | 3 | 4 | Focus on specific keywords | Set a budget limit |
| Hard to see what’s working | 3 | 3 | Decide on one way to measure success | Use special tracking links |
| Social media algorithm | 4 | 3 | Different type of content (9stories, videos) | Stay in touch with customers |
| Brand message mixed up | 2 | 4 | Keep all content in 1 place | Check all messages |

If social media Ads underperform at the beginning, the mismanagement budget could be the main risk. Expert personal in marketing or agency is crucial. Google Ads costs can be managed by focusing on specific keywords and setting a budget cap. Is important to unify a brand guide. Tracking difficulties may occur from different team and inconsistent data across systems , so a single measurement approach and regular comparisons is needed

7. Implementation plan for the best solution

| Action | Description | Time Frame | Staff Responsible |
| --- | --- | --- | --- |
| Define campaign goals | Set clear objective for the digital campaign | Week 1 | Marketing manager |
| Set up social media accounts | Create and optimize Facebook, Insta, google my business | Week1 | Digital creator |
| Prepare content calendar | Plan posts, promotions, and ad content for 4 weeks | Week 1 | Content creator |
| Choose tracking tools | Install Google analytic, Facebook Pixel, and CRM integrations | Week 2 | Manager |
| Run small social media tests | Test ad variation on Insta and Facebook to see what works best | Week 3 | Digital creator |
| Run small Google Ads test | Tests keywords and ad copies on Google Ads to find high-performing options | Week3 | Marketing manager |
| Monitor and adjust ads | Review performance daily and pause underperforming ads, scale the best one | Week 4 | Marketing manager |
| Scale successful campaign | Increase budget for top-performing ads and expand the new audiences | Week5-6 | Digital creator |
| Integrate CRM tools | Ensure customer data flows correctly between ads, website, and sales system | Week 7 | Operations manager |
| Train staff on new tools | Teach team how to use Google analytics, ad platforms, and CRM affectively | Week 8 | Marketing manager |
| Track performance weekly | KPIs (Click, conversations, sales) and adjust strategy as needed | Ongoing (week 9+) | Marketing manager |
| Hold weekly team meeting | Discuss progress, challenges, and next steps to keep everyone align | Ongoing (week 9+) | All team leads |

8.  key performance indicator

| Specific | Measurable | Attainable | Relevant | Time-bound |
| --- | --- | --- | --- | --- |
| Reduce system downtime to <1H/month | Track uptime via monitoring tools | Upgrade redundant servers & failover systems | Ensure 99.9% service availability for clients | Within 4 months |
| Achieve 100% security patch compliance | Patch 100% of critical vulnerabilities | Automate patch deployment process | Maintain regulatory compliance & security | Within 3 months |
| Decrease incident response time to <30minutes | Log & track incident resolution time | Train team on incident response protocols | Improve customer trust & service reliability | Within 5 months |
| Eliminate unauthorize data access | Audit & revoke unused accounts monthly | Implement role-based access control (RBAC) | Protect sensitive customer data | Within 2 months |

9.  Conclusion

Digital marketing presents a transformative opportunity for Basil’s bakery to regain competitivity. By adding a Google Ads and email marketing strategy, supported by a steady social media presence, the bakery may increase visibility, customer engagements and higher sales. Regular performances revies and adaptability will ensure long-term success.

10.  References

Chaffey, D. (2022). Digital business and E-Commerce Management (7th ed.) Pearson.

Kotler, P., & Kotler, K.L (2016). Marketing Management (15th ed.). Pearson.

UK Government. (2023). Small business Costs and Challenges. GOV>UK

Statista. (2024). UK Bakery Industry Report 2024.

Appendices

Risk assessment matrix

Customer feedback survey template