## Sheet1
Task | Date Started | Due Date | Owner | status | Notes | Resources
Painting | 2019-02-01 | 2019-02-05 |  | Not started | oil paint for gates are required | https://docs.google.com/document/d/1t-12UYt0yJw6jZCDr-LQ9Krnj5UsuMzr-fLx4izHNng/edit
Flooring | 2019-03-10 | 2019-03-14 |  | In progress
Window fitting | 2019-01-02 | 2019-01-03 |  | On hold | double glazing required | Window & Door Fitters across the UK ¦ Find Local Window ...
Plumbing | 2019-01-16 | 2019-01-18 |  | Completed |  | Plumbers.World (@plumbers.world) • Instagram photos and ...
Kitchen fitting | 2019-01-20 | 2019-01-21 |  | Completed |  | 75 Beautiful Kitchen Pictures & Ideas - January, 2021 ¦ Houzz
Buying Kitchen Fittings | 2019-01-15 | 2019-01-19 |  | Not started | air stracture is required and table top cooker | Kitchen Fitting & Installation Service ¦ Wickes
Buying Window Fittings | 2019-01-29 | 2019-01-01 |  | On hold |  | Window Fittings ¦ Window Furniture ¦ Screwfix.com
buying flooring fittings | 2019-03-08 | 2019-03-09 |  | In progress |  | Carpet Fitting & Floor Laying Services ¦ Tapi Carpets & Floors